3GPP TSG RAN WG2 Meeting #111-e	R2- 2007565

Electronic meeting, August 17 - 28, 2020

Title:	NR_NTN_solutions work plan

Source:	Thales

Type:	Discussion

For:	Decision

Agenda Item:	8.10

Release:	Rel-17

# Introduction

At the RAN#86 meeting, upon successful completion of the “Study Item on NR support non-terrestrial network” [1], the corresponding work item was approved, with the core part completion by June 2021 (RAN#92), and the RAN4 performance part by December 2021 (RAN#94) [2].

In this contribution, we provide a tentative work plan on the Rel-17 NR-NTN work item. Note that it is provided for informative purposes only.

# WID Objective

The work item aims to specify the enhancements identified for NR NTN (non-terrestrial networks) especially LEO and GEO with implicit compatibility to support HAPS (high altitude platform station) and ATG (air-to-ground) scenarios according to the following principles:

- FDD is assumed for core specification work for NR-NTN.

  - NOTE: This does not imply that TDD cannot be used for relevant scenarios, e.g. HAPS, ATG.

- Earth fixed Tracking area is assumed with Earth fixed and moving cells.

- UEs with GNSS capabilities are assumed.

The detailed objectives are to specify enhancing features to Rel-15 & Rel-16’s NR radio interface & NG-RAN as follows:

## RAN1

Enhancing features to address the identified issues due to long propagation delays, large Doppler effects, and moving cells in NTN, the following should be specified (see TR 38.821):

- Timing relationship enhancements[RAN1,RAN2]

- Enhancements on UL time and frequency synchronization [RAN1,RAN2]

- HARQ

  - Number of HARQ process [RAN1]

  - Enabling / disabling of HARQ feedback as described in the TR 38.821 [RAN1&2]

In addition, the following topics should be specified if beneficial and needed:

- Enhancement on the PRACH sequence and/or format and extension of the ra-ResponseWindow duration (in the case of UE with GNSS capability but without pre-compensation of timing and frequency offset capabilities) [RAN1/2].

- Feeder link switch [RAN2,RAN1]

- Beam management and Bandwidth Parts (BWP) operation for NTN with frequency reuse [RAN1/2]

  - Including signalling of polarization mode

## RAN2

NOTE: offset based solutions for timer adaptations are assumed.

The following user plane procedures enhancements should be specified (see TR 38.821)

- MAC

  - Random access:

    - Definition of an offset for the start of the ra-ResponseWindow for NTN.

    - Introduction of an offset for the start of the ra-ContentionResolutionTimer to resolve Random access contention

    - Solutions for resolving preamble ambiguity and extension of RAR window.

    - Adaptation for Msg-3 scheduling

      - Only for the case with pre-compensation of timing and frequency offset at UE side)

  - Enhancement on UL scheduling to reduce scheduling latency.

  - DRX:

    - If HARQ feedback is enabled, introduction of offset for drx-HARQ-RTT-TimerDL and drx-HARQ-RTT-TimerUL.

    - If HARQ is turned off per HARQ process, adaptions in HARQ procedure

  - Scheduling Request: Extension of the value range of sr-ProhibitTimer

- RLC

  - Status reporting: Extension of the value range of t-Reassembly

  - Sequence Numbers: extension of the SN space only for GEO scenarios

- PDCP

  - SDU discard: Extension of the value range of discardTimer.

  - Sequence Numbers: extension of the SN space for GEO scenarios.

The following control plane procedures enhancements should be specified (see TR 38.821)

- Idle mode:

  - Definition of additional assistance information for cell selection/reselection (e.g. using UE location information, satellite Ephemeris information)

  - Definition of NTN (satellite/HAPS) cell specific information in SIB

- Connected mode

  - Enhancement necessary to take into account location information (UE & Satellite/HAPS) and/or ephemeris in determining when to perform hand-over, in order to have a high degree of hand-over control for hand-over robustness and coverage management.

  - Enhancement to existing measurement configurations to address absolute propagation delay difference between satellites (e.g. SMTC measurement gap adaptation to the SSB/CSI-RS measurement window) [RAN2/4].

- Service continuity for mobility from TN to NTN and from NTN to TN systems (to be addressed when connected mode mobility has sufficiently progressed)

- Identify potential issues associated to the use of the existing Location Services (LCS) application protocols to locate UE in the context of NTN and specify adaptations if any [RAN2/3]

Furthermore the following can be considered with 2nd priority

- Verify the applicability of existing Rel-16 ANR techniques to solve PCI confusion in order to support co-channel operation between HAPS & terrestrial networks and develop enhancements if needed [RAN2/3]

## RAN3

The following NG-RAN architecture enhancements should be specified (see TR 38.821)

- to support feeder link switch over in Transparent payload architecture based LEO scenarios

- network identities handling

- registration update and paging handling

- cell relation handling and related features e.g. neighbours, ANR, RAN paging.

## RAN4

Study the framework for how NTN core requirements are defined.

Specify the following requirements [RAN4] (Note 1)

  - UE RRM core requirements

- Study and identify which bands may be potentially relevant to NTN including:

  - Analysis of regulations in the spectrum considered

  - Adjacent channel co-existence

- Considering the potential bands to be used as example for the WID:

- Specify needed generic RF core requirements for the network and the UE such that adjacent channel co-existence scenarios are met and performance of other RF parameters (RX performance, TX signal quality etc.) are subject to acceptable minimum requirements

- Investigate and specify UE timing & frequency pre-compensation accuracy requirements as needed [RAN4].

Note 1: It is assumed that this work item will be frequency agnostic and therefore we can consider that NTN can operate in FR1 or FR2 ranges. Defining NR bands for NTN should be included as part of dedicated Rel-17 RAN4 led work items including an analysis of regulations in spectrum considered, which bands 3GPP should specify, as well as potential co-existence between NR terrestrial and satellite

# Work Plan

## For RAN1 WG

In this section RAN1 work plan for NR support non-terrestrial network WI is provided:

17-28 August 2020, RAN1#102e, e-meeting

- Work plan presented for information

- Agree on reference scenarios for transparent payload (e.g. beam size, RTD, min elevation angle/altitude, UE types, outdoor/indoor coverage, mobility conditions, etc.) to be considered

- Confirm scope of timing relationship enhancements (leveraging TR 38.821).

- Discuss assumption and clarify the scope of UL time and frequency synchronization.

- Discuss the GNSS capabilities in the context of RAN1.

- Clarify the scope for HARQ enhancements.

26 October-13 November 2020, RAN1#103-e, e-meeting

- Aim to conclude on timing relationship enhancements.

- Agree design alternatives of UL time and frequency synchronization.

- Agree design alternatives of HARQ enhancements.

- Initiate discussion on feeder link switch issues

18-22 January 2021, RAN1#103bis-e, TBC

- Agree detailed solutions of timing relationship enhancements.

- Down-select solutions if needed of UL time and frequency synchronization.

- Down-select solutions if needed of HARQ.

- Discussion and comparison among alternatives of Random access enhancements identified in SI (e.g., PRACH sequence/format).

- Identify needs for Beam management and Bandwidth Parts (BWP) operation (including SSB arrangement and rate matching behavior).

- Identify RAN1 impacts for feeder link switch.

1-5 March 2021, RAN1#104, Athens

- Agree detailed solution for UL time and frequency synchronization.

- Agree detailed solution for HARQ.

- Conditioning on the need, agree design alternatives of Beam management and Bandwidth Parts (BWP) operation.

- Continue discussion and down-selection of Random access enhancements conditioning on the needs.

- Process potential LS from RAN2 on feeder link switch (if Hard switch should be supported) and with identification on the potential enhancements, if necessary.

19 – 23 April 2021, RAN1#104bis, China

- Down-select solutions if needed of Beam management and Bandwidth Parts (BWP) operation, Random access enhancements (PRACH and RA window), feeder link switch, if any.

- Discuss remaining details on UL time and frequency synchronization and HARQ

24 -28 May 2021, RAN1#105, Toulouse

- Agree detailed solution for Beam management and Bandwidth Parts (BWP) operation, Random access enhancements (PRACH and RA window), if any.

- Agree detailed solution for feeder link switch, if any.

- Agree remaining details on timing relationship enhancements, UL time and frequency synchronization and HARQ.

## For RAN2 WG

In this section, the RAN2 work plan for NR support non-terrestrial network WI is provided:

17-28 August 2020, RAN2#111-e, e-meeting

- Work plan presented for information

- Agree on reference scenarios (e.g. Earth fixed or moving beams, etc.)  to be considered

- Initial discussion and agree on design alternatives on MAC layer (Random Access, DRX, Scheduling Request, UL scheduling as well as timing/offset aspects)

- Initial discussion and agree on design alternatives on RLC and PDCP layer

- Initial discussion on design alternatives on idle mode (including tracking area management) and SIBs impact (e.g. new IEs, rate of transmission)

2-13 November 2020, RAN2#112-e, e-meeting

- Down-select solutions if needed for MAC layer (Random Access, DRX, Scheduling Request, UL scheduling as well as timing/offset aspects)

- Down-select solutions if needed for RLC and PDCP layer

- Agree on design alternatives on idle mode

- Initial discussion on Connected mode

- Initiate discussion on feeder link switch over options

18-22 January 2021, RAN2#112bis-e, TBC

- Agree detailed solution for MAC layer (Random Access, DRX, Scheduling Request, UL scheduling as well as timing/offset aspects)

- Agree detailed solution for RLC and PDCP layer

- Down-select solutions if needed for idle mode

- Continue discussion on Connected mode

- Agree on design alternatives for feeder link switch over options, send LS to RAN1, if necessary

1-5 March 2021, RAN2#113, Athens

- Agree remaining details on MAC layer

- Agree remaining details on RLC/PDCP

- Agree detailed solution for idle mode

- Continue discussion on Connected mode

- Identify potential issues with Location Services (LCS) application protocols for NR NTN

- Initial discussion on HAPS enhancement

19 – 23 April 2021, RAN2#113bis, Taiwan

- Agree remaining details on idle mode

- Agree design alternatives on Connected mode

- Identify potential adaptations with Location Services (LCS) application protocols for NR NTN Agree design alternatives on HAPS enhancement

24 -28 May 2021, RAN2#114, Toulouse

- Down-select solutions if needed of Connected mode

- Down-select, if needed, potential adaptations with Location Services (LCS) application protocols for NR NTN Down-select solutions of HAPS enhancement

- Initial discussion and agree design alternatives on NTN/TN service continuity

23 -27 August 2021, RAN2#115, Toulouse

- Agree detailed solution for Connected mode

- Agree potential adaptations with Location Services (LCS) application protocols for NR NTN

- Agree detailed solution for HAPS enhancement

- Down-select, if needed, solutions of NTN/TN service continuity

11 -19 October 2021, RAN2#115bis, Toulouse

- Agree remaining details for Connected mode

- Agree final details of potential adaptations with Location Services (LCS) application protocols for NR NTN

- Agree remaining details for HAPS enhancement

- Agree detailed solution for NTN/TN service continuity

## For RAN3 WG

In this section, the RAN3 work plan for NR support non-terrestrial network WI is provided:

17-28 August 2020, RAN3#109-e, e-meeting

- Work plan presented for information

- Agree on reference scenarios to be considered

- Initial discussion on feeder link switch

- Initial discussion on network identities handling

- Initial discussion on registration update and paging handling

- Initial discussion on cell relation handling and related features (e.g. neighbours, ANR, RAN paging)

2-13 November 2020, RAN3#110-e, e-meeting

- Agree on design alternatives on feeder link switch

- Agree on design alternatives on network identities handling

- Agree on design alternatives on registration update and paging handling

- Agree on design alternatives on cell relation handling and related features (e.g. neighbours, ANR, RAN paging)

18-22 January 2021, RAN3#110bis-e, TBC

- Down-select, if needed, solutions for feeder link switch

- Down-select, if needed, solutions for network identities handling

- Down-select, if needed, solutions for registration update and paging handling

- Down-select, if needed, solutions for cell relation handling and related features (e.g. neighbours, ANR, RAN paging)

1-5 March 2021, RAN3#111, Athens

- Discuss detailed solution for feeder link switch

- Discuss detailed solution for network identities handling

- Discuss detailed solution for registration update and paging handling

- Discuss detailed solution for cell relation handling and related features (e.g. neighbours, ANR, RAN paging)

19 – 23 April 2021, RAN3#111bis, Taiwan

- Agree detailed solution for feeder link switch

- Agree detailed solution for network identities handling

- Agree detailed solution for registration update and paging handling

- Agree detailed solution for cell relation handling and related features (e.g. neighbours, ANR, RAN paging)

23 -27 August 2021, RAN3#112, Toulouse

- Agree remaining details for feeder link switch

- Agree remaining details for network identities handling

- Agree remaining details for registration update and paging handling

- Agree remaining details for cell relation handling and related features (e.g. neighbours, ANR, RAN paging)

## For RAN4 WG

In this section RAN4 work plan for NR support non-terrestrial network WI is provided:

26 october-13 November 2020, RAN4#97-e, e-meeting

- Work plan presented for information.

- Presentation of reference scenarios to be considered.

- Initial discussion on the framework definition of the NTN core requirements (e.g. list of relevant KPIs).

- Initial discussion on the candidate bands relevant for NTN and their regulatory constraints, including the channel coexistence.

18-22 January 2021, RAN4#97bis-e, TBC

- To be completed

1-5 March 2021, RAN4#98, Athens

- To be completed

19 – 23 April 2021, RAN4#98bis, China

- To be completed

24-28 May 2021, RAN4#99, USA

- To be completed

23 -27 August 2021, RAN4#100, Toulouse

- To be completed

11-15 Oct 2021, RAN4#100bis, China

- To be completed

15-19 Nov 2021, RAN4#101, USA (TBC TU)

- To be completed

# References

TR 38.821 “Study on solutions for NR to support non-terrestrial networks”

RP-191256, “Solutions for NR to support non-terrestrial networks (NTN)”, Thales, RAN#88-e, june 2020.

END