## Slide 1: RAN2 planning 2022 H1
Source RAN2 Chair
3GPP TSG RAN WG2#116bis-e
January 2022
R2-2201693
For Discussion

## Slide 2: ASN.1 Ad-Hoc
The plan for a RAN2 ad-hoc in April 2022 is confirmed / endorsed, with the following:
− Ad-hoc Scope: NR ASN.1 review (including NR+LTE parts but not EUTRA-specific parts), TBD whether NR UE caps would be included (i.e. beyond ASN.1 review of NR UE caps signalling).
− Ad-hoc to treat input tdocs, and to treat, approve and send LSes (e.g. for asking questions) within the scope of the Ad-Hoc. Endorsements (of TPs, Draft CRs, CRs) are subject to final approval/agreement at RAN2 118.
− Ad-hoc GTW sessions: April 20, 21, 22 (e.g. 3h + 3h + 1h), the last session April 22 will only be used if needed.
− Ad-hoc tdoc submission deadline: April 14

## Slide 3: R2 Plan 2022 H1
I
N
A
C
T
I
V
E
I
N
A
C
T
I
V
E
January
2022
February
2022
17-21
24-28
31-04
07-11
14-18
21-25
March
2022
28-04
07-11
14-18
T
S
G
#
9
5
R2 117-E
(5+4)
10-14
03-07
I
N
A
C
T
I
V
E
21-25
R2 116bis-E
(5+2)
April
2022
May
2022
11-15
18-22
25-29
02-06
09-13
16-20
June
2022
23-27
30-3
6-10
20-24
28-01
13-17
04-08
T
S
G
#
9
6
R2 118-E
I
N
A
C
T
I
V
E
03/17-03/23
NO LONG EMAIL DISCUSSIONS
Ad hoc

## Slide 4: Coordinated Input to R2 117-E Proposal To Close Open Issues
I
N
A
C
T
I
V
E
I
N
A
C
T
I
V
E
January
2022
February
2022
17-21
24-28
31-04
07-11
14-18
21-25
March
2022
28-04
07-11
14-18
T
S
G
#
9
5
R2 117-E
(5+4)
10-14
03-07
I
N
A
C
T
I
V
E
21-25
R2 116bis-E
(5+2)
April
2022
May
2022
11-15
18-22
25-29
02-06
09-13
16-20
June
2022
23-27
30-3
6-10
20-24
28-01
13-17
04-08
T
S
G
#
9
6
R2 118-E
I
N
A
C
T
I
V
E
03/17-03/23
Jan 28
Open Issues ready
Short Post Disc Close
Feb 9
Rap provide
Input Forms
To address
Open Issues
Feb 14
Deadline
A: Company
Input in
Input forms
B: Tdoc
Submission
R2 117-E
Ad hoc
Towards R2 117-E
For groups of pre-identified Open issues
Assigned rapporteurs provide input forms (one per group of Open issues). FEB 9
Companies provide their input in the input forms FEB 9-14
This is similar to any offline discussion.
NO Tdocs shall be submitted with contents that overlaps with any Open issue input forms
The Rapporteur may organize the input and propose ways forward.
NOTE that Open issues must be identified, and rapporteurs assigned at 116bis-E at latest Jan 28.
There may be cases when rapporteur provides initial proposals, e.g. for detailed issues in a CR.