3GPP TSG-RAN WG2 Meeting #121	R2-2300478

Athens, Greece, 27th of Feb – 3rd of Mar 2023

Agenda item:	8.8.1

Source:	Nokia, Nokia Shanghai Bell

Title:	Uncrewed Aerial Vehicles in Rel-18 - Updated Workplan

WID/SID:	NR_UAV - Release 18

Document for:	Discussion and Decision

# 1	Introduction

In December 2022 RAN#98 has revised Rel-18 work item on NR UAVs, see [1]. As a rapporteur company, herein we provide a workplan proposal considering all impacted RAN working groups.

# 2	Work Item objectives

Work Item aims at specifying UAV-related enhancements to support drones in NR networks. In the following subsections the WI objectives are split over engaged working groups.

## 2.1	RAN1

Study UE capability signalling to indicate UAV beamforming capabilities and, if necessary, RRC signalling:

- FR1 with directional antenna at UE side

## 2.2	RAN2

Specify the following enhancements on measurement reports:

- UE-triggered measurement report based on configured height thresholds

- Reporting of height, location and speed in measurement report

- Flight path reporting

- Measurement reporting based on a configured number of cells (i.e. larger than one) fulfilling the triggering criteria simultaneously

Study and specify, if needed, enhancements to NR PC5 and LTE PC5 to support UAV identification broadcast [RAN2]. Check at RAN#99 for further elaboration of this objective, based on RAN2 discussions and SA2 development. Note: This objective is not intended to introduce new band(s) with support for the PC5 interface. UAV use of LTE PC5 or NR PC5 is not addressing any operator licensed band.

Study UE capability signaling to indicate UAV beamforming capabilities and, if necessary, RRC signaling:

- FR1 with directional antenna at UE side

Specify the signaling to support subscription-based aerial-UE identification

## 2.3	RAN3

Specify the signalling to support subscription-based aerial-UE identification.

# 3	Timeline

In this section a timeline is proposed with rough suggestion which objectives are handled where and when. This is in line with the approved time budget [1].

## Q3 2022

RAN2#119 (0,5 TU):

- Workplan presentation, RAN2 WI scope clarifications

- Initial discussion on the solutions designed in Rel-15 of LTE (including measurement reporting based on height thresholds, flight path reporting, interference detection and reporting based on a configured number of cells fulfilling the event, reporting of height, location and speed).

- Initial discussion on the subscription based UE identification – whether the LTE Rel-15 solution can be adopted.

## Q4 2022

RAN1#110bis (0,5 TU):

- Workplan presentation, RAN1 WI scope clarifications

- Initial discussion on UE capability signalling to indicate UAV beamforming capabilities (FR1 with directional antenna at UE side)

RAN2#119bis (0,5 TU):

- Further discussion on the solutions designed in Rel-15 of LTE (including measurement reporting based on height thresholds, flight path reporting, interference detection and reporting based on a configured number of cells fulfilling the event, reporting of height, location and speed) and for further study issues identified at RAN2#119. Subsequent gaps/problems identified.

- Potential discussion on the subscription based UE identification.

RAN3#117bis (0,5 TU):

- Workplan presentation, RAN3 WI scope clarifications

- Initial discussion on subscription-based aerial-UE identification, taking work done in LTE as a starting point.

RAN2#120 (0,5 TU):

- Further discussion on the solutions designed in Rel-15 of LTE, to be adopted in NR. Further agreements on the necessary NR adaptations – height-dependent adjustments, flight path plan reporting, multi-cell triggering.

RAN3#118 (0,5 TU):

- First decisions on the subscription based UE identification (considerations on NGAP and/or Xn impacts) – In case of conclusions - LS to RAN2 with feedback.

## Q1 2023

RAN1#112 (0,5 TU):

- Further discussion and first decisions on UE capability signalling to indicate UAV beamforming capabilities (FR1 with directional antenna at UE side. Potential LS to RAN2 with intermediate feedback.)

RAN2#121 (0,5 TU):

- LTE Rel-15 measurement-based solutions – further NR adaptations pursued on measurements for interference mitigation and for mobility.

- Flight path reporting – NR enhancements

- Initial discussion on Broadcasting UAV’s ID (BRID), based on the decisions in SA2 and RAN.

RAN3#119 (0,5 TU):

- Work towards Stage-3 details on Subscription-based UE identification

## Q2 2023

RAN1#112bis (0,5 TU):

- Final decisions and refinements on UE capability signalling to indicate UAV beamforming capabilities (FR1 with directional antenna at UE side).

RAN2#121bis (1 TU):

- RAN2 decisions on subscription-based UE identification. Response LS to RAN3

- RAN2 decisions on UE capability signalling to indicate UAV beamforming capabilities. Response LS to RAN1

- Stage-2 details of the measurement report related UAV solutions agreed. Running 38.300 CR initiated.

- Stage-2 details of UAV identification broadcast.

RAN3#119bis (0,5 TU):

- Stage-3 details on Subscription-based UE identification agreed. Running CR(s) initiated.

- Details on other potential RAN3 impacts of the WI discussed.

RAN2#122 (1 TU):

- Stage-2 decisions for all RAN2 related WI objectives

- Updates to running Stage-2 CR.

- Potentially/preferably Stage-3 running CRs initiated.

RAN3#120 (0,5 TU):

- Further work on Stage-3 details on Subscription-based UE identification and other relevant RAN3 aspects, considering RAN2 response LS.

## Q3 2023

RAN2#123 (1 TU):

- Final decisions on measurement report related enhancements for UAVs

- Final decisions on UE capability signalling to indicate UAV beamforming capabilities

- Final decisions on subscription-based UE identification

- Final decisions on UAV identification broadcast.

- Stage-2 specification ready

RAN3#121 (0,5 TU):

- All Stage-2 and Stage-3 RAN3 aspects of UAV WI defined, drafts CRs available and shared with RAN2 (LS)

## Q4 2023

RAN2#123bis (1 TU):

- Stage-3 CRs (38.331, 38.306) on all RAN2-related aspects

RAN3#121bis (0,5 TU):

- Minor updates (if needed) to RAN3-impacted specifications.

RAN2#124 (1 TU):

- Finalization of Stage-3 CRs (38.331, 38.306) on all RAN2 matters

RAN3#122 (0,5 TU):

- Minor updates (if needed) to RAN3-impacted specifications.

Overall, we would like to ask RAN2 to endorse the abovementioned workplan, which may be further revised when WI objectives pending the progress in other WGs are resolved.

Proposal: RAN2 is kindly asked to endorse the Rel-18 UAV WI work plan presented in R2-2300478.

# 4	Conclusion

The following proposal has been made in this paper:

Proposal: RAN2 is kindly asked to endorse the Rel-18 UAV WI work plan presented in R2-2300478.

# References

- RP-223545 Revised WID: NR Support for UAV (Uncrewed Aerial Vehicles) 3GPP TSG RAN Meeting #98e Electronic Meeting, Dec. 12 - 16, 2022