3GPP TSG RAN WG2 #121	R2-2301344

Athens, GR, 27 Feb 2023– 03 Mar 2023

Title:	R18 WI NR-NTN-enh work plan at RAN1, 2 and 3

Source:	Thales

Type:	Work Plan

For:	Agreement

Agenda Item:	8.7.1

Release:	Rel-18

WI:	NR NTN enhancements

# Introduction

In this contribution, an updated work plan for the Rel-18 NR-NTN-enh work item [1] is proposed for RAN 1, 2 & 3.

# WID Objective

The work item aims at specifying enhancements for NG-RAN based NTN (Non-Terrestrial Networks) according to the following assumptions with implicit compatibility to support HAPS (High Altitude Platform Station) and ATG (Air To Ground) scenarios:

- GSO (Geo Synchronous Orbit) and NGSO (Non Geo Synchronous Orbit). NGSO includes Low Earth Orbit (LEO) and Medium Earth Orbit (MEO).

- Earth fixed tracking area. Earth fixed & Earth moving cells for NGSO

- FDD mode

- UEs with GNSS (Global Navigation Satellite Systems) capabilities

- Both “VSAT” (Very Small Aperture Terminal) devices with directive antenna (including fixed and moving platform mounted devices and commercial handset terminals (e.g. Power class 3) are supported in FR1

- Only “VSAT” devices with directive antenna (including fixed and moving platform mounted devices) are supported in above 10 GHz bands.

Note 1: In Rel-17 WID, “VSAT” device with external antenna on moving platform is equivalent to a device that operate on platforms in motion, and this is referred to as ESIM (Earth Station In Motion).

Note 2: The Rel-17 NTN architecture is assumed.

The detailed objectives are to specify enhancing features to Rel-15, 16 & 17’s NR radio interface & NG-RAN as follows:

## Coverage enhancement

The Rel-18 NTN objectives are focused on the applicability of the solutions developed by general NR coverage enhancement to NTN, and identifying potential issues and enhancements if necessary, considering the NTN characteristics including large propagation delay and satellite movement. Only NTN-specific characteristics are to be included in this coverage enhancement work, otherwise it should be part of another WI (e.g., UL enhancement of coverage).

The following sentence will be revisited in RAN#99 as part of the DL enhancements discussion:

“The evaluation should also take into account any related regulatory requirements, e.g., ITU limitation of power flux density.” No work on this topic will take place in RAN WGs before the discussion on DL enhancements in RAN#99.

The following reference scenario is considered for the definition of uplink coverage enhancements for NTN: parameter set-1 for LEO-1200 satellite operating at Line of Sight (LOS) and commercial smartphones with -5.5 dBi antenna gain and 3 dB polarisation loss (per antenna port).

Note: It is understood that the enhancements defined for LEO can also apply to GEO and MEO scenarios as appropriate. No additional work is expected for MEO/GEO.

The targeted services are VoIP using AMR 4.75 kbps and data transmission services with Low data rate of 3 kbps.

The detailed objectives are for NTN:

- To specify PUCCH enhancements for Msg4 HARQ-ACK (e.g. repetition) [RAN1, RAN4]

- To specify if necessary, enhancements to the Rel-17 procedures for DMRS bundling for PUSCH taking into account NTN-specifics (e.g. time-frequency pre-compensation) [RAN1]

## NR-NTN deployment in above 10 GHz bands

The following assumptions are taken a baseline for this work:

- GSO and NGSO (e.g. LEO, MEO, HEO) based satellite access to be considered

  - ESIM scenarios for NGSO in Ka band are not considered in this WI.

- Targeted UE types: fixed and mobile VSAT. VSAT UE characteristics from TR38.821 to be considered in priority but additional NTN UE classes may be considered if justified

  - Regarding mobile VSAT, three types of terminal and scenario exist; airborne, maritime and land based ESIM. Which type(s) to be specified depends on the outcome of the regulation analysis and co-existence study.

- FDD mode is assumed for satellite operation above 10 GHz, while TDD mode is assumed for terrestrial operation in FR2

- The ITU-R harmonized Ka band will serve as reference

- Co-existence between overlapping NTN and TN band portions is out of scope of this work item. This aspect will be captured in the specification.

The following covers the objectives for NR-NTN deployment in above 10 GHz bands. This work is expected to start after June 2022.

- Study and identify NTN example band: Analysis of regulations and adjacent channel co-existence scenarios. The example band shall be identified early in the WI. Additional bands can be introduced in a release-independent manner. [RAN4]

  - Consider the satellite harmonized Ka band as a reference, according to ITU allocation; taking into account deployment type (e.g. VSAT, ESIM), scenarios, and ITU-R/regional regulations, define an example band suitable for development of generic 3GPP minimum performance requirements (the example RAN4 band may be a portion of or the entire harmonized Ka band). [RAN4]

  - Study implications of FDD operation in FR2 and derive requirements for the identified example band appropriately. Satellite bands introduced in 3GPP for NTN for FDD shall not impact the existing 3GPP TDD specifications for terrestrial bands adjacent to the NTN band (see note 3 of the approved way forward RP-211596 in RAN#92-e). [RAN4]

  - Relevant coexistence scenarios and analysis to be considered in RAN4, if and where applicable, to ensure that satellite bands introduced in 3GPP for NTN shall not impact the existing specifications and shall not cause degradation (in the sense of RAN4 co-existence studies) to networks in 3GPP specified terrestrial bands adjacent to the NTN band. In that, it is assumed that the NTN-TN adjacent band coexistence will be performed at the harmonized Ka band edges. The outcome is expected to be applicable to all NTN-TN adjacent band scenarios (if any) in the whole Ka band range where applicable and regulations allow. [RAN4]

  - For all the above, RAN4 process as agreed for NTN in FR1 should be used for coexistence analysis in above 10 GHz bands [RAN4].

  - Definition of NTN band(s) above 10 GHz does not change the current FR1/FR2 definition, nor automatically apply to future terrestrial bands defined in this frequency region; (see proposal 2 of the approved way forward RP-211596 in RAN#92-e) [RAN4]

- Specify Rx/Tx requirements for satellite access node and different VSAT UE class (not only 60 cm aperture) as appropriate for the identified example band [RAN4]

- Identify values for physical layer parameters chosen from the existing FR1 and FR2 sets. The following set of parameters to specify, but not necessarily limited to, are listed.as follows [RAN4]:

  - time relationship related enhancement (e.g. K_offset)

  - subcarrier spacing for different UL/DL signals/channels

  - PRACH configuration index for FDD above 10 GHz.

## Network verified UE location

Based on RAN1 conclusions of the study phase, RAN to prioritize the specification of necessary enhancements to multi-RTT to support the network verified UE location in NTN assuming a single satellite in view [RAN1, 2, 3, 4]. DL-TDoA methods for verification may be considered as lower priority and if time permits and condition in Note is satisfied.

Note 1: Enhancements assume reuse of the RAT dependent positioning framework

Note 2: The specification of DL-TDOA enhancements will be subject to the study of the impact of realistic UE clock drift onto DL-TDOA performance

Note 3: The target accuracy for position verification purposes is as documented in clause « recommendations » of the 3GPP TR 38.882 (i.e. 10 km granularity)

Note 4 : Multiple satellite in view by the UE may be considered if time allows

Note 5 : The enhancements may be subject to relevant SA WGs (e.g. SA3/SA3-LI) feedbacks on the reliability of UE reports involved

Note 6 : The enhancements should take into account the mirror-image ambiguity

Note 7 : Network verified UE location is an optional UE feature

## NTN-TN and NTN-NTN mobility and service continuity enhancements

This work considers existing methods from NR TN as well as outcome of Rel-17 NR NTN WI outcome as baseline for NTN-TN mobility.

- Specify NTN-TN and NTN-NTN measurement/mobility and service continuity enhancements [RAN2,RAN3,RAN4]

  - For NTN-NTN mobility, specify cell reselection enhancements for earth moving cell, the timing based and location-based cell reselection for quasi-earth fixed cell in Rel-17 can be considered as the starting point. [RAN2, RAN3, RAN4]

  - Specify NTN-NTN handover enhancement for RRC_CONNECTED UEs in the quasi-earth-fixed cell and earth-moving cell to reduce the signalling overhead. [RAN2, RAN3]

  - Specify cell reselection enhancements for RRC_IDLE/INACTIVE UEs to reduce UE power consumption (NTN-TN mobility is prioritized). [RAN2, RAN3, RAN4]

  - Study and, if needed, specify enhancement to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs. [RAN3]

# Work Plan

The work plan for each WID objective is given within the following sub-sections.

## Coverage enhancement:

The tentative work plan for coverage enhancement work item is proposed as follows:

| Meetings | WG and TU | Objectives |
| --- | --- | --- |
| February 2023, RAN1#112 February 2023, RAN2#121 | RAN1 0.25 TU | Further discuss the potential solutions and the performance for uplink coverage enhancements in NTN environment: - Specify PUCCH enhancements for Msg4 HARQ-ACK (e.g. repetition) - specify if necessary, enhancements to the Rel-17 procedures for DMRS bundling for PUSCH taking into account NTN-specifics (e.g. time-frequency pre-compensation) |
|  | RAN2 0.2 TU | Considering the last RAN 2 meeting (November 2022#120) and the last RAN plenary meeting (December 2022, RAN#98), potential RAN 2 impacts are still subject to discussion on user plane (HARQ, timers), control plane (SIB, RRC signaling). However, most of the remaining work is in the RAN1 working group. |
| April 2023, RAN1#112-bis April 2023, RAN2#121-bis | RAN1 0.25 TU | Further discuss the potential solutions and the performance for uplink coverage enhancements in NTN environment: - Specify PUCCH enhancements for Msg4 HARQ-ACK (e.g. repetition) - specify if necessary, enhancements to the Rel-17 procedures for DMRS bundling for PUSCH taking into account NTN-specifics (e.g. time-frequency pre-compensation) Discuss draft CRs |
|  | RAN2 0.2 TU | Considering the last RAN 2 meeting (November 2022#120) and the last RAN plenary meeting (December 2022, RAN#98), potential RAN 2 impacts are still subject to discussion on user plane (HARQ, timers), control plane (SIB, RRC signaling). However, most of the remaining work is in the RAN1 working group. |
| May 2023, RAN1#113 May 2023, RAN2#122 | RAN1 0.25 TU | Discuss the remaining aspects of the solutions for coverage enhancements in NTN environment. Discuss related RRC parameters, if needed, and send LS to RAN2 Discuss draft CRs |
|  | RAN2 0.2 TU | Discuss the remaining aspects of the solutions for coverage enhancements in NTN environment. Discuss draft CRs |
| August 2023, RAN1#114 August 2023, RAN2#123 | RAN1 0.25 TU | Conclude on the solutions for coverage enhancements in NTN environment. Further discuss related RRC parameters, if needed, and send LS to RAN2 Finalize RAN1 CRs. |
|  | RAN2 0.2 TU | Conclude on the solutions for coverage enhancements in NTN environment. Discuss draft CRs. |
| October 2023, RAN2#123-bis | RAN2 0.2 TU | Discuss draft CRs. Conclude on the remaining aspects, if any |
| November 2023, RAN2#124 | RAN2 0.2 TU | Finalize RAN2 CRs. Conclude on the remaining aspects, if any |

## Network verified UE location:

The tentative work plan for the normative phase of Network verified UE location is proposed as follows:

| Meetings | WG and TU | Objectives |
| --- | --- | --- |
| February 2023, RAN1#112 February 2023, RAN2#121 February 2023, RAN3#119 | RAN1 0.25 TU | Agree on detailed design for solution for network to verify UE reported location information: - Specify necessary enhancements to multi-RTT to support the network verified UE location in NTN assuming a single satellite in view - Enhancements assume reuse of the RAT dependent positioning framework - DL-TDoA methods for verification may be considered as lower priority and if time permits. - The specification of DL-TDOA enhancements will be subject to the study of the impact of realistic UE clock drift onto DL-TDOA performance - Multiple satellite in view by the UE may be considered if time allows - The enhancements should take into account the mirror-image ambiguity |
|  | RAN2 0.4 TU | RAN1 WG has completed the study phase and reported its conclusions during the plenary meeting (December 2022, RAN#98). The conclusions can be found in Section 2.2. Therefore, the normative phase begins : - Specify necessary enhancements to multi-RTT, in particular the impact on signaling, to support the network verified UE location in NTN assuming a single satellite in view. - Enhancements assume reuse of the RAT dependent positioning framework. - Multiple satellites in view by the UE may be considered if time allows. If needed other topics related to enhancement solutions for network verified UE location could be discussed. RAN2 waits for feedback of the LS on Latency impact for NTN verified UE location. |
|  | RAN3 0.25 TU | RAN1 WG has completed the study phase and reported its conclusions during the plenary meeting (December 2022, RAN#98). The conclusions can be found in Section 2.2. Therefore, the normative phase begins. If needed discuss enhancement solutions for network verified UE location, in particular : - Identify potential impact in RAN3 (NRPPa and LPP). - Specify necessary enhancements to multi-RTT to support the network verified UE location in NTN assuming a single satellite in view. - Multiple satellites in view by the UE may be considered if time allows. |
| April 2023, RAN1#112-bis April 2023, RAN2#121-bis April 2023, RAN3#119-bis | RAN1 0.25 TU | Further discuss the detailed design for solution for network to verify UE reported location information: - Specify necessary enhancements to multi-RTT to support the network verified UE location in NTN assuming a single satellite in view - Enhancements assume reuse of the RAT dependent positioning framework - DL-TDoA methods for verification may be considered as lower priority and if time permits. - The specification of DL-TDOA enhancements will be subject to the study of the impact of realistic UE clock drift onto DL-TDOA performance - Multiple satellite in view by the UE may be considered if time allows - The enhancements should take into account the mirror-image ambiguity |
|  | RAN2 0.4 TU | RAN1 WG has completed the study phase and reported its conclusions during the plenary meeting (December 2022, RAN#98). The conclusions can be found in Section 2.2. Therefore, the normative phase begins : - Specify necessary enhancements to multi-RTT, in particular the impact on signaling, to support the network verified UE location in NTN assuming a single satellite in view. - Enhancements assume reuse of the RAT dependent positioning framework. - Multiple satellites in view by the UE may be considered if time allows. If needed other topics related to enhancement solutions for network verified UE location could be discussed. |
|  | RAN3 0.25 TU | RAN1 WG has completed the study phase and reported its conclusions during the plenary meeting (December 2022, RAN#98). The conclusions can be found in Section 2.2. Therefore, the normative phase begins. If needed discuss enhancement solutions for network verified UE location, in particular : - Identify potential impact in RAN3 (NRPPa and LPP). - Specify necessary enhancements to multi-RTT to support the network verified UE location in NTN assuming a single satellite in view. - Multiple satellites in view by the UE may be considered if time allows. |
| May 2023, RAN1#113 May 2023, RAN2#122 May 2023, RAN3#120 | RAN1 0.25 TU | Conclude on detailed design for solution for network to verify UE reported location information Conclude on detailed design for NR positioning enhancements for NTN Discuss related RRC parameters, if needed, and send LS to RAN2 Discuss draft CRs |
|  | RAN2 0.4 TU | If needed discuss enhancement solutions for network verified UE location |
|  | RAN3 0.25 TU | If needed discuss enhancement solutions for network verified UE location |
| August 2023, RAN1#114 August 2023, RAN2#123 August 2023, RAN3#121 | RAN1 0.25 TU | Conclude on the remaining aspects, if any Further discuss related RRC parameters, if needed, and send LS to RAN2 Finalize RAN1 CRs. |
|  | RAN2 0.4 TU | If needed discuss enhancement solutions for network verified UE location |
|  | RAN3 0.25 TU | Address RAN3 impacts depending on RAN1/RAN2 progress |
| October 2023, RAN2#123-bis October 2023, RAN3#121-bis | RAN2 0.4 TU | If needed discuss RAN2 draft CRs |
|  | RAN3 0.25 TU | If needed discuss RAN3 draft CRs |
| November 2023, RAN2#124 November 2023, RAN3#122 | RAN2 0.4 TU | If needed finalize RAN2 draft CRs Conclude on the remaining aspects, if any |
|  | RAN3 0.25 TU | If needed finalize RAN3 draft CRs Conclude on the remaining aspects, if any |

## NTN-TN and NTN-NTN mobility and service continuity enhancements

| Meetings | WG and TU | Objectives |
| --- | --- | --- |
| February 2023, RAN2#121 February 2023, RAN3#119 | RAN2 0.4 TU | Further discuss enhancements for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode |
|  | RAN3 0.25 TU | Further discuss enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs Some clarifications are expected regarding: - The type of cell id (mapped cell id/ Uu cell Id) to use in handover signaling - Xn interface in transparent payload scenario |
| April 2023, RAN2#121-bis April 2023, RAN3#119-bis | RAN2 0.4 TU | Further discuss enhancements for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode |
|  | RAN3 0.25 TU | Further discuss enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs |
| May 2023, RAN2#122 May 2023, RAN3#120 | RAN2 0.4 TU | Agree on detailed design and solution for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode |
|  | RAN3 0.25 TU | Agree on detailed design of solution for enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs |
| August 2023, RAN2#123 August 2023, RAN3#121 | RAN2 0.4 TU | Agree on detailed design and solution for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode |
|  | RAN3 0.25 TU | Agree on detailed design of solution for enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs |
| October 2023, RAN2#123-bis October 2023, RAN3#121-bis | RAN2 0.4 TU | Conclude on the detailed solution Discuss RAN2 draft CRs |
|  | RAN3 0.25 TU | Conclude on the detailed solution Conclude on the remaining aspects, if any Discuss RAN3 draft CRs |
| November 2023, RAN2#124 November 2023, RAN3#122 | RAN2 0.4 TU | Agree on the remaining details Conclude on the remaining aspects, if any Finalize RAN2 CRs. |
|  | RAN3 0.25 TU | Agree on the remaining details Conclude on the remaining aspects, if any Finalize RAN3 CRs. |

# References

RP-223534  (revision of RP-222654) NR NTN (Non-Terrestrial Networks) enhancements

END