3GPP TSG-RAN WG2 Meeting #122	R2-2305186

Incheon, South Korea, 22– 26 May 2023

Agenda item:	7.5.1

Source:	Nokia, Qualcomm (Rapporteurs); Ericsson (RAN1 FL)

Title:	Work Plan for Rel-18 on XR Enhancements for NR

WID/SID:	NR_XR_enh - Release 18

Document for:	Discussion and Decision

# 1	Introduction

At RAN#99, the XR study was closed, TR 38.835 approved and WID updated to reflect the outcome of the study. The updates objectives are [RP-230786]:

Specify the enhancements related to power saving: - DRX support of XR frame rates corresponding to non-integer periodicities (through at least semi-static mechanisms e.g. RRC signalling) (RAN2). Specify the enhancements related to capacity: - Multiple Configured Grant (CG) PUSCH transmission occasions in a period of a single CG PUSCH configuration (RAN1, RAN2); - Dynamic indication of unused CG PUSCH occasion(s) based on Uplink Control Information (UCI) by the UE (RAN1, RAN2); - Buffer Status Report (BSR) enhancements including at least new Buffer Status Table(s) (RAN2); - Delay reporting of buffered data in uplink (RAN2); - Discard operation of PDU Sets for DL and UL (RAN2, RAN3); Specify the enhancements for XR Awareness: - Signalling by CN of semi-static information per QoS flow (e.g. PDU set QoS parameters), dynamic information per PDU set (PDU Set information and Identification) and End of Data Burst indication (RAN3, RAN2); - Impact of identifying by UE of PDU Sets, Data bursts and PSI, as needed (RAN2); - Provisioning by UE of XR traffic assistance information e.g. periodicity, UL traffic arrival information (RAN2, RAN3); - Support signalling the congestion information from RAN to the CN in alignment with SA2 (RAN3);

Note that in addition to these objectives, it was agreed that two additional power saving enhancements can be discussed in working groups:

-	PDCCH monitoring resume if UE transmits NACK after PDCCH skipping starts (RAN1, see e.g. RP-230649); and

-	CG without retransmissions for uplink XR traffic (RAN2, see e.g. RP-230456).

# 2	Plan

A workplan corresponding to the objectives and allocated TUs is suggested the table below.

Table 3: Workplan for the XR WI

| Date | RAN1 | RAN2 | RAN3 | RAN |
| --- | --- | --- | --- | --- |
| 2023-02 | RAN1#112 Start the discussion in RAN1 for designing the configured grant enhancement features to improve capacity. | RAN2#121 Designate responsible companies for running Stage 2 & 3 CRs Agree skeleton of Stage 2 CR Start discussing Power Saving and Capacity Enhancements. |  |  |
| 2023-03 |  |  |  | RAN#99 Status Report (target of 7% for 1 TU spent over 14) |
| 2023-04 | RAN1#112bis Continue the discussion in RAN1 for designing the configured grant enhancement features to improve capacity. Start the discussion in RAN1 to identify and describe the impact of adding PDCCH monitoring resumption after UL NACK functionality and aim to finalize the discussion. | RAN2#121bis Populate Stage 2 CR with relevant background information from TR Continue discussing Power Saving and Capacity Enhancements and start discussing XR Awareness Start discussing CG without retransmissions for uplink XR traffic Start updating running Stage 2 CR |  |  |
| 2023-05 | RAN1#113 Continue the discussion in RAN1 for designing the configured grant enhancement features to improve capacity. Finalize, if not already, the discussion in RAN1 to identify and describe the impact of adding PDCCH monitoring resumption after UL NACK functionality. | RAN2#122 Continue discussing all 3 objectives Start agreeing Stage 3 level descriptions of solutions for all 3 objectives Finalise, if not already, the discussion on CG without retransmissions for uplink XR traffic Continue updating running Stage 2 CR |  |  |
| 2023-06 |  |  |  | RAN#100 Status Report (target of 45% for 7 TUs spent over 15.5) |
| 2023-08 | RAN1#114 Finalize the discussion in RAN1 for designing the configured grant enhancement features to improve capacity. Provide RAN1 input to RAN2 on RRC configuration parameters and UE capabilities. | RAN2#123 Continue the work on the details of the agreed solutions for all 3 objectives Reflect new agreements in running Stage 2 & 3 CRs. | RAN3#121 Start discussion on RAN3 related objectives, e.g. signalling enhancements to support XR awareness in the RAN node, congestion indication to CN, etc. Designate responsible companies for running Stage-2 & 3 CRs. Agree skeleton of Stage-2 CR(s). |  |
| 2023-09 |  |  |  | RAN#101 Status Report (target of 68% for 10.5 TUs spent over 15.5) |
| 2023-10 |  | RAN2#123bis Continue the work on the details of the agreed solutions for all 3 objectives Reflect new agreements in running Stage 2 & 3 CRs. | RAN3#121bis Finalize the solution on required enhancements. Finalize Stage-2 CR(s) Agree the skeleton of Stage-3 CR(s). |  |
| 2023-11 |  | RAN2#124 Finalise Stage 2 & 3 CRs Agree Stage 2 & 3 CRs | RAN3#122 Agree Stage-2 CR(s) and Stage-3 CR(s) |  |
| 2023-12 |  |  |  | RAN#102 Status Report (target of 100% for 14 TUs spent over 15.5) CRs received for approval. |