3GPP TSG-RAN WG2 Meeting #125bis                                                                        R2-2402941

Changsha, China,  April 15th – 19th, 2024

Agenda Item:	    8.9.1

Source: 	    MediaTek Inc. (Rapporteur)

Title:		    Work Plan for Rel-19 IoT NTN

Document for:	    Discussion and decision

# 1 Introduction

In RP#103, a revised WID, “Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3” is approved in [1]. The objectives of this WID are listed below.

- Support of Store&Forward (S&F) satellite operation with full eNB as regenerative payload, therefore:

  - Define the necessary enhancements into E-UTRAN (network & UE) to support S&F operation for delay-tolerant services [RAN3, RAN2]

    - At least specify necessary enhancements e.g. related to S1 protocol, especially to address the feeder link switch over as needed [RAN3]

Note: Strive to minimise UE impact.

Note: Coordination with SA2 (Rel-19 SA2 led Sat-Arch ph3 SI) is needed on the detail requirements (e.g. traffic type, or QoS parameters for S&F), network architecture (e.g. whether consider (partial) core network on satellite) etc.; further coordination with CT1 might be required

- Support of Capacity enhancements for uplink

  - Study then specify, if beneficial, enhancements to enable multiplexing of multiple UEs (e.g. up to the min of 4 and the maximum allowed by the existing UL and DL signalling) in a single 3.75 kHz or 15 kHz subcarrier via orthogonal cover codes (OCC) for NPUSCH format 1 and NPRACH [RAN1, RAN2, RAN4]

    - Multi-tone support for 15 kHz SCS should also be considered

    - Specify necessary signalling, if needed

    - Update RF requirements accordingly, if needed

Note: Impact of impairment shall be taken into account

  - Study and specify, if beneficial the following enhancements to reduce the necessary uplink and downlink signaling to complete an Early Data Transmission (EDT) transaction [RAN2]:

    - Msg3 transmission without msg1/ Random Access Response (RAR)

    - Efficient delivery (reduced overhead) of msg4 / RRCEarlyDataComplete

In this contribution, we discuss the work plan for this WI.

# 2 Work Plan

We propose the following work plan.

| Month | Meeting# | #TU | Work plan |
| --- | --- | --- | --- |
| 2024 Q1 | RAN1#116 | 0.5 | - Discuss RAN1 work plan Capacity enhancements for uplink - Initial discussion on OCC for NPUSCH and NPRACH |
|  | RAN2#125 | 0 |  |
|  | RAN3#123 | 0 |  |
|  | RAN4#110 | 0 |  |
| 2024 Q2 | RAN1#116bis | 0.5 | Capacity enhancements for uplink - Study the benefit and identify the options for usage of OCC on NPUSCH and NPRACH |
|  | RAN2#125bis | 0.5 | - Discuss RAN2 work plan Capacity enhancements for uplink - Initial discussion on enhancements of EDT |
|  | RAN3#123bis | 0 |  |
|  | RAN4#110bis | 0 |  |
|  | RAN1#117 | 0.5 | Capacity enhancements for uplink - Continue discussion on the benefits and the options to use OCC on NPUSCH and NPRACH |
|  | RAN2#126 | 1 | Capacity enhancements for uplink - Study the benefit and identify the options for enhancements of EDT |
|  | RAN3#124 | 0 |  |
|  | RAN4#111 | 0 |  |
| 2024 Q3 | RAN1#118 | 0.5 | Capacity enhancements for uplink - Continue discussion on the benefits and the options to use OCC on NPUSCH and NPRACH |
|  | RAN2#127 | 1 | Capacity enhancements for uplink - Continue discussion on the benefit and options for EDT enhancement - Study the RAN2 impacts on usage of OCC (coordinate with RAN1 if needed) S&F operation for delay-tolerant services - Study on potential RAN2 impact due to S&F operation (coordinate with CT1/SA2/RAN3 if needed) |
|  | RAN3#125 | 0.5 | - Discuss RAN3 work plan S&F operation for delay-tolerant services - Initial discussion on necessary enhancements for S&F |
|  | RAN4#112 | 0.5 (RD) 0.5 (RF) | - Discuss RAN4 RRM core requirement impact and work plan |
| 2024 Q4 | RAN1#118bis | 0.5 | Capacity enhancements for uplink - Down-select the options for the design of OCC on NPUSCH and NPRACH |
|  | RAN2#127bis | 1 | Capacity enhancements for uplink - Continue discussion on the benefit and options for EDT enhancement - Study the RAN2 impacts on usage of OCC (coordinate with RAN1 if needed) S&F operation for delay-tolerant services - Study on potential RAN2 impact due to S&F operation (coordinate with CT1/SA2/RAN3 if needed) |
|  | RAN3#125bis | 0 |  |
|  | RAN4#112bis | 0.5 (RD) 0.5 (RF) | - Discuss RAN4 RRM core requirement |
|  | RAN1#119 | 0.5 | Capacity enhancements for uplink - Discuss on further details for usage of OCC on NPUSCH and NPRACH |
|  | RAN2#128 | 1 | Capacity enhancements for uplink - Conclude on baseline procedure of EDT enhancement - Study the RAN2 impacts on usage of OCC (coordinate with RAN1 if needed) S&F operation for delay-tolerant services - Study on potential RAN2 impact due to S&F operation (coordinate with CT1/SA2/RAN3 if needed) |
|  | RAN3#126 | 0.5 | S&F operation for delay-tolerant services - Continue discussion on necessary enhancements for S&F (coordinate with CT1/SA2/RAN2 if needed) |
|  | RAN4#113 | 0.5 (RD) 0.5 (RF) | - Discuss RAN4 RRM core requirement |
| 2025 Q1 | RAN1#120 | 0.5 | - Further stage-3 works (draft CR, RRC Parameter list) on usage of OCC on NPUSCH and NPRACH |
|  | RAN2#129 | 1 | Capacity enhancements for uplink - Stage-3 details discussion for EDT enhancement and usage of OCC - Identify the RAN2 impacts on usage of OCC (coordinate with RAN1 if needed) S&F operation for delay-tolerant services - Identify the RAN2 impact due to S&F operation (coordinate with CT1/SA2/RAN3 if needed) |
|  | RAN3#127 | 0.5 | S&F operation for delay-tolerant services - Continue discussion on necessary enhancements for S&F (coordinate with CT1/SA2/RAN2 if needed) - Endorse draft CRs |
|  | RAN4#114 | 0.5 (RD) 0.5 (RF) | - Discuss RAN4 RRM core requirement - Initial discussion on UE feature list, if any |
| 2025 Q2 | RAN1#120bis | 0.5 | - Further stage-3 works (draft CR, RRC Parameter list) on usage of OCC on NPUSCH and NPRACH - Initial discussion on UE feature list |
|  | RAN2#129bis | 1 | - Further stage-3 works (draft CRs) on UL capability enhancement and S&F operation. |
|  | RAN3#127bis | 0 |  |
|  | RAN4#114bis | 0.5 (RD) 0.5 (RF) | - Discuss RAN4 RRM core requirement - LS R2 on the UE feature list, if any - Initial draft of corresponding CRs |
|  | RAN1#121 | 0.5 | - Approve corresponding CRs - Finalize RRC parameter list and UE feature list |
|  | RAN2#130 | 1 | - Remaining stage-3 details discussion for draft CR endorsement - UE Capability discussion |
|  | RAN3#128 | 0.5 | - Conclude the remaining details for S&F operation - Endorse draft CRs |
|  | RAN4#115 | 0.25 (RD) 0.5 (RF) | - Endorse corresponding draft CRs |
| 2025 Q3 | RAN1#122 | 0 | - Note: R1 in maintenance phase. |
|  | RAN2#131 | 1 | - Conclude on UE Capability - Approve corresponding CRs |
|  | RAN3#129 | 0.5 | - Approve corresponding CRs |
|  | RAN4#116 | 0.25 (RD) 0.5 (RF) | - Approve corresponding CRs |

# 3 Conclusions

Based on the discussion in section 2, we propose the following:

Proposal 1:  RAN2 to take the above work plan into consideration.

# 4 References

[1] RP-240776, “Revised WID on Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3”, Rapporteur (MediaTek)