3GPP TSG RAN2 meeting #125bis		                                            R2-2403564

Changsha, China, 15th – 19th April 2024

Agenda item: 	    8.10.1

Source: 	China Unicom (WI Rapporteur)

Title: 	Workplan for Rel-19 SON_MDT Enhancement

Document for:	Information

1	Introduction

At RAN#102, the new Work Item on Data Collection for SON_MDT in NR standalone and MR-DC phase 4 was agreed [1]. As WI Rapporteur, in this contribution, we recommend a work plan for RAN2 and RAN3. The workplan captures dependencies among tasks and timeline for RAN2/3.

The WID [1] introduced the following objectives in the core part:

The objective of this work item is to specify data collection enhancement in NR standalone and MR-DC for SON/MDT purpose. The specific objectives of this work item are: - MRO enhancement for R18 mobility mechanisms, including, Lower layer triggered mobility (LTM), CHO with candidate SCGs, subsequent CPAC [RAN3, RAN2]: - Specification of the inter-node information exchange, including possible enhancements to interfaces [RAN3] - Identify and specify necessary UE reporting to enhance the mobility parameter tuning [RAN2] - Support of SON/MDT enhancements for [RAN3, RAN2]: - Intra-NTN mobility - Network Slicing - Support of the leftovers in Rel-18 SON/MDT [RAN3, RAN2]: - RACH optimization for SDT - MHI Enhancement for SCG Deactivation/Activation - MRO for MR-DC SCG failure If needed, co-operate with RAN1, SA2, SA5, CT4. Note 5: Specification of RAN visible QoE for XR related Service types shall take into account the outcome of XR SI and XR WI if applicable.

2	Workplan

2.1	Timeline

Table 1 summarizes a timeline for RAN2 and RAN3 while the timeline is based on the time budget approved at RAN#102 in [2].

Table 1: Timeline for RAN2, 3 efforts

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN2 | #125bis | Apr. 2024 | 0.5 | In the first meeting, RAN2 can start working on the following items considering the limited TU: 1. Discussion on the scenario of MRO enhancement for R18 mobility mechanisms, where LTM can be prioritized. 2. Discussion on leftover features from R18 with corresponding specification impacts: - MHI enhancement with SCG activation/deactivation - RA report enhancement for SDT -Approval of the work plan -Update BL CRs if needed. |
| RAN3 | #123bis | Apr. 2024 | 1.5 | RAN3 can start working on the following items: - Discussion on the scenario and high-level solutions of MRO enhancement for R18 mobility mechanisms, including, Lower layer triggered mobility (LTM), CHO with candidate SCGs, subsequent CPAC, - Discussion on the scenario and high-level solutions for supporting SON/MDT enhancements for intra-NTN mobility - Discussion on the scenario and high-level solutions for supporting SON/MDT enhancements for network slicing Discussion on leftover features from R18 with corresponding specification impacts: MRO for MR-DC SCG failure - Approval of the work plan - Discuss and agree on the BL CR assignment -Update BL CRs if needed. |
| RAN2 | #126 | May 2025 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #124 | May 2024 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #127 | Aug. 2024 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #125 | Aug. 2024 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #127bis | Oct. 2024 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #125bis | Oct. 2024 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #128 | Nov. 2024 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #126 | Nov. 2024 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #129 | Feb. 2025 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #127 | Feb. 2025 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #129bis | Apr. 2025 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #127bis | Apr. 2025 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #130 | May 2025 | 0.5 | Finalize Stage-2 discussion |
| RAN3 | #128 | May 2025 | 1.5 | Finalize Stage-2 discussion |
| RAN2 | #131 | Aug. 2025 | 0.5 | Finalize Stage-3 discussion |
| RAN3 | #129 | Aug. 2025 | 1.5 | Finalize Stage-3 discussion |
| RAN | #109 | Sep. 2025 |  | Functional freeze |

Note that the detailed work plan for the meetings after April will be updated based on the progress.

2.2	BL CRs assignments

38.300, China Unicom

38.401, CMCC

37.340, ZTE

36.413, Qualcomm

36.423, CATT

36.300, Lenovo

37.480, Qualcomm

37.483, Lenovo

SON:

38.413, Ericsson

38.420, Huawei

38.423, ZTE

38.470, Ericsson

38.473, Huawei

MDT:

38.413, Nokia

38.420, Samsung

38.423, CATT

38.470, Nokia

38.473, Samsung

Note:

- Some of the specs listed here may not be affected

- There could be more specs are impacted which can be allocated later.

3	Summary

Proposal 1: RAN2 working group is kindly asked to endorse the workplan.

Proposal 2: Capture the BL CR assignment in the Chair minutes.

4   References

- RP-234038: New WID: Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4; TSG RAN Meeting #102, Edinburgh, Scotland, Dec 11-15, 2023

- RP-232744, Status of time budgets for RAN1/2/3/4 ongoing and new WIs/SIs after RAN #102, TSG RAN Meeting #102, Edinburgh, Scotland, Dec 11-15, 2023