## Sheet1
ID | Delegate | Work Item | Class | TDoc | Status | Processed | Proposed Conclusion | Description | Proposed Change | Comments | Section
C260 | CATT(Hao) | XR | 1 | R2-2402508 | Agreed |  | v32 | the initialazation of transmitting UAI is according to 5.7.4.2 only. Hence, the UE cannot transmit the concerned UL traffic information to the target cell after handover if the UE transmitted the concerned UL traffic information during the last 1 second before handover and the UE is still configured to provide the concened UE assistance information in the target cell. | allow to report the UL traffic information to the target cell after handover, we will address this issue in a Tdoc. | Huawei (rapp): This seems a relevant correciton, I will include it in the rapporteur CR with a slightly modified TP.
B020 | Lenovo (Hyung-Nam) | XR | 1 | None | Agreed |  | v067 | Value should be changed to "barred" to be aligned with TS 38.304, clause 5.3.1: - cellBarred2RxXR (IE type: "barred") Indicated in SIB1 message. In case of multiple PLMNs or NPNs indicated in SIB1, this field is common for all PLMNs and NPNs. This field is only applicable to 2Rx XR UEs. | Change value of cellBarred2RxXR-r18 IE to “barred”. | Huawei (rapp): This is related to TEI18 2Rx XR, so not really for me to decide. But if I was to suggest something, I would propose to rather modify 38.304 as we either have there IE types with both “barred” and “not barred” or IE types with “true” only. This one would then fall into the second category, so we can change “barred” to “true” in 38.304. Lenovo (Hyung-Nam): on B020: I thought the proposed resolution is straightforward considering the fact that all barring-related flags in SIBs (e.g. cellBarredNTN-r17, cellBarredATG-r18, cellBarredFixedVSAT-r18) use the value “barred”. Therefore, my preference is to fix this issue in RRC and not in 38.304. Huawei (rapp)-2024-05-10: after discussion with the proponent it is proposed to agree the issue and the proponent is expected to provide a CR for the relevant TEI18 item.
O502 | OPPO (Zhe) | XR | 1 | R2-xxxxxx | Agreed |  | Q2-v005 | RAN1 has agreed that the time domain resource allocation for multi-PUSCH CG is implemented in a way of Type-A repetition, although they do not support the PUSCH repetition. This restriction for CG Type 2 is already specified by RAN1 but the one for CG Type 1 is missing. | We will provide a paper for R2 to further discuss whether/where to add the restriction for CG Type 1. | Huawei (rapp): The following is captured in 38.214: "For a configuredGrantConfig, if a UE is configured with higher layer parameter nrofSlotsInCG-Period, the UE does not support repetition nor the TB processing over multiple slots for the configuredGrantConfig." Hence, repetition is not supported at all together with nrOfSlotsInCG-Period. There are also other configuration restrictions captured in 38.214: "If a UE is configured with higher layer parameter nrofSlotsInCG-Period in a configuredGrantConfig, the UE does not expect to be configured with cg-nrofSlots and cg-nrofPUSCH-InSlot in the configuredGrantConfig." Since those are very clear in RAN1 specifications already, perhaps there is no need to repeat all of them in our specifications.