## Slide 1
NTT DOCOMO, INC. (Rapporteur)
Work plan for Rel-15 New Radio access technology WI
3GPP TSG RAN WG2 Meeting #97bis
Spokane, USA, April 3-7, 2017
R2-1702533
(Same as RP-170794)

## Slide 2: RAN/RAN1 Time Plan
2017 (C.Y.) |  |  |  | 2018 |  |  | 
RAN1
Channel coding/Modulation
IMT-2020 evaluation
Rel-15
Rel-16
SI(s)
WI(s)
#75
#76
#77
#78
#79
#80
#81
#82
AH
AH
AH
LS to RAN2
Complete PHY common for NSA and Non-SA
Evaluation scenarios
and assumption (ITU)
Sync/system info. broadcast/paging
L1/L2 data/control channels
Scheduling HARQ procedure
MIMO Tx schemes
Random access channel/procedure
Beam management and CSI
RS design, QCL
RRM measurement
NR-NR CA
RAN1only topic
RAN
Remaining issues
UR part of URLLC
UR part of URLLC

## Slide 3: RAN1 Work Plan
Physical layer aspects
  Until Sept. 2017
    Channel coding and modulation;
  Until Dec. 2017
    Physical layer channels for control and data based on associated waveform, numerologies and frame structure in line with the conclusions of the study item, including mini-slot design;
    Synchronization and broadcast channels/signals related to initial access and mobility and channel/signals related to random access, including multi-beam support;
    Downlink and uplink functionality related to multi-antenna transmission/reception enabling closed loop and open/semi-open loop transmissions, beam management, interference measurement, Type I codebook-based CSI acquisition and Type II CSI acquisition as well as CSI acquisition for reciprocity-based operation, the associated reference signal designs, and related quasi-colocation assumptions.
Physical layer procedure(s)
  Until Dec. 2017
    Procedures related to initial access, paging, and mobility;
    Scheduling /HARQ mechanisms.

## Slide 4: RAN1 Work Plan
Duplexing identified in Section 5.1 of TR38.802 supported by a PHY design common to paired and unpaired spectrum, including
  Until Dec. 2017
    Enablers for interference management mechanisms for handling cross-link interference.
NR-LTE co-existence mechanisms
  Until Dec. 2017
    Support co-existence of LTE UL and NR UL within the bandwidth of an LTE component carrier and co-existence of LTE DL and NR DL within the bandwidth of an LTE component carrier, and identify and specify at least one NR band/LTE-NR band combination for this operation.
Support of ultra-reliable part of URLLC
  Jun. 2017 – Dec. 2017
    Identify techniques to meet the URLLC requirements set forth by [TR38.913] starting after RAN#76
  Dec. 2017 – June 2017
    Conduct corresponding URLLC specific normative work after RAN#78 for the selected techniques

## Slide 5: RAN2 Time Plan
2017 (C.Y.) |  |  |  | 2018 |  |  | 
RAN2
RAN
Rel-15
Rel-16
#75
#76
#77
#78
#79
#80
#81
#82
AH
AH?
PDCP/RLC/MAC (common to NSA and SA, including CA within NR)
RRC procedures for NSA including UE capability coordination and CA configuration within NR
System information design at least for NSA
PDCP and new ASL specific to SA (e.g. flow based QoS)
Stage-2 for NSA
Stage-2 for SA
Additional system information design for SA
Secondary Node (NR) mobility including multi-beam operation (some parts are common to SA)
ASN.1 freeze for NSA
ASN.1 freeze for SA
Additional mobility required for SA including NR UE state machine
RRC procedures for SA including access control and NW slicing
Measurements required for NSA
Additional measurements required for SA

## Slide 6: RAN2 work prioritisation
Features for Dec 2017 early drop | Features for Phase 1 (beyond Dec 2017)
・Layer 2 protocols - PDCP - RLC - MAC ・Minimum System Information required for NSA ・Secondary Node (NR) mobility - beam level mobility is included ・Measurements required for NSA, including - NR measurements for UE in LTE - Measurements for Secondary Node mobility ・RRC procedures for NSA - UE capability coordination is included ・Carrier Aggregation with NR for Secondary Node (i.e. only PSCell and SCell) | ・New AS layer for flow based QoS ・Additional System Information for SA ・Additional mobility required for SA, including - NR UE state machines and relevant mobility - NR paging ・Additional measurements for SA ・Additional RRC procedures for SA, including - access control - security key management ・Network slicing

## Slide 7: RAN3 Time Plan
2017 (C.Y.) |  |  |  | 2018 |  |  | 
RAN3
RAN
Rel-15
Rel-16
#75
#76
#77
#78
#79
#80
#81
#82
AH
AH?
Xx-C IF based on LTE DC procedures over X2-C
ASN.1 freeze for SA
NG-C/U IF including NW slicing support and flow based QoS
Xx-U IF based on LTE DC procedures over X2-U
Xn-C/U IF including intra-NR and inter-RAT mobility
Higher layer split for CU-DU split RAN architecture
(higher priority is set to NSA specific aspects if any)
Xx-C IF based on LTE DC procedures over X2-C

## Slide 8: RAN3 work prioritisation
Features for Dec 2017 early drop | Features for Phase 1 (beyond Dec 2017)
・Xx-C/U interface for EN-DC (option 3) operation, including; - SgNB addition - SgNB modification (MeNB/SgNB initiated) - Intra-MeNB HO involving SCG change - SgNB release (MeNB/SgNB initiated) - MeNB to eNB change and vice versa - SCG change - Inter-MeNB HO w/o SgNB change ・Higher layer split for CU-DU split RAN architecture (for EN-DC operation) | ・NG and Xn interface for; - Standalone NR operation - Flow based Qos - Intra-NR mobility for connected/inactive - Inter-RAT mobility - Network slicing ・Higher layer split for CU-DU split RAN architecture (for Standalone NR operation, if there is delta from EN-DC)

## Slide 9: RAN/RAN4 Time Plan
2017 (C.Y.) |  |  |  | 2018 |  |  | 
RAN4
Rel-15
Rel-16
#75
#76
#77
#78
#79
#80
#81
#82
AH
AH?
AH
AH?
RAN
Milestone
UE/BS Common RF
Including spectrum
(common to NSA and SA)
UE RF/BS RF
(common to NSA and SA)
RRM
Performance part
Common NAS and SA. Specific to NSA
Cornerstones, e.g., CBW for UE RF/BS RF/RRM spec is determined based on RAN1 spec.
Assumptions, e.g., for simulation for the requirements for UE RF/BS RF/RRM are determined based on R1 spec.
Specific to SA
Finalize the core requirements (values) based on evaluation results.
Common NAS and SA. Specific to NSA
Bands and band combinations related spec such CBW as well as TBC size shall be determined.
After AH, needs stable RAN1 spec impacting on RAN4 evaluation. E.g. SS and RS signal design for RRM measurement, etc
Specific to SA
Initial simulation assumptions for performance part are determined based on core requirements.