3GPP RAN WG3 Meeting #117-e	R3-224235

Electronic meeting, August 15th – 24th, 2022								rev RP-220389

Title:	R18 WI NR-NTN-enh work plan at RAN1, 2 and 3

Source:	Thales

Type:	Work Plan

For:	Agreement

Agenda Item:	17.1 general

Release:	Rel-18

WI:	NR NTN enhancements

# Introduction

In this contribution, an updated work plan for the Rel-18 NR-NTN-enh work item [1] is proposed for RAN 1, 2 & 3.

# WID Objective

The work item aims at specifying enhancements for NG-RAN based NTN (Non-Terrestrial Networks) according to the following assumptions with implicit compatibility to support HAPS (Altitude Platform Station) and ATG (Air To Ground) scenarios:

- GSO (Geo Synchronous Orbit) and NGSO (Non Geo Synchronous Orbit). NGSO includes Low Earth Orbit (LEO) and Medium Earth Orbit (MEO)

- Earth fixed tracking area. Earth fixed & Earth moving cells for NGSO

- FDD mode

- UEs with GNSS (Global Navigation Satellite Systems) capabilities

- Both “VSAT” (Very Small Aperture Terminal) devices with directive antenna (including fixed and moving platform mounted devices and commercial handset terminals (e.g. Power class 3) are supported in FR1

- Only “VSAT” devices with directive antenna (including fixed and moving platform mounted devices) are supported in above 10 GHz bands.

Note: In Rel-17 WID, “VSAT” device with external antenna on moving platform is equivalent to a device that operate on platforms in motion, and this is referred to as ESIM (Earth Station In Motion).

Note 2: The Rel-17 NTN architecture is assumed.

The detailed objectives are to specify enhancing features to Rel-15, 16 & 17’s NR radio interface & NG-RAN as follows:

- Coverage enhancement

The Rel-18 NTN objectives are focused on the applicability of the solutions developed by general NR coverage enhancement to NTN, and identifying potential issues and enhancements if necessary, considering the NTN characteristics including large propagation delay and satellite movement. Only NTN-specific characteristics are to be included in this coverage enhancement work, otherwise it should be part of another WI (e.g., UL enhancement of coverage). The work needs to cover the use case of voice and low-data rate services using commercial smartphones with more realistic assumptions on antenna gains instead of 0dBi currently assumed for link budget analysis for non-terrestrial networks. The specific realistic antenna gain assumption will be determined at the working group level. The evaluation should also take into account any related regulatory

requirements, e.g., ITU limitation of power flux density.

Have a 1-TU 6-month study phase focusing on the following (to derive clear & limited scope):

- Evaluate the coverage performance and identify the candidate physical radio channels that have coverage issues specific to NTN with following target services taking into account the studies in TR38.830 where appropriate, as well as general coverage enhancement techniques specified in Rel-18 [RAN1,RAN2,RAN4]

  - VoIP and low-data rate services for commercial handset terminals

The following items are shown as examples of areas to consider in the next step of the study. The actual items for study will be based on the evaluation of coverage issues specific to NTN identified above.

- NTN-specific repetitions enhancements beyond techniques covered in Rel-17 CovEnh WI for the relevant channels

- NTN-specific techniques for improved diversity and/or reduced polarization loss

- Improved performance of low-rate codecs in link budget limited situation including reducing RAN protocol overhead for VoNR

  - NOTE: Intent is not to introduce a new codec.

RAN to determine by RAN#97 (for RAN1 items) and RAN#98 (for RAN2 items) whether the study phase has identified any need for NTN-specific coverage enhancements in Rel-18. If needed, the set of NTN-specific work item objectives will be updated.

- NR-NTN deployment in above 10 GHz bands

The following assumptions are taken a baseline for this work:

- GSO and NGSO (e.g. LEO, MEO, HEO) based satellite access to be considered

  - ESIM scenarios for NGSO in Ka band are not considered in this WI.

- Targeted UE types: fixed and mobile VSAT. VSAT UE characteristics from TR38.821 to be considered in priority but additional NTN UE classes may be considered if justified

  - Regarding mobile VSAT, three types of terminal and scenario exist; airborne, maritime and land based ESIM. Which type(s) to be specified depends on the outcome of the regulation analysis and co-existence study.

- FDD mode is assumed for satellite operation above 10 GHz, while TDD mode is assumed for terrestrial operation in FR2

- The ITU-R harmonized Ka band will serve as reference

- Co-existence between overlapping NTN and TN band portions is out of scope of this work item. This aspect will be captured in the specification.

The following covers the objectives for NR-NTN deployment in above 10 GHz bands. This work is expected to start after June 2022.

- Study and identify NTN example band: Analysis of regulations and adjacent channel co-existence scenarios. The example band shall be identified early in the WI. Additional bands can be introduced in a release-independent manner. [RAN4]

  - Consider the satellite harmonized Ka band as a reference, according to ITU allocation; taking into account deployment type (e.g. VSAT, ESIM), scenarios, and ITU-R/regional regulations, define an example band suitable for development of generic 3GPP minimum performance requirements (the example RAN4 band may be a portion of or the entire harmonized Ka band). [RAN4]

  - Study implications of FDD operation in FR2 and derive requirements for the identified example band appropriately. Satellite bands introduced in 3GPP for NTN for FDD shall not impact the existing 3GPP TDD specifications for terrestrial bands adjacent to the NTN band (see note 3 of the approved way forward RP-211596 in RAN#92-e). [RAN4]

  - Relevant coexistence scenarios and analysis to be considered in RAN4, if and where applicable, to ensure that satellite bands introduced in 3GPP for NTN shall not impact the existing specifications and shall not cause degradation (in the sense of RAN4 co-existence studies) to networks in 3GPP specified terrestrial bands adjacent to the NTN band. In that, it is assumed that the NTN-TN adjacent band coexistence will be performed at the harmonized Ka band edges. The outcome is expected to be applicable to all NTN-TN adjacent band scenarios (if any) in the whole Ka band range where applicable and regulations allow. [RAN4]

  - For all the above, RAN4 process as agreed for NTN in FR1 should be used for coexistence analysis in above 10 GHz bands [RAN4].

  - Definition of NTN band(s) above 10 GHz does not change the current FR1/FR2 definition, nor automatically apply to future terrestrial bands defined in this frequency region; (see proposal 2 of the approved way forward RP-211596 in RAN#92-e) [RAN4]

- Specify Rx/Tx requirements for satellite access node and different VSAT UE class (not only 60 cm aperture) as appropriate for the identified example band [RAN4]

- Identify values for physical layer parameters chosen from the existing FR1 and FR2 sets. The following set of parameters to specify, but not necessarily limited to, are listed.as follows [RAN4]:

  - time relationship related enhancement (e.g. K_offset)

  - subcarrier spacing for different UL/DL signals/channels

  - PRACH configuration index for FDD above 10 GHz.

- Network verified UE location

Pending on the conclusion of the RAN SI FS_NR_NTN_netw_verif_UE_loc study item, study and evaluate, if needed, solutions for network to verify UE reported location information [RAN2,RAN1,RAN3].

RAN is expected to determine by RAN#98 whether the study has identified any need for Network verified UE location specification support in Rel-18.

- NTN-TN and NTN-NTN mobility and service continuity enhancements

This work considers existing methods from NR TN as well as outcome of Rel-17 NR NTN WI outcome as baseline for NTN-TN mobility.

- Specify NTN-TN and NTN-NTN measurement/mobility and service continuity enhancements [RAN2,RAN3,RAN4]

  - For NTN-NTN mobility, specify cell reselection enhancements for earth moving cell, the timing based and location-based cell reselection for quasi-earth fixed cell in Rel-17 can be considered as the starting point. [RAN2, RAN3, RAN4]

  - Specify NTN-NTN handover enhancement for RRC_CONNECTED UEs in the quasi-earth-fixed cell and earth-moving cell to reduce the signalling overhead. [RAN2, RAN3]

  - Specify cell reselection enhancements for RRC_IDLE/INACTIVE UEs to reduce UE power consumption (NTN-TN mobility is prioritized). [RAN2, RAN3, RAN4]

  - Study and, if needed, specify enhancement to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs. [RAN3]

NOTE: The objective on mobility and service continuity enhancements will be clarified at RAN#95-e.

# Work Plan

The work plan for each WID objective is given within the following sub-sections.

## Coverage enhancement:

The tentative work plan for coverage enhancement study item, which may be followed by a work item is proposed as follows:

Note that depending on the SI outcomes, the set of NTN-specific work item objectives will be updated.

| Meetings | WG and TU | Objectives |
| --- | --- | --- |
| August 2022, RAN1#110 August 2022, RAN2#119 | RAN1 0.25 TU | Discuss the coverage performance for each scenario, including VoNR and low-data rate services using commercial smartphones. Identify the physical channels that have coverage issue in NTN Conclude the baseline coverage performance for each scenario (GSO and NGSO), including VoIP and low-data rate services using commercial smartphones Conclude on the remaining aspects, if any. Conclude the study item. |
|  | RAN2 0.2 TU | Discuss potential RAN2 impacts depending on RAN1 progress |
| October 2022, RAN1#110-bis October 2022, RAN2#119-bis | RAN1 0.25 TU | Discuss the potential solutions and the performance for coverage enhancements in NTN environment. This may include: - NTN-specific repetitions enhancements beyond techniques covered in Rel-17 CovEnh WI for the relevant channels - Discuss NTN-specific techniques for improved diversity and/or reduced polarization loss - Improved performance of low-rate codecs in link budget limited situation including reducing RAN protocol overhead for VoNR - NOTE: Intent is not to introduce a new codec. Identify the potential specification impacts. |
|  | RAN2 0.2 TU | Discuss potential RAN2 impacts on user plane (HARQ, timers), control plane (SIB, RRC signaling) depending on RAN1 progress on the potential solutions. If needed send LS to RAN1 |
| November 2022, RAN1#111 November 2022, RAN2#120 | RAN1 0.25 TU | Discuss the solutions for coverage enhancements in NTN environment. This may include: Discuss the detailed design for physical channel subject to coverage enhancement in NTN Discuss NTN-specific techniques for improved diversity and/or reduced polarization loss Discuss solutions to improve performance of low-rate codecs in link budget limited situation including reducing RAN protocol overhead for VoNR Other solutions may be discussed depending on the SI outcomes |
|  | RAN2 0.2 TU | Further discuss potential RAN2 impacts on user plane (HARQ, timers), control plane (SIB, RRC signaling) depending on RAN1 progress on the potential solutions. If needed send LS to RAN1 |
| February 2023, RAN1#112 February 2023, RAN2#121 | RAN1 0.25 TU | Further discuss the solutions for coverage enhancements in NTN environment. This may include: Further discuss the detailed design for physical channel subject to coverage enhancement in NTN Further discuss NTN-specific techniques for improved diversity and/or reduced polarization loss Further discuss solutions to improve performance of low-rate codecs in link budget limited situation including reducing RAN protocol overhead for VoNR Other solutions may be discussed depending on the SI outcomes |
|  | RAN2 0.2 TU | Further discuss potential RAN2 impacts on user plane (HARQ, timers), control plane (SIB, RRC signaling) depending on RAN1 progress on the potential solutions. If needed send LS to RAN1 |
| April 2023, RAN1#112-bis April 2023, RAN2#121-bis | RAN1 0.25 TU | Further discuss the solutions for coverage enhancements in NTN environment. This may include: Further discuss the detailed design for physical channel subject to coverage enhancement in NTN Further discuss NTN-specific techniques for improved diversity and/or reduced polarization loss Further discuss solutions to improve performance of low-rate codecs in link budget limited situation including reducing RAN protocol overhead for VoNR Other solutions may be discussed depending on the SI outcomes Discuss related RRC parameters, if needed, and send LS to RAN2 Discuss draft CRs |
|  | RAN2 0.2 TU | Further discuss potential RAN2 impacts on user plane (HARQ, timers), control plane (SIB, RRC signaling) depending on RAN1 progress on the potential solutions. If needed send LS to RAN1 |
| May 2023, RAN1#113 May 2023, RAN2#122 | RAN1 0.25 TU | Discuss the remaining aspects of the solutions for coverage enhancements in NTN environment. Further discuss related RRC parameters, if needed, and send LS to RAN2 Discuss draft CRs |
|  | RAN2 0.2 TU | Discuss the remaining aspects of the solutions for coverage enhancements in NTN environment. Discuss draft CRs |
| August 2023, RAN1#114 August 2023, RAN2#123 | RAN1 0.25 TU | Conclude on the solutions for coverage enhancements in NTN environment. Further discuss related RRC parameters, if needed, and send LS to RAN2 Finalize RAN1 CRs. |
|  | RAN2 0.2 TU | Conclude on the solutions for coverage enhancements in NTN environment. Discuss draft CRs. |
| October 2023, RAN2#123-bis | RAN2 0.2 TU | Discuss draft CRs.Conclude on the remaining aspects, if any |
| November 2023, RAN2#124 | RAN2 0.2 TU | Finalize RAN2 CRs.Conclude on the remaining aspects, if any |

## Network verified UE location:

The tentative work plan for Network verified UE location study item, which may be followed by a work item is proposed as follows:

Note that depending on the SI outcomes, the set of NTN-specific work item objectives will be updated.

| Meetings | WG and TU | Objectives |
| --- | --- | --- |
| August 2022, RAN1#110 August 2022, RAN2#119 August 2022, RAN3#117 | RAN1 0.25 TU | Discuss solutions for network to verify UE reported location information Discuss the performance of Rel-17 positioning solutions by considering NTN constraints for both GSO and NGSO scenarios (i.e. wider radio cell and limited number of satellite in view) and target requirements for NR positioning enhancements in Rel-18: - Positioning accuracy analysis - Physical layer latency analysis Discuss NR positioning enhancements for NTN Discuss the performance of studied NR positioning enhancements for NTN Identify NR impacts in Rel-18 |
|  | RAN2 0.4 TU | Discuss solutions for network to verify UE reported location information - Understanding of the issues to be addressed at user plane and control plane level - Identification and analysis of existing 3GPP solutions that could be considered as candidate for network verified UE location for NTN - Evaluate the need for enhancements |
|  | RAN3 0.25 TU | Discuss solutions for network to verify UE reported location information - Understanding of the issues to be addressed at NG RAN architecture level - Identification and analysis of existing 3GPP solutions that could be considered as candidate for network verified UE location for NTN - Evaluate the need for enhancements |
| October 2022, RAN1#110-bis October 2022, RAN2#119-bis October 2022, RAN3#117-bis | RAN1 0.25 TU | Further discuss the potential solutions for network to verify UE reported location information Further discuss the performance of studied NR positioning enhancements for NTN Identified NR impacts in Rel-18 |
|  | RAN2 0.4 TU | Further discuss solutions for network to verify UE reported location information - Understanding of the issues to be addressed - Identification and analysis of existing 3GPP solutions that could be considered as candidate for network verified UE location for NTN - Evaluate the need for enhancements |
|  | RAN3 0.25 TU | Further discuss solutions for network to verify UE reported location information - Understanding of the issues to be addressed at NG RAN architecture level - Identification and analysis of existing 3GPP solutions that could be considered as candidate for network verified UE location for NTN - Evaluate the need for enhancements |
| November 2022, RAN1#111 November 2022, RAN2#120 November 2022, RAN3#118 | RAN1 0.25 TU | Down-select suitable solutions for network to verify UE reported location information Agree on NR positioning enhancements for NTN |
|  | RAN2 0.4 TU | Conclude on the need for enhancements |
|  | RAN3 0.25 TU | Conclude on the need for enhancements |
| February 2023, RAN1#112 February 2023, RAN2#121 February 2023, RAN3#119 | RAN1 0.25 TU | Agree on detailed design for solutions for network to verify UE reported location information Agree on detailed design for NR positioning enhancements for NTN |
|  | RAN2 0.4 TU | If needed discuss enhancement solutions for network verified UE location |
|  | RAN3 0.25 TU | If needed discuss enhancement solutions for network verified UE location |
| April 2023, RAN1#112-bis April 2023, RAN2#121-bis April 2023, RAN3#119-bis | RAN1 0.25 TU | Agree on detailed design for solutions for network to verify UE reported location information Agree on detailed design for NR positioning enhancements for NTN |
|  | RAN2 0.4 TU | If needed discuss enhancement solutions for network verified UE location |
|  | RAN3 0.25 TU | If needed discuss enhancement solutions for network verified UE location |
| May 2023, RAN1#113 May 2023, RAN2#122 May 2023, RAN3#120 | RAN1 0.25 TU | Conclude on detailed design for solutions for network to verify UE reported location information Conclude on detailed design for NR positioning enhancements for NTN Discuss related RRC parameters, if needed, and send LS to RAN2 Discuss draft CRs |
|  | RAN2 0.4 TU | If needed discuss enhancement solutions for network verified UE location |
|  | RAN3 0.25 TU | If needed discuss enhancement solutions for network verified UE location |
| August 2023, RAN1#114 August 2023, RAN2#123 August 2023, RAN3#121 | RAN1 0.25 TU | Conclude on the remaining aspects, if any Further discuss related RRC parameters, if needed, and send LS to RAN2 Finalize RAN1 CRs. |
|  | RAN2 0.4 TU | If needed discuss enhancement solutions for network verified UE location |
|  | RAN3 0.25 TU | Address RAN3 impacts depending on RAN1/RAN2 progress |
| October 2023, RAN2#123-bis October 2023, RAN3#121-bis | RAN2 0.4 TU | If needed discuss RAN2 draft CRs |
|  | RAN3 0.25 TU | If needed discuss RAN3 draft CRs |
| November 2023, RAN2#124 November 2023, RAN3#122 | RAN2 0.4 TU | If needed finalize RAN2 draft CRs Conclude on the remaining aspects, if any |
|  | RAN3 0.25 TU | If needed finalize RAN3 draft CRs Conclude on the remaining aspects, if any |

## NTN-TN and NTN-NTN mobility and service continuity enhancements

| Meetings | WG and TU | Objectives |
| --- | --- | --- |
| August 2022, RAN2#119 August 2022, RAN3#117 | RAN2 0.4 TU | Discuss enhancements for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode mobility |
|  | RAN3 0.25 TU | Discuss enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs |
| October 2022, RAN2#119-bis October 2022, RAN3#117-bis | RAN2 0.4 TU | Further discuss enhancements for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode mobility |
|  | RAN3 0.25 TU | Further discuss enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs |
| November 2022, RAN2#120 November 2022, RAN3#118 | RAN2 0.4 TU | Further discuss enhancements for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode |
|  | RAN3 0.25 TU | Further discuss enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs |
| February 2023, RAN2#121 February 2023, RAN3#119 | RAN2 0.4 TU | Further discuss enhancements for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode |
|  | RAN3 0.25 TU | Further discuss enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs |
| April 2023, RAN2#121-bis April 2023, RAN3#119-bis | RAN2 0.4 TU | Further discuss enhancements for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode |
|  | RAN3 0.25 TU | Further discuss enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs |
| May 2023, RAN2#122 May 2023, RAN3#120 | RAN2 0.4 TU | Agree on detailed design and solution for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode |
|  | RAN3 0.25 TU | Agree on detailed design of solution for enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs |
| August 2023, RAN2#123 August 2023, RAN3#121 | RAN2 0.4 TU | Agree on detailed design and solution for: - NTN-NTN idle mode mobility (earth moving cells) - NTN-NTN connected mode mobility (optimizations) - NTN-TN idle mode mobility (optimizations) - If time allows NTN-TN connected mode |
|  | RAN3 0.25 TU | Agree on detailed design of solution for enhancements to Xn[/NG] signalling to support feeder link switch-over, CHO, e.g. exchange of necessary information between gNBs |
| October 2023, RAN2#123-bis October 2023, RAN3#121-bis | RAN2 0.4 TU | Conclude on the detailed solution Discuss RAN2 draft CRs |
|  | RAN3 0.25 TU | Conclude on the detailed solution Conclude on the remaining aspects, if any Discuss RAN3 draft CRs |
| November 2023, RAN2#124 November 2023, RAN3#122 | RAN2 0.4 TU | Agree on the remaining details Conclude on the remaining aspects, if any Finalize RAN2 CRs. |
|  | RAN3 0.25 TU | Agree on the remaining details Conclude on the remaining aspects, if any Finalize RAN3 CRs. |

# References

RP-221819 R18 WID NR_NTN_enhancements

END