3GPP TSG-RAN WG3 Meeting #119                                                                 R3-230226

Athens, Greece, February 27 – March 3, 2023

Agenda item: 		13.1

Source: 		Qualcomm Incorporated (WI Rapporteur)

Title: 	Workplan for Rel-18 mobile IAB

Document for:	Information

# 1	Introduction

At RAN#94e, the Work Item on Mobile IAB (Integrated Access and Backhaul) for NR (NR_mobile_IAB) was agreed [1]. As WI Rapporteur, in this contribution, we recommend a work plan for RAN2, RAN3 and RAN4. The workplan captures interdependences among tasks and timeline for RAN2/3/4.

The WID [1] introduced the following objectives in the core part:

The detailed objectives of the WI are listed as follows: - Define Procedures for migration/topology adaptation to enable IAB-node mobility, including inter-donor migration of the entire mobile IAB-node (full migration) [RAN3, RAN2] - The mobile IAB-node can connect to a stationary (intermediate) IAB-node. Optimizations specific to the scenarios, where the mobile IAB-node connects to a stationary (intermediate) IAB-node, or where it directly connects to an IAB-donor-DU are de-prioritized. - The mobility of dual-connected IAB-nodes is down-prioritized. - Enhancements for mobility of an IAB-node together with its served UEs, including aspects related to group mobility. No optimizations for the targeting of surrounding UEs. [RAN3, RAN2] Note: Solutions should avoid touching upon topics where Rel-17 discussions already occurred and where the topic was excluded from Rel-17, except for enhancements that are specific to IAB-node mobility. - Mitigation of interference due to IAB-node mobility, including the avoidance of potential reference and control signal collisions (e.g. PCI, RACH). [RAN3, RAN2] The following principles should be respected: - Mobile IAB-nodes should be able to serve legacy UEs. - Solutions providing optimization for Mobile IAB may entail Rel-18 UE enhancements, provided that such enhancements are backwards compatible RAN4 is expected to study impact on RF and RRM requirements: - Conduct co-existence study to assess the impact of moving cells. Based on the study outcome, specify RF and RRM requirements and mechanisms for the mobile IAB-node to enable co-existence, if needed. - Specify RRM requirements for the mobile IAB-node to enable IAB-node mobility, if needed. The involvement of RAN1 may be needed, depending on work progress.

The WID [1] introduced the following objectives in the performance part:

- Specify RF conformance requirements for the mobile IAB-node, if needed. - Specify RRM and demodulation performance requirements for the mobile IAB-node by taking into account IAB-node mobility, if needed.

The WID further emphasizes on interaction with SA2:

- Alignment and coordination with Rel-18 SA2 work on VMR should be considered, if needed.

# 2	Workplan

## 2.1	Prioritization of efforts

This section captures prioritization of the various tasks defined as well as interdependences among these tasks handled by different RAN WGs.

RAN3/2-related efforts:

- Procedures for migration/topology adaptation to enable IAB-node mobility, including inter-donor migration of the entire mobile IAB-node (full migration):

This objective primarily focuses on the migration of the mobile IAB-node. The following topics should be considered:

  - Inter-donor migration of the entire IAB-node (full migration): RAN3 can be expected to take the lead in this effort. RAN3 can continue the discussion on full migration started in Rel-17. Since this discussion is expected to have impact on RAN2 and potentially also RAN1 and RAN4, RAN3 should start with this effort in the first meeting. RAN2 and potentially other RAN WGs may wait for RAN3 progress on this topic.

  - Other new procedures or enhancements to existing procedures related to this objective can be defined by RAN3 and RAN2. New procedures should be identified at the beginning of the WI since such work typically takes significant time and may further affect other RAN WGs. As always, new functionality that is necessary to support IAB-node mobility should be given higher priority than optimizations to existing functionality.

  - Topology adaptation in absence of Xn was identified in Rel-18 SA2 Study on VMR as part of key issue #3. RAN3 may want to consider discussing the relevance of this issue for RAN independent of SA2’s effort. This discussion should start early in case interaction with SA2 is necessary.

- Enhancements needed for the mobility of an IAB-node together with its served UEs, including aspects related to group mobility:

This objective primarily focuses on the impact on the UE connected to or camping on a mobile IAB-node cell. It can also include handover to and/or reselection of a mobile IAB-node cell. The objective allows for enhancements in a variety of areas; a few of them are given below. The discussion should include the consideration of the support for legacy UEs. RAN2 and RAN3 should identify the enhancements to be handled in Rel-18 at the beginning of the WI so that sufficient time remains for thorough discussion. In this discussion, the definition of new functionality should be given priority over optimizations. For new procedures, optimizations should only be considered after a baseline has been defined.

The following areas may be explored by RAN2 and RAN3:

  - Enhancements to cell (re-)selection between stationary network and mobile IAB-node, and between mobile IAB-nodes.

  - Enhancements to UE access to the mobile IAB-node vs. the stationary network.

  - Enhancements to UE handover between stationary network and mobile IAB-node and between mobile IAB-nodes.

  - Enhancements for location updates (TA, RNA) for UEs that are camping on or connected to mobile IAB-node cells. This issue was identified in Rel-18 SA2 Study on VMR as key issues #5 and #6. RAN3 and RAN2 may want to consider discussing the relevance of this issue for RAN independently of SA2’s effort.

  - Signalling optimizations due to collective migration of UEs connected to a mobile IAB-node. This may include the bundling of UE-associated information into one common message. RAN3 should consider optimizations of this nature at a later stage of the WI after the baseline procedures (i.e., w/o such bundling) have been established.

- Mitigation of interference due to IAB-node mobility, including the avoidance of potential reference and control signal collisions (e.g., PCI, RACH):

The following topics may be explored under this objective:

  - PCI collision avoidance: RAN3 may discuss means for PCI collision avoidance. RAN2 may discuss potential means for PCI collision detection.

  - RACH resource collision avoidance: RAN2 may discuss potential issues related to this topic.

  - Other issues related to interference mitigation may be identified and discussed in RAN2 and RAN3.

- Note on potential complexity related to multi-hop backhauling for mobile IAB:

  - Aspects of the potential complexity related to multi-hop backhauling should be briefly discussed at the beginning of the WI in RAN2 and RAN3.

RAN4-related efforts (Core Part):

- Co-existence study to assess the impact of moving cells.

  - The co-existence criteria defined in Rel-16/17 only apply to stationary IAB-nodes, and they were based on a specific minimum distance between IAB-nodes and macro-cell. For mobile IAB-nodes, the assumption on the minimum distance and the implications on power control, receiver dynamic range, etc. need to be revised. RAN4 may need to consider if additional simulation work is needed. These topics should be discussed early during the RAN4 effort since they are expected to consume a lot of time.

- RRM requirements for the mobile IAB-node to enable IAB-node mobility.

  - RRM requirements defined in Rel-16/17 only included RLF recovery. For mobile IAB, the IAB-node is expected to undergo frequent topology adaptations. The associated RRM requirements need to be discussed. This discussion should include identification of the relevant mobile IAB scenarios. The prior RAN work on high-speed trains should be included into these considerations. These topics should be discussed early since they are expected to consume a lot of time.

RAN4-led efforts (Performance Part):

- The topics related to the performance part need to be handled based on the progress of the discussion on the Core Part.

Alignment and coordination with Rel-18 SA2 work on VMR

- RAN WGs should try to align efforts on mobile IAB with SA2 normative work on VMR if such normative work is agreed by SA2. It is expected that such alignment will be discussed by TSG RAN before.

- RAN WGs may want to include into the discussion all aspects related to the key issues identified by the SA2 Study on VMR that have RAN impact and are aligned with the RAN WI objectives. The above outline has captured some aspects that might be considered.

## 2.2	Timeline

Table 1 summarizes a timeline for RAN2/3/4. This timeline is based on RP-221060 [2].

Table 1: Timeline for RAN2, 3, 4 efforts

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN2 | #121 | Feb 2023 | 0.5 | AI 8.12.1: General Discussion on SA2’s LS in S2-2211437 and potential replies. AI 8.12.2: Enhancements for the mobility of an IAB-node together with its served UEs, including aspects related to group mobility. - Mobile-IAB-node broadcast: R2#119bis-e agreed that 1bit for mobile-cell-type indication is broadcast. R2#120 it was agreed to define the behaviour of the UE detecting this indicator. One aspect discussed in this context related to the UE’s determination of its mobility state. Contributions to the last meeting further proposed change of the inter-frequency (re-)selection behaviour. We need to converge on this topic. - Other topics: Propose/discuss enhancements that fall under this objective and are in RAN2 scope. AI 8.12.3: Procedures for migration/topology adaptation to enable IAB-node mobility, including inter-donor migration of the entire mobile IAB-node (full migration) - Location info: TAC/RANAC broadcast by IAB-node: - RAN3 agreed: - Static TAC solution is not pursued. - RAN3 assumes that dynamic TAC solution should be supported. - RAN3 to continue discussions on impacts (if any) of dynamic TAC solutions on RAN3 specs - Send an LS to RAN2 (include SA2 in To) informing RAN2 of the decisions taken by RAN3 and send LS to RAN2 in R3-226831. RAN2 should discuss RAN2-related aspects of this agreement. RAN2 should further discuss handling of RANAC during IAB-DU migration, and the potential impact on UEs in RRC INACTIVE. Impact on BAP: During DU-migration, there are time frames where the IAB-node concurrently supports two logical DUs. RAN2 needs to discuss if this has any impact on the mobile IAB-node’s BAP configuration (BAP address, default configuration, routing and UL mapping configurations for both logical DUs). The discussion should focus on RAN2-related aspects. - Other topics: Propose/discuss enhancements that fall under this objective and are in RAN2 scope. AI 8.12.4: Mitigation of interference due to IAB-node mobility, including the avoidance of potential reference and control signal collisions (e.g. PCI, RACH) This topic was not handled in last meeting. - PCI collision: RAN2 agreed that further work on this matter would be based on LS by RAN3. |
| RAN3 | #119 | Feb 2023 | 1 | AI 13.1: General Discussion on SA2’s LS in S2-2211437 and potential replies. AI 13.2: Procedures for migration/topology adaptation to enable IAB-node mobility, including inter-donor migration of the entire mobile IAB-node (full migration) - Migration procedures - Last meeting, RAN3 agreed: WA: The mIAB-MT and its co-located mIAB-DU can be handed over/migrated to different donor CUs. This WA is subject to validation that the impact involved is affordable. - We need to discuss if the WA can be made an agreement or if there are any technical obstacles to this WA. - Last meeting, RAN3 agreed: The mIAB-MT’s source donor CU can send the info on the mIAB-MT’s target donor CU to the mIAB-DU’s donor CU after the completion of IAB-MT HO. - This agreement is insufficient since it does not preclude collision between DU migration and next following MT migration. We therefore need to discuss: - What would be the impact in case DU migration and MT migration collide, if any? There might be race conditions to be considered. How can they be addressed? - Otherwise, how can the collision of DU migration and MT migration be avoided? - We need to converge if this matter. - Last meeting, RAN3 agreed: The mIAB-MT ID sent by the mIAB-MT’s source donor CU to the mIAB-DU’s donor CU is the XnAP UE ID. FFS which donor generates this ID. - We need to discuss how this mIAB-MT’s Xn UE IE information is generated and passed on so that it can be used by the mIAB-DU’s donor to unambiguously identify the mIAB-MT at any later point in time. - Last meeting, RAN3 agreed: The trigger for F1 setup between the mobile IAB-node’s second logical DU and its donor CU may be based on OAM or pre-configuration. - We need to clarify if and how the CU knows that it itself should trigger the F1 setup vs. leaving it up to the IAB-node to proactively initiate F1 setup. - Further discussion on the following topics: - How the 1st logical DU’s donor is informed about the completion of the F1 setup for the 2nd logical DU. - How the 1st logical DU’s donor is informed about the 2nd logical DU’s target cell for UE handover. - The trigger mechanism for the 1st logical DU’s donor to initiate UE handover to the 2nd logical DU’s target cell. - The trigger mechanism for the removal of the 1st logical DU’s F1 connection. - BH transport in presence of two concurrent logical IAB-DUs - In RAN2, the issue has been raised if and how BAP can support F1 transport to two logical IAB-DU’s on the IAB-node at the same time, or if any enhancements to BAP and BH configurations are needed. - RAN3 should discuss this matter and conclude if any enhancements are needed from RAN3 perspective. - Unavailability of Xn and/or inter-donor IP connectivity: - Open issues to be addressed: - Should unavailability of Xn be handled separately from unavailability of inter-donor IP connectivity (e.g., Xn may not be available even if inter-donor IP connectivity is available)? - Which aspects of partial migration and DU migration, can be supported if Xn is not available vs. if there is no inter-donor IP connectivity? - What enhancements would be needed to handle these scenarios? AI 13.3: Enhancements for the mobility of an IAB-node together with its served UEs, including aspects related to group mobility. - Configuration of 2nd logical IAB-DU’s NCGI and TAC - These configurations can be based on F1 signaling from the mIAB-DU’s donor or based on pre-configuration/OAM-configuration on the IAB-DU. - Please discuss the benefits/shortcomings for either configuration approach. - As discussed in the last RAN3 meeting, we had a similar issue with the IAB-node’s IP address configuration in Rel-16. We should aim for consistent behaviour. Please include in the discussion if/how the same/similar approach can be taken for the NCGI/TAC issue, or why this is might not be possible. UE handover to target mobile IAB-node: - Discuss whether the source CU of a UE should know that the target cell considered for UE handover belongs to a mobile IAB-node. - Configuration optimizations: - Open issues: whether and which information can be shared between the logical DUs. In particular: How does the target DU’s donor know about the target DU’s configuration which the target DU has copied from the source DU? This issue is instrumental to make progress on this item. AI 13.4: Mitigation of interference due to IAB-node mobility, including the avoidance of potential reference and control signal collisions (e.g. PCI, RACH) - PCI collision avoidance: - RAN3 agreed: PCI-change on the IAB-node can be supported via handover of connected UEs between cells using old and new PCI, respectively. - This agreement implies that both PCIs are simultaneously supported on the IAB node. We need to discuss the procedure. - RAN3 agreed: PCI collision can be detected by the F1-terminating IAB-donor of the mobile IAB-node. The chairman notes further contain: - FFS for the PCI reconfiguration in case of IAB-donor and IAB-node with different OAMs. - Using separate OAMs for IAB-donor and IAB-node should be considered the baseline. We need to discuss the issues in this case, and potential solutions. |
| RAN4RF | #106 | Feb 2023 | 0.25 | Discuss work plan Initial discussion on co-existence scenarios and RF core requirements for mobile IABs |
| RAN4RD | #106 | Feb 2023 | 0.25 | Discuss work plan Initial discussion on RRM core requirements for mobile IABs |
| RAN | #99 | March 2023 |  |  |
| RAN2 | #121bis | April 2023 | 0.5 | Continue discussion |
| RAN3 | #119bis | April 2023 | 1.5 | Continue discussion |
| RAN4RF | #106bis | April 2023 | 0.5 | Continue discussion |
| RAN4RD | #106bis | April 2023 | 0.5 | Continue discussion |
| RAN2 | #122 | May 2023 | 0.5 | Continue discussion |
| RAN3 | #120 | May 2023 | 1.5 | Continue discussion |
| RAN4RF | #107 | May 2023 | 0.5 | Continue discussion |
| RAN4RD | #107 | May 2023 | 0.5 | Continue discussion |
| RAN | #100 | June 2023 |  |  |
| RAN2 | #123 | Aug 2023 | 0.5 | Continue discussion |
| RAN3 | #121 | Aug 2023 | 1.0 | Continue discussion |
| RAN4RF | #108 | Aug 2023 | 0.5 | Continue discussion |
| RAN4RD | #108 | Aug 2023 | 0.5 | Continue discussion |
| RAN | #101 | Sept 2023 |  |  |
| RAN2 | #123bis | Oct 2023 | 0.5 | Finalize St2 discussion |
| RAN3 | #121bis | Oct 2023 | 1.5 | Finalize St2 discussion |
| RAN4RF | #108bis | Oct 2023 | 0.5 | Continue discussion |
| RAN4RD | #108bis | Oct 2023 | 0.5 | Continue discussion |
| RAN2 | #124 | Nov 2023 | 0.5 | Finalize St3 discussion |
| RAN3 | #122 | Nov 2023 | 1.5 | Finalize St3 discussion |
| RAN4RF | #109 | Nov 2023 | 0.5+0.25 | Finalize discussion on Core Part. Start discussion on Performance part. |
| RAN4RD | #109 | Nov 2023 | 0.5+0.25 | Finalize discussion on Core Part. Start discussion on Performance part. |
| RAN | #102 | Dec 2023 |  | Functional freeze |

# References

- RP-222671: Revised WID for NR_mobile_IAB; TSG RAN Meeting #97e, electronic meeting, Sept. 12 - 16, 2022

- RP-221060: Draft Status of TU RAN1 to 4 after RAN#96 v01, Budapest, Hungary, June 6 - 9, 2022