3GPP TSG-RAN WG3 Meeting #123bis	R3-242002

Changsha, China, 15 – 19 April 2024

Agenda item:	21.1

Source:	Nokia, Qualcomm (Rapporteurs)

Title:	Work Plan for Rel-19 on XR Enhancements for NR

WID/SID:	NR_XR_Ph3-Core - Release 19

Document for:	Discussion and Decision

# 1	Introduction

The Rel-19 XR Phase 3 objectives are as follows [RP-240791]:

- Study and if justified, specify aspects related to multi-modality (intra-UE) (with coordination with SA2/SA4 as needed by LS request). Aim to facilitate efficient and effective support for XR application with Multiple QoS flows with multi-modal inter-dependencies, meeting multi-modal QoS requirements, e.g. synchronization and/or coordination. Efficiency enhancements are expected to be visible in terms of capacity or power consumption. [RAN2]. NOTE: Check in RAN#105 (check also other WG involvement if needed). - Specify enhancements to enable transmission/reception in gaps/restrictions that are caused by RRM measurements (from inter-frequency RRM measurement gaps, or intra-frequency measurements, or other scheduling restrictions etc). [RAN1, RAN2, RAN4] - Specify the corresponding measurement gap and scheduling restriction to enable the identified enhancements with RRM performance impact taken into consideration, work being triggered by LS. [RAN4] - Specify Enhancements for Scheduling, as follows: - For the UL, Study and if justified, Specify enhancements using delay/deadline information, for support of UL scheduling to enable high XR capacity while meeting delay requirements/avoiding too late PDUs. [RAN2]. NOTE: LCP implementation complexity need to be taken into account when evaluating solutions. NOTE: Check in RAN#105 - Specify the following user plane enhancements [RAN2] - RLC re-transmission related enhancements for operation of RLC Acknowledged Mode (AM) with small packet delay budget. - Specify Core requirements related to the above objectives as necessary [RAN4] - Extend Release 18 standalone mechanism to support NR-NR dual connectivity as follows [RAN3] - PDU set based handling - ECN marking - Burst Arrival Time reporting, if needed - PSI Discard coordination, if needed - Note: No RAN2 impact from above items NOTE: Whether / to what extent network exposure / RAN awareness / e.g. RAN involved rate control, possibly additional info for DL scheduling, parallel with SA2 work, shall be covered in this WI is TBD.

Note the Rel-19 SA2 Study on Extended Reality and Media service (XRM) Phase 2 scheduled for completion in June [SP-231671] may trigger additional work in RAN2.

# 2	Plan

A workplan corresponding to the objectives and allocated TUs is suggested the table below.

Table 3: Workplan for the XR WI

| Date | RAN1 | RAN2 | RAN3 | RAN |
| --- | --- | --- | --- | --- |
| 2024-02 | RAN1#116 Start discussion on a design of the enhancement feature(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. |  |  |  |
| 2024-03 |  |  |  | RAN#103 Status Report (target of 2% corresponding to 0.5 TU spent over an initial allocation of 24.8) |
| 2024-04 | RAN1#116bis Continue the discussion on the design of the enhancement feature(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. Start agreeing on solution(s). | RAN2#125bis Endorse workplan Start the work on all 4 objectives except measurement gaps, for which RAN1 conclusions first need to be reached. For multi-modality and scheduling enhancements, start the study phase. | RAN3#123bis Start discussion on RAN3 related objectives on NR-DC, e.g. PDU set based handling, ECN marking, etc. Agree the DC bearer types to be supported. Designate responsible companies for BL Stage-2 & 3 CRs. |  |
| 2024-05 | RAN1#117 Continue developing the solution(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. | RAN2#126 Continue the work on all 3 objectives. | RAN3#124 Finalize the solution on required enhancements. Finalize Stage-2 CR(s) Agree the skeleton of Stage-3 CR(s). |  |
| 2024-06 |  |  |  | RAN#104 Status Report (target of 18% corresponding to 4.5 TUs spent over an initial allocation of 24.8) Take into account outcome of SA2 study if available. |
| 2024-08 | RAN1#118 Continue the work on the details of the agreed solution(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. | RAN2#127 Continue the work on all 3 objectives. For multi-modality and scheduling enhancements, conclude the study phase and convey the outcome to RAN#105. | RAN3#125 Agree Stage-2 CR(s) and Stage-3 CR(s) |  |
| 2024-09 |  |  |  | RAN#105 Status Report (target of 30% corresponding to 7.5 TUs spent over an initial allocation of 24.8) Checkpoints: 1. Multi-modality (RAN2) 2. Scheduling enhancements (RAN2) |
| 2024-10 | RAN1#118bis Continue the work on the details of the agreed solution(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. Check if RAN1 involvement related to objective on multi-modality is needed. | RAN2#127bis Continue the work depending on RAN#105 outcome. |  |  |
| 2024-11 | RAN1#119 Continue the work on the details of the agreed solution(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. | RAN2#128 Narrow down possible solutions. First version of Stage 2 CR |  |  |
| 2024-12 |  |  |  | RAN#106 Status Report (target of 55% corresponding to 13.5 TUs spent over an initial allocation of 24.8) |
| 2025-02 | RAN1#120 Finalize, if not already, the discussion on the design of the enhancement feature(s) to enable transmission/reception in gaps/restrictions that are caused by RRM measurements. Provide RAN1 input to RAN2 on RRC configuration parameters, UE capabilities, and Stage 2 TPs. | RAN2#129 Continue the work on the details of the agreed solutions. Check with RAN1 the progress on measurement gaps and start discussing in RAN2. First versions of Stage 3 CR. |  |  |
| 2025-03 |  |  |  | RAN#107 Status Report (target of 67% corresponding to 16.5 TUs spent over an initial allocation of 24.8) |
| 2025-04 | RAN1#120bis | RAN2#129bis Continue the work on the details of the agreed solutions for all objectives. Reflect new agreements in running Stage 2 & 3 CRs. |  |  |
| 2025-05 | RAN1#121 | RAN2#130 Continue the work on the details of the agreed solutions for all objectives. Reflect new agreements in running Stage 2 & 3 CRs. |  |  |
| 2025-06 |  |  |  | RAN#108 Status Report (target of 91% corresponding to 22.5 TUs spent over an initial allocation of 24.8) |
| 2025-08 |  | RAN2#131 Finalise Stage 2 & 3 CRs Agree Stage 2 & 3 CRs |  |  |
| 2025-09 |  |  |  | RAN#109 Status Report (target of 100% corresponding to 24.8 TUs spent over an initial allocation of 24.8) CRs received for approval. |

# 3	Proposal for BL CR owner

Based on companies’ interest, it is proposed to assign the following BL CR owner for the specs listed in the WID.

It is proposed to capture following in the MCC notes:

|  | BL CR owner |
| --- | --- |
| 38.300 (RAN3 part) | Nokia |
| 37.340 (RAN3 part) | ZTE |
| 38.423 | CATT |
| 38.473 | Huawei |