3GPP TSG RAN WG4 Meeting #109	R4-2320700

Chicago, USA, November 13-17, 2023

Agenda Item:	8.22.2.1

Source: 	Ericsson

Title:	Updated work Split on RRM Core Requirements for Positioning Enhancement

Document for:	Approval

- Introduction

The RRM core requirements for Rel-18 WI on Expanded and improved NR positioning are supposed to be completed in RAN4#109 (November 2023) in accordance with the timeline in the latest approved WID [1].

The work split for the draft CRs for defining the RRM core requirements was approved in [2].

This contribution provides further updates on the work split among companies volunteering for providing draft CRs at the next RAN4 meeting to timely complete the core part of the WI.

# Positioning RRM core requirements and work split

According to the WID objectives and the ongoing work in RAN4 the RRM requirements for the following broad topics are expected to be specified to complete the core WI [1]:

- PRS measurement requirements in RRC idle state

- PRS measurement requirements for RedCap in RRC idle state

- PRS measurement requirements with bandwidth aggregation in RRC inactive state

- PRS measurement requirements for RedCap in RRC inactive state

- PRS measurement requirements for RedCap in RRC connected state

- PRS measurement requirements with bandwidth aggregation in RRC connected state

- Carrier phase positioning measurement requirements in RRC inactive state

- Carrier phase positioning measurement requirements in RRC connected state

- SL positioning measurement requirements

Table 1 provides list of individual draft CRs. The main addition is the introduction of the TA validation requirements for positioning measurements using SRS transmission in RRC inactive state. The clause number for draft CR # 17 is also updated based on the MCC feedback. The updated Big CR template/skeleton is also provided in [3].

Table 1: Work split on major topics and corresponding RRM core requirements for positioning measurements.

| DraftCR No. | Requirements for feature | Detail of requirements | New or impacted section in TS 38.133 | Volunteer Company |
| --- | --- | --- | --- | --- |
| 1 | All | Draft Big CR for RRM Core Requirements for Positioning Enhancement | All relevant sections in TS 38.133 | Ericsson (Rapporteur) |
| 2 | PRS measurement requirements in RRC idle state | General aspects: introduction | 4.x1.1 | Qualcomm |
|  |  | RSTD measurement requirements | 4.x1.3 |  |
| 2A |  | Cell re-selection for positioning | 4.x1.2 | Huawei |
| 3 |  | PRS-RSRP measurement requirements | 4.x1.4 | OPPO |
|  |  | PRS-RSRPP measurement requirements | 4.x1.5 |  |
| 4 | PRS measurement requirements for RedCap in RRC idle state | General aspects: introduction | 4.x1A.1 | Xiaomi |
|  |  | RSTD measurement requirements | 4.x1A.3 |  |
| 4A |  | Cell re-selection for positioning | 4.x1A.2 | Huawei |
| 5 |  | PRS-RSRP measurement requirements | 4.x1A.4 | CATT |
|  |  | PRS-RSRPP measurement requirements | 4.x1A.5 |  |
| 6 | PRS measurement requirements in RRC inactive state (LPHAP related updates) | General aspects: introduction (including general aspects of PRS measurements with bandwidth aggregation and CPP) | 5.6.1 (existing section) | Ericsson |
| 7 |  | Cell re-selection for positioning | 5.6.1A | Huawei |
| 7A |  | TA validation requirements for positioning measurements | 5.6.1B | Ercisson |
| 8 |  | RSTD measurement requirements | 5.6.2 (existing section) | CMCC |
|  |  | PRS-RSRP measurement requirements | 5.6.3 (existing section) |  |
| 9 |  | UE Rx-Tx time difference measurement requirements | 5.6.4 (existing section) | CATT |
|  |  | PRS-RSRPP measurement requirements | 5.6.5 (existing section) |  |
| 10 | PRS measurement requirements with bandwidth aggregation in RRC inactive state | RSTD measurement requirements | 5.6.2.x1 | Huawei |
|  |  | UE Rx-Tx time difference measurement requirements | 5.6.4.x1 |  |
| 11 | CPP: DL RSCP and DL RSCPD in RRC inactive state | Measurement requirements for DL RSCPD reported with RSTD | 5.6.x1 | Nokia |
| 12 |  | Measurement requirements for DL RSCP reported with UE Rx-Tx time difference | 5.6.x2 | Nokia |
| 13 | PRS measurement requirements for RedCap in RRC inactive state | General aspects: introduction | 5.6A.1 | Xiaomi |
| 14 |  | Cell re-selection for positioning | 5.6A.2 | Huawei |
| 14A |  | TA validation requirements for positioning measurements | 5.6A.3 | Ericsson |
| 15 |  | RSTD measurement requirements | 5.6A.4 | Ericsson |
|  |  | PRS-RSRP measurement requirements | 5.6A.5 |  |
| 16 |  | UE Rx-Tx time difference measurement requirements | 5.6A.6 | Xiaomi |
|  |  | PRS-RSRPP measurement requirements | 5.6A.7 |  |
| 17 | UE autonomous timing adjustment at cell reselection in RRC inactive | UE transmit timing for positioning measurements | 7.1E | LG |
| 18 | PRS measurement requirements with bandwidth aggregation in RRC connected state | General aspects: introduction (include also general aspects of CPP) | 9.9.1 (existing section) | ZTE |
| 19 |  | RSTD measurement requirements | 9.9.2.x1 | Ericsson |
|  |  | UE Rx-Tx time difference measurement requirements | 9.9.4.x1 |  |
| 20 | PRS measurement requirements for RedCap in RRC connected state | General aspects: introduction | 9.9A.1 | ZTE |
| 21 |  | RSTD measurement requirements | 9.9A.2 | Mediatek |
|  |  | PRS-RSRP measurement requirements | 9.9A.3 |  |
| 22 |  | UE Rx-Tx time difference measurement requirements | 9.9A.4 | Huawei |
|  |  | PRS-RSRPP measurement requirements | 9.9A.5 |  |
| 23 | CPP: DL RSCP and DL RSCPD in RRC connected state | Measurement requirements for DL RSCPD reported with RSTD | 9.9.x1 | Ericsson |
| 24 |  | Measurement requirements for DL RSCP reported with UE Rx-Tx time difference | 9.9.x2 | Nokia |
| 25 | NR sidelink positioning measurements | General aspects: introduction | 12A.1 | Ericsson |
| 26 |  | SL-RSTD measurement requirements | 12A.2 | Ericsson |
|  |  | SL-RSRP measurement requirements | 12A.3 |  |
| 27 |  | SL-Rx-Tx time difference measurement requirements | 12A.4 | CATT |
|  |  | SL-RSRPP measurement requirements | 12A.5 |  |
| 28 |  | SL-AoA measurement requirements | 12A.6 | Vivo |
|  |  | SL-RTOA measurement requirements | 12A.7 |  |
| NOTE: Company providing draft CR to include the draftCR No. in the draft CR title e.g. Draft CR # X: Title |  |  |  |  |

# Timeplan

- RAN4#108bis:

  - Endorsement of Big draft CR on structure and template.

  - Work split of draft CRs between companies.

- RAN4#109:

  - Companies provide draft CRs.

  - Endorsement of draft CRs.

  - Agreement of Big CR.

# References

- RP-232670, Revised WID on Expanded and Improved NR Positioning, Intel Corporation, CATT, MediaTek, RAN#101.

- R4-2317388, Work Split on RRM Core Requirements for Positioning Enhancement, Ericsson.

- R4-2320701, Updated Draft Big CR Skeleton for RRM Core Requirements for Positioning Enhancement, Ericsson.