3GPP TSG-WG RAN4 Meeting #114bis	R4- 2504070

# Wuhan, Hubei, China, 07th – 11th April, 2025

Source: 	Astrum Mobile, Qualcomm Incorporated

Title: 	Work plan for WI： New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite

Agenda item:	7.9.1

Document for:	Information

1. Introduction

In RAN#107, the new WID for new LTE band for 5G Broadcast for region 3 Utilizing Geosynchronous satellite was approved in [1] with the following objectives:

- Specify a new SDO band for LTE-based 5G Broadcast operating in 1467 to 1492 MHz in Region 3 for GSO: - Specify related UE RF core requirements for 10MHz PMCH - UE requirements specified in TS 36.101 for LTE-based 5G Broadcast shall be considered as baseline (reuse assumption of 10 MHz UE Rx filter) - Specify related SAN RF core requirements for 10 MHz PMCH considering also applicable regulatory requirements: - Take existing SAN RF requirements specified in TS 38.108 for 10MHz as baseline - Requirements based on Resolution 761 in WRC-19 - Only consider QPSK and 16QAM modulation Note: UE only needs to support 5G broadcast for this band Note: Release independence applicability will be further discussed

In this contribution, a work plan for WID on new LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite is proposed for RAN 4.

2. Work Plan

The Work Plan for RAN4 is provided in Table 1:

Table 1: RAN4 Work Plan

| Quarter | Meeting # | TU | Work plan |
| --- | --- | --- | --- |
| RAN#107 (Mar. 2025) | RAN4#114bis | 0.25 | - Work Plan submission for Information - Discussion on band definition and system parameters - Discussion on UE RF requirements - Discussion on SAN RF requirements |
|  | RAN4#115 | 0.25 | - Discuss draft Core part CRs on TS36.102 - Discuss draft Core part CRs on TS36.108 |
| RAN#108 (Jun. 2025) | RAN4#116 | 0.25+0.25 | - Agree on Core part CRs - Finish CRs for Core part - Discussion on Pref part requirements on TS36.102 - Discussion on Perf part requirements on TS36.108 |
| RAN#109 (Sep. 2025) | RAN4#116bis | 0.25 | - Discuss draft Perf part CRs on TS36.102 - Discuss draft Perf part CRs on TS36.108 |
|  | RAN4#117 | 0.25 | - Agree on Perf part CRs |
| RAN#110 (Dec. 2025) | RAN4#118 | 0.25 | - Finish CRs for Perf part |
| RAN#111 (Mar. 2026) |  |  | - Finish WI |

3. References

- RP-250788, “New WID: New band for 5G Broadcast Utilizing Geosynchronous Satellite”, Astrum Mobile,    Qualcomm, RAN#107, March, 2025