## cover
3GPP RAN4 #78bis San Jose del Cabo, Mexico, April 11-16, 2016
Tdoc number: | R4-161825
Agenda item: | 7.15.1
Source: | Intel Corporation
Title: | MIMO OTA work plan
Document for: | Approval

## work plan
Timeline | Performance Tasks | Harmonization Tasks
RAN #71, Mar '16 | Initiate the work item
RAN4 #78bis, Apr '16 | Approve the work plan
| Define test case parameters | Define harmonization test plan and analysis (include Open Items #2, 4, 5, 6, 7, 8)
| Define the FoM (include Open Item #1) | Select single lab with controllable environment (it is understood that the effort to find the lab is initiated prior to the meeting)
| Exchange views on general approach to selecting bands and device types for performance work | RC+CE: define harmonization work plan (include further optimization plan and Open Item #3)
| Define lab alignment procedure | RTS: define harmonization work plan (include further optimization plan)
Study DUT size constraints, test volume size, and chamber size constraints for MPAC, RTS, and RC+CE
Select bands and device types for performance activity (Performance Set 1 or PS1)
Inform CTIA on progress of test case parameters and harmonization work plan
RAN4 #79, May '16 | Finalize test case parameters | Finalize harmonization test plan and analysis (include Open Items #2, 4, 5, 6, 7, 8)
| Finalize the FoM | Finalize harmonization work plan for RC+CE
| Review initial lab alignment results from companies participating in performance work | Finalize harmonization work plan for RTS
| Define performance requirement framework (bands and device selection, result collection, analysis, requirement derivation, tolerance derivation) | Identify devices to be used for harmonization activity with PS1 bands (Harmonization Set 1 or HS1)
Finalize DUT size constraints, test volume size, and chamber size constraints for MPAC, RTS, and RC+CE
| Agree CR to 37.977 on performance requirement framework | Agree CR to 37.977 on harmonization test plan, analysis, RC+CE work plan, and RTS work plan
Agree TP to 37.144 on skeleton structure and test case parameters
Inform COST and CTIA on progress of harmonization and methodology optimization work
Summer break | It is understood that companies participating in performance work will utilize this time to perform measurements | It is understood that this time will be utilized to perform harmonization testing
RAN #72, Jun '16
RAN4 #80, Aug '16 | Review lab alignment results from companies participating in performance work (continued) | Initial HS1 harmonization results and analysis are submitted
| Interested companies report PS1 results into requirement framework | RC+CE: conclude further optimization and Open Item #3 activities
| Select next set of bands and device types (PS2) | RTS: conclude further optimization activity
| Select remaining bands and device types (PS3) | Identify devices to be used for harmonization activity with PS2 bands (HS2)
Determine if a Jan '17 adhoc is needed
RAN #73, Sep '16 | If Jan '17 adhoc is needed, gain RAN approval
RAN4 #80bis, Oct '16 | Interested companies report PS1 and PS2 results into requirement framework | HS1 and initial HS2 harmonization results and analysis are submitted
| Derive requirement proposal for PS1 from framework (for further check by companies) | Determine harmonization outcome for HS1
Identify devices to be used for harmonization activity with PS3 bands (HS3)
Inform RAN5, GCF, CTIA, and CCSA on progress of performance and harmonization work
RAN4 #81, Nov '16 | Interested companies report PS2 and PS3 results into requirement framework | HS2 and initial HS3 harmonization results and analysis are submitted
| Derive requirement proposal for PS2 from framework (for further check by companies) | Determine harmonization outcome for HS2
Agree requirements, tolerance, and MU package for PS1
RAN #74, Dec '16
[pot. adhoc, Jan '17] | TBD
RAN4 #82, Feb '17 | Interested companies report PS3 results into requirement framework | HS3 harmonization results and analysis are submitted
| Derive requirement proposal for PS3 from framework (it is understood that companies are prepared to check proposal during the meeting) | Determine harmonization outcome for HS3
| Agree requirements, tolerance, and MU package for PS2 and PS3 | Finalize harmonization outcome for the WI
Agree CRs for 37.144 and 37.977
Inform RAN5, GCF, CTIA, and CCSA on outcome of performance and harmonization work
RAN #75, Mar '17 | Finalize the work item (CR package for 37.144 & 37.977 for approval)

## bands and device types
Bands | DL Freq (MHz) | Device types
1 | 2140 | Handset (40mm < width <= 72mm)
2 | 1960 | LME
3 | 1842.5 | LEE notebook
4 | 2132.5 | LEE tablet
5 | 881.5
7 | 2655
8 | 942.5
12 | 737.5
13 | 751
19 | 882.5
20 | 806
28 | 780.5
32 | 1474
38 | 2595
39 | 1900
40 | 2350
41 | 2593
42 | 3500
46 | 5537.5