## main
RRM requirements |  |  |  | RAN4 Discussion |  |  | Draft TS36.133 |  | Remarks
|  |  | Requirements | Status | Approved relevant document | CR editor | Status | Approved relevant CR
2 | References | 2 | References | Not yet |  | (if needed) Kunihiko (DOCOMO)
3 | Definitions, symbols and abbreviations | 3 | Definitions, symbols and abbreviations | Not yet |  | Kunihiko (DOCOMO)
4 | E-UTRAN RRC_IDLE state mobility | 4.1 | Cell Selection | On going |  | Santhan (Ericsson)
|  | 4.2 | Cell Re-selection | On going | No requirements for inter RAT reselection are specified(R4-158205)
|  | 4.3 | Minimization of Drive Tests (MDT) | N/A |  |  |  |  | Not supported.
|  | 4.4 | MBSFN Measurements | N/A |  |  |  |  | Not supported
|  | 4.5 | Proximity-based Services | N/A |  |  |  |  | Not supported
5 | E-UTRAN RRC_CONNECTED state mobility | 5.1 | E-UTRAN Handover | N/A |  |  |  |  | Not supported
|  | 5.3 | Handover to other RATs | N/A |  |  |  |  | Not supported
|  | 5.4 | Handover to Non-3GPP RATs | N/A |  |  |  |  | Not supported
6 | RRC Connection Mobility Control | 6.1 | RRC Re-establishment | Not yet |  | Qiming (Huawei)
|  | 6.2 | Random Access | On going
|  | 6.3 | RRC Connection Release with Redirection | N/A |  |  |  |  | Not supported
|  | 6.4 | CSG Proximity Indication for E-UTRAN and UTRAN | N/A |  |  |  |  | Not supported
7 | Timing and signalling characteristics | 7.1 | UE transmit timing | On going |  | Santhan (Ericsson)
|  | 7.2 | UE timer accuracy | On going
|  | 7.3 | Timing Advance | On going
|  | 7.4 | Cell phase synchronization accuracy (TDD) | N/A |  |  |  |  | This requirement is not specific to NB-IoT.
|  | 7.5 | Synchronization Requirements for E-UTRAN to 1xRTT and HRPD Handovers | N/A |  |  |  |  | Not supported
|  | 7.6 | Radio Link Monitoring | On going |  | Amith (Qualcomm)
|  | 7.7 | SCell Activation and Deactivation Delay for E-UTRA Carrier Aggregation | N/A |  |  |  |  | Not supported
|  | 7.8 | Interruptions with Carrier Aggregation | N/A |  |  |  |  | Not supported
|  | 7.9 | Maximum Transmission Timing Difference in Carrier Aggregation | N/A |  |  |  |  | Not supported
|  | 7.10 | Interruptions with RSTD Measurements with Carrier Aggregation | N/A |  |  |  |  | Not supported
|  | 7.11 | Radio Link Monitoring for UE Category 0 | N/A |  |  |  |  | It's not applicable.
|  | 7.12 | Interruptions with Dual Connectivity | N/A |  |  |  |  | Not supported
|  | 7.13 | Cell phase synchronization accuracy (Synchronized mode of dual connectivity) | N/A |  |  |  |  | Not supported
|  | 7.14 | PSCell Addition and Release Delay for E-UTRA Dual Connectivity | N/A |  |  |  |  | Not supported
|  | 7.15 | Maximum Receive Timing Difference in Dual Connectivity | N/A |  |  |  |  | Not supported
|  | 7.16 | Proximity-based Services | N/A |  |  |  |  | Not supported
|  | 7.17 | Maximum Transmission Timing Difference in Dual Connectivity | N/A |  |  |  |  | Not supported
|  | 7.18 | SCell Activation and Deactivation Delay for E-UTRA Dual Connectivity | N/A |  |  |  |  | Not supported
8 | UE Measurements Procedures in RRC_CONNECTED State | 8 | UE Measurements Procedures in RRC_CONNECTED State | On going |  | (if needed) Qiming (Huawei) |  |  | Mobility in Connected mode and measurement report are not supported by NB-IoT. But it is under discussion whether measurement requirement in connected mode for UL TPC and/or RACH is needed or not.
|  | 8.1 | General Measurement Requirements | N/A |  |  |  |  | Not supported
|  | 8.2 | Capabilities for Support of Event Triggering and Reporting Criteria | N/A |  |  |  |  | Not supported
|  | 8.3 | Measurements for E-UTRA carrier aggregation | N/A |  |  |  |  | Not supported
|  | 8.4 | OTDOA RSTD Measurements for E-UTRAN carrier aggregation | N/A |  |  |  |  | Not supported
|  | 8.5 | Measurements for UE category 0 | N/A |  |  |  |  | Not supported
|  | 8.6 | Discovery signal measurements | N/A |  |  |  |  | Not supported
|  | 8.7 | Discovery signal measurements for E-UTRA carrier aggregation | N/A |  |  |  |  | Not supported
|  | 8.8 | Measurements for E-UTRA dual connectivity | N/A |  |  |  |  | Not supported
|  | 8.9 | MBSFN Measurements | N/A |  |  |  |  | Not supported
|  | 8.10 | Proximity-based Services | N/A |  |  |  |  | Not supported
|  | 8.11 | Discovery Signal Measurements under Operation with Frame Structure 3 | N/A |  |  |  |  | Not supported
|  | 8.12 | Discovery Signal Measurements for E-UTRA Carrier Aggregation under Operation with Frame Structure 3 | N/A |  |  |  |  | Not supported
9 | Measurements performance requirements for UE | 9.1.2 | Intra-frequency RSRP Accuracy Requirements | On going |  | Lars (Nokia)
|  | 9.1.3 | Inter-frequency RSRP Accuracy Requirements | On going
|  | 9.1.4 | RSRP Measurement Report Mapping | N/A |  |  |  |  | Not supported
|  | 9.1.5 | Intra-frequency RSRQ Accuracy Requirements | On going
|  | 9.1.6 | Inter-frequency RSRQ Accuracy Requirements | On going
|  | 9.1.7 | RSRQ Measurement Report Mapping | N/A |  |  |  |  | Not supported
|  | 9.1.8 | Power Headroom | Not yet
|  | 9.1.9 | UE Rx – Tx time difference | N/A |  |  |  |  | Not supported
|  | 9.1.10 | Reference Signal Time Difference (RSTD) | N/A |  |  |  |  | Not supported
|  | 9.1.11 | Carrier aggregation measurement accuracy | N/A |  |  |  |  | Not supported
|  | 9.1.12 | Reference Signal Time Difference (RSTD) Measurement Accuracy Requirements for Carrier Aggregation | N/A |  |  |  |  | Not supported
|  | 9.1.13 | Measurement accuracy for UE category 0 | N/A |  |  |  |  | It's not applicable.
|  | 9.1.14 | Accuracy requirements for Discovery Signal Measurements | N/A |  |  |  |  | Not supported
|  | 9.1.15 | Discovery signal measurements accuracy for E-UTRAN carrier aggregation | N/A |  |  |  |  | Not supported
|  | 9.1.16 | Accuracy requirements for RSRQ measurement on all OFDM symbols | Not yet
|  | 9.1.17 | RS-SINR Measurements | N/A |  |  |  |  | Not supported
|  | 9.1.18 | Accuracy Requirements for Measurements under Operation with Frame Structure 3 | N/A |  |  |  |  | Not supported
|  | 9.1.19 | Accuracy Requirements for Carrier Aggregation for Measurements under Operation with Frame Structure 3 | N/A |  |  |  |  | Not supported
|  | 9.1.20 | SFN and Subframe Time Difference (SSTD) | N/A |  |  |  |  | Not supported
|  | 9.2 | UTRAN FDD Measurements | N/A |  |  |  |  | Not supported
|  | 9.3 | UTRAN TDD Measurements | N/A |  |  |  |  | Not supported
|  | 9.4 | GSM Measurements | N/A |  |  |  |  | Not supported
|  | 9.5 | CDMA2000 1x RTT Measurements | N/A |  |  |  |  | Not supported
|  | 9.6 | PCMAX,c | N/A |  |  |  |  | Not supported
|  | 9.7 | IEEE802.11 Measurements | N/A |  |  |  |  | Not supported
|  | 9.8 | MBSFN Measurements | N/A |  |  |  |  | Not supported
10 | Measurements Performance Requirements for E-UTRAN | 10 | Measurements Performance Requirements for E-UTRAN | N/A |  |  |  |  | This requirement is not specific to NB-IoT.
11 | ProSe Requirements in Any Cell Selection state | 11 | ProSe Requirements in Any Cell Selection state | N/A |  |  |  |  | Not supported
Annex A | Test Cases | Annex A | Test Cases | N/A |  |  |  |  | test requirement
Annex B | Conditions for RRM requirements applicability for operating bands | Annex B | Conditions for RRM requirements applicability for operating bands | Not yet |  | Kunihiko (DOCOMO)