3GPP TSG-RAN WG4 Meeting RAN4#87                                                 R4-1808029

Busan,Korean, 21 -25 May, 2018

Agenda Item:   7.12.1

Source:        Samsung

Title:          Work plan for UE performance requirements (38.101-4)

Document for:  Discussion

Introduction

A dedicated specification was assigned for NR UE performance requirements as 38.101-4. The target competition time for Rel-15 NR performance part is RAN#82 in Dec 2018. In this contribution, preliminary plan for UE performance requirements was provided.

Discussion

In last RAN plenary, such TUs were assigned for Rel-15 NR WI in latest Status report. Overall we can observe that there are 5 regular RAN4 meetings plus one performance AH reserved for completing Rel-15 NR performance part in Dec 2018, and very limited TUs assigned for performance parts in April and May meetings.

In order to meet such aggressive timeline and organize RAN4 work efficiency, introducing performance test cases under a phase approach manner was proposed in [1]. In last RAN4 meeting, a generic test scope for CSI and demodulation requirements was agreed in [2], followed the agreements, we can divide test cases with two different priorities.

Generally, work plan can be divided into three phases as show in figure below:

Phase 0: Overall test scope, generic common test set-up and channel modelling, specification skeleton

Phase 1: Completion 1st bullet of test cases (RAN4 July Ad-hoc, RAN4#88)

- Demod:

  - PDSCH: Normal test cases with single carrier

  - PDCCH

- CSI: CQI (static), PMI, RItest cases

Phase 2: Completion 2nd bullet of test cases (RAN4#88bis, RAN4#89)

- Demod:

  - PDSCH: SDR test, CA/DC/SUL test cases if any

  - PBCH if any

- CSI: CQI (fading), L1-RSRP, CRI test cases if any

Phase 0: Overall test scope, generic common test set-up and channel modelling, specification skeleton

RAN4#86bis April 16-20

- Identify overall performance scope of Rel-15 NR UE performance requirements in general

- List all the candidate skeleton structures for TS38.101-4 drafting

RAN4#87 May 21-15

- Agree skeleton structure for TS38.101-4 and drafting rules

- Agree generic simulation assumption, and list of candidate test cases for demodulation test cases and CSI test cases

RAN#80

Phase 1: Completion 1st bullet of test cases

RAN4 Performance-AH Jul 2-6

- Bring preliminary simulation results for 1st bullet of simulation cases

- Further decide test scope for remaining open issues, updated framework for UE performance requirements (demodulation and CSI)

RAN4#88 Aug 20-24

- Further collection results and fixed test set-up for 1st bullet of simulation cases

- Discussion simulation assumption for 2nd bullet of simulation cases

- Draft pCRs for corresponding agreed test cases

RAN#81

Phase 2: Completion 2nd bullet of test cases

RAN4#88bis Oct 8-12

- Collection IM results for 1st bullet of simulation cases;

- Draft pCRs for remaining agreed test cases

RAN4#89 Nov 12-16

- Collection IM results for 2nd bullet of simulation cases

- Draft pCRs to update requirements for the introduced test cases

- Big CR provided for email approval and submission to RAN plenary

RAN#82

Conclusion

In this contribution, preliminary plan for introducing NR UE performance requirements was provided.

Reference

[1]R4-1804647, Phased approach for NR UE demodulation and CSI requirements, Ericsson

[2]R4-1805549, Way forward on UE demodulation requirements, Inte