3GPP TSG-RAN WG4 Meeting #98-e	R4-2103880

Online meeting Jan 25 –  Feb 5, 2021

Title:	Work plan for RF Repeaters

Source:	Qualcomm Incorporated

Agenda item:	11.11.1

Release:	Rel-17

Work Item:	NR_Repeaters-Core

Responsible WG:	RAN4

Document for:	Approval

# 1.	Introduction

RAN#90e approved a new “New WID on NR Repeaters” [1] with RAN4 as the responsible WG.  RAN4 was tasked with the following objectives and guidance:

Normative work phase objective [RAN4]

- Specify RF and EMC requirements for NR repeaters

- Consider FR1 (FDD and TDD) and FR2 (TDD) bands

For the above objective, the leveraging of RF specifications for LTE repeater and IAB should be sought.

It is assumed that the repeater does not perform adaptive beamforming towards the UE.

It is assumed that the TDD repeater meets both BS and UE emission requirements (or the more stringent absolute level in dBm) in all slots.

The following constraint may be considered for TDD repeaters, as needed, to contain the workload associated with this project:

- TX EIRP/TRP/power of Repeater not exceeding any UE power class defined in the band

Note: FR1 FDD repeaters testing is assumed to be conducted. This assumption can be revisited in RAN#91.

This paper discusses the objectives and their details and proposes a work plan to enable conclusion of repeater TSs WID by RAN#95 (December 2021)

## 2	Work plan

The proposed work plan is outlined below. A new TU spreadsheet will be provided as part of a modified WID to reflect the timeline, removal of RRM, and addition of conformance

RAN4#98-e (This meeting)

Agreement on work plan targeting RAN4 RF conclusion by RAN#95

Discussion of parameters to be specified

Discussion on bands to be included

Discussion on regulatory limits

Discussion on which TS document(s) are needed

Discussion on EMC

RAN4#98-bis-e

Discussion on parameters to be specified

Agreement on bands to be included

Discussion on regulatory limits

Agreement on skeleton TSdocument(s)

RAN4#99

RF core CRs into draft TSs

RF core CRs for regulatory limits

Draft TS provided to RAN#93 for information

RAN4#100

Discussion on conformance testing and skeleton TS

Normative RF core values CR into draft TS

RAN4#100 bis

Discussion on conformance testing

Normative RF core values CR into draft TS RAN4#101

Draft CRs into conformance TS

Normative RF core values CR into draft TS TSs to be provided in RAN#94 for approval

RAN4#102

Conclusion on conformance testing

Conclusion on RF core requirements

References:

[1]	RP-202927, “New WID on NR Repeaters”, Qualcomm Incorporated, 3GPP TSG RAN Meeting #90e Electronic meeting, December 7 – 11, 2020