## R5#51
3GPP TSG RAN WG5 (RAN5) Meeting #51 |  |  |  |  | R5-112067
Barcelona, Spain
09 - 13 May 11
Post RAN5#51 Work/Study Item Progress Review
Source: RAN5 Chair
To: RAN5
Purpose: For Endorsement
Work/Study Item | Rapporteur | Tdoc# | Pre -mtg |  | Post-mtg |  | change
|  |  | TCD | % | TCD | % | TCD
Enhanced Dual-layer transmission for LTE TDD | CMCC | R5-112032 | 2011-06-01 | 70 |  | 100
The E850 Upper Band | Sprint | R5-112034 | 2011-06-01 | 0 | 2011-12-01 | 5 | 6
AGNSS test case development for UMTS | Thales | R5-112036 | 2011-06-01 | 85 | 2011-09-01 | 95 | 3
Fixed Wireless CPE | Verizon | R5-112038 | 2011-06-01 | 0 |  | 0
Combination of DC-HSDPA with MIMO | Ericsson | R5-112040 | 2011-06-01 | 80 |  | 100
UMTS 3500 | Ericsson | R5-112042 | 2011-09-01 | 5 | 2011-12-01 | 5 | 3
LTE 3500 | Ericsson | R5-112044 | 2011-09-01 | 30 | 2011-12-01 | 45 | 3
LTE Positioning (Rel 9) | Qualcomm | R5-112046 | 2011-09-01 | 50 | 2011-12-01 | 60 | 3
Home eNB enhancements | Qualcomm | R5-112048 | 2011-09-01 | 20 |  | 70
Support of different bands for Dual-Cell HSDPA | Ericsson | R5-112050 | 2011-09-01 | 0 |  | 50
L-Band (Band 24) LTE for ATC of MSS in NA | Lightsquared | R5-112052 | 2011-09-01 | 0 |  | 80
CT1 aspects of IMS Emergency Calls over GPRS & EPS | Samsung | R5-112054 | 2011-12-01 | 50 |  | 65
Multiple Band & Multiple Freq operation for LCR TDD | CATR | R5-112056 | 2011-12-01 | 40 |  | 80
Home NB enhancements for FDD | Huawei | R5-112058 | 2011-12-01 | 50 |  | 70
MBMS in LTE | Huawei | R5-112060 | 2011-12-01 | 5 |  | 50
Dual-Cell HSUPA | Ericsson | R5-112062 | 2011-12-01 | 0 |  | 5
MIMO Operation with non-MIMO Co-existence in HSDPA | Qualcomm | R5-112064 | 2012-03-01 | 0 |  | 5
SI: UE Application Layer Data Throughput Performance | Spirent | R5-112066 | 2012-03-01 | 5 |  | 60