## R5#59
3GPP TSG RAN WG5 (RAN5) Meeting #59 | [9 empty] | R5-131062
Fukuoka, Japan
20 - 24 May 13
Post Meeting Active Work Item (WI) Progress and Target Completion Date (TCD) Review draft v1
Source: RAN5 Chair
To: RAN5
Purpose: For Endorsement
UIC | WI Name | Rel | Tdoc# | Pre TCD | pre % | post % | post TCD | change (mths) | Rapporteur | other comments
420013 | LTE 3500 | 10 | R5-131030 | 2013-06-01 | 91% |  |  |  | Ericsson
540006 | Four Carrier HSDPA | 10 | R5-131032 | 2013-06-01 | 90% |  |  |  | Qualcomm
550001 | Enhanced ICIC for non-CA based deployments of heterogeneous networks for LTE | 10 | R5-131034 | 2013-06-01 | 35% |  |  |  | Qualcomm
560012 | Enhanced Downlink Multiple Antenna Transmission for LTE | 10 | R5-131036 | 2013-06-01 | 90% |  |  |  | ZTE
570004 | Network Improvements for Machine-Type Communications | 10 | R5-131038 | 2013-06-01 | 80% |  |  |  | Ericsson
520011 | UE Over The Air (Antenna) - Laptop mounted eqpt Free Space test | 11 | R5-131040 | 2013-12-01 | 94% |  |  |  | ZTE
560011 | LTE for 700 MHz Digital Dividend | 11 | R5-131042 | 2013-06-01 | 80% |  |  |  | Ericsson
570006 | Carrier Aggregation of Intra-band contiguous and Inter-band configurations | 11 | R5-131044 | 2013-09-01 | 15% |  |  |  | Nokia
590001 | Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN - UE Conformance tests | 11 | R5-131046 | 2013-12-01 | 0% |  |  |  | DOCOMO
590002 | Service continuity improvements for MBMS for LTE | 11 | R5-131048 | 2013-09-01 | 0% |  |  |  | Ericsson
590003 | LTE RAN Enhancements for Diverse Data Applications | 11 | R5-131050 | 2013-09-01 | 0% |  |  |  | Research in Motion
590004 | Coordinated Multi-Point Operation for LTE | 11 | R5-131052 | 2013-12-01 | 0% |  |  |  | Samsung
590005 | Enhanced downlink control channel(s) for LTE | 11 | R5-131054 | 2014-03-01 | 0% |  |  |  | Huawei
590006 | Public Safety Broadband High Power UE for Band 14 for Region 2 | 11 | R5-131056 | 2013-12-01 | 0% |  |  |  | Motorola Solutions
590007 | Additional special subframe configuration for LTE TDD | 11 | R5-131058 | 2013-09-01 | 0% |  |  |  | Huawei
590008 | Uplink Transmit Diversity (ULTD) for HSPA Qualcomm Incorporated | 11 | R5-131060 | 2014-06-01 | 0% |  |  |  | Qualcomm