## CA 3DL WI conf status RAN5#65
[8 empty] | TS 36.508 |  |  | TS 36.521-1 |  |  |  | TS 36.521-3 |  | TS 36.521-2 | TS 36.523-2
CA Configuration | UID | Core WI Name | WID | RAN4 rapport. | RAN4 Compl | RAN5 company | RAN5 Compl | RF | SIG | Tdoc | Ch. 0-5 Gen | Ch. 6 Tx | Ch. 7 Rx | Tdoc | Ch. 8 - 9 | Tdoc | ICS proforma tables | ICS proforma tables |  | Comments
CA_1A-3A-5A | 620150 620250 | LTE Advanced 3 Band Carrier Aggregation(3DL/1UL) for Band 1, Band 3 and Band 5 | RP-141454 | SK Telecom | 09/2014 RAN#65 | Intel | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_1A-3A-8A | 620124 620224 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8 | RP-141654 | KT | 09/2014 RAN#65 | KT | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_1A-8A |  | Additional BW combination set 2 |  |  |  | Ericsson | 100%
CA_3A-8A |  | Additional BW combination set 2 |  |  |  | Ericsson | 100%
CA_1A-3A-19A | 640128 640128 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19 | RP-141004 | NTT DOCOMO | 09/2014 RAN#65 | NTT Docomo | 0% | 0% | 0% |  | 100% | 0% | 0% | R5-145854 | tbd |  | 0% | 0%
CA_1A-3A-20A | 620151 620251 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20 | RP-141222 | Vodafone | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0% |  | Responsible company needs to be the same as in CA_1A-7A-20A
CA_1A-3A |  | Additional BW combination set or not? (refer to comments) |  |  |  | as above | 0% | [12 empty] | From the core WID it is unclear if there is a need to define additional BW combination set for this configuration or is it already covered.
CA_1A-20A | [5 empty] | Keysight | 0%
CA_1A-5A-7A | 620125 620225 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7 | RP-141462 | LG Uplus | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_1A-5A |  | Additional BW combination set |  |  |  | Ericsson | 100%
CA_1A-7A |  | Additional BW combination set |  |  |  | as above | 0%
CA_1A-7A-20A | 620152 620252 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 7 and Band 20 | RP-141223 | Vodafone | 09/2014 RAN#65 | Keysight | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0% |  | Responsible company needs to be the same as in CA_1A-3A-20A
CA_1A-20A |  | Also in CA_1A-3A-20A |  |  |  | Keysight | 0%
CA_1A-19A-21A | 630127 630227 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21 | RP-141193 | NTT DOCOMO | 09/2014 RAN#65 | NTT Docomo | 10% | 0% | 0% |  | 100% | 0% | 0% | R5-145854 | tbd |  | 0% | 0%
CA_1A-42C | 640131 640231 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42 | RP-141006 | NTT DOCOMO | 09/2014 RAN#65 | NTT Docomo | 10% | 0% | 0% |  | 100% | 0% | 0% | R5-145854 | tbd |  | 0% | 0%
CA_1A-42A | [5 empty] | NTT Docomo |  |  |  |  | 100% |  |  | R5-145854
CA_2A-2A-13A | 600138 600238 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13 | RP-141435 | Verizon | 09/2014 RAN#65 | Keysight | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_2A-4A-4A | 630138 630238 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4 | RP-141236 | T-Mobile USA | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_2A-4A-5A | 620126 620226 | TE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5 | RP-140186 | U.S. Cellular | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_2A-4A-12A | 620127 620227 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12 | RP-140189 | U.S. Cellular | Incompl. | Intel | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_2A-4A-13A | 600137 600237 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13 | RP-141434 | Verizon | 09/2014 RAN#65 | Intel | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_2A-5A-12A | 620128 620228 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12 | RP-140190 | U.S. Cellular | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_2A-5A-30A | 600131 600231 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30 | RP-131696 | AT&T | 09/2014 RAN#65 | Intertek | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_2A-30A | [5 empty] | Intertek | 0%
CA_5A-30A | [5 empty] | Intertek | 0%
CA_2A-12A-12A | 620129 620229 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 12 | RP-131654 | AT&T | 09/2014 RAN#65 | Keysight | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_12A-12A | [5 empty] | Keysight | 0%
CA_2A-12A-30A | 620130 620236 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30 | RP-141211 | AT&T | 09/2014 RAN#65 | Intel | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_12A-30A | [5 empty] | Intel | 0%
CA_2A-29A-30A | 600133 600233 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30 | RP-141212 | AT&T | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_29A-30A | [5 empty] | as above
CA_3A-7A-20A | 620131 620231 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 20 | RP-141224 | Vodafone | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_3A-7C | 630126 630226 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | RP-141196 | Nokia Networks | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_3A-42C | 640130 640230 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | RP-141005 | NTT DOCOMO | Incompl. | NTT Docomo | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_3A-42A | [5 empty] | NTT Docomo
CA_3C-7A | 630128 630228 | LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7 | RP-141126 | TeliaSonera | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_4A-4A-12A | 630137 630237 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12 | RP-141709 | T-Mobile USA | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_4A-4A-13A | 600139 600239 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 13 | RP-141433 | Verizon | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA-4A-5A-12A | 620133 620233 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12 | RP-140191 | U.S. Cellular | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_4A-5A-30A | 600134 600234 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 30 | RP-141213 | AT&T | 09/2014 RAN#65 | Intertek | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_4A-30A | [5 empty] | Intertek | 0%
CA_4A-12A-12A | 620134 620234 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12 | RP-131655 | AT&T | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_4A-12A-30A | 620135 620235 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30 | RP-141214 | AT&T | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_4A-29A-30A | 600136 600236 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30 | RP-141215 | AT&T | 09/2014 RAN#65 |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_7A-8A-20A | 620153 620253 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20 | RP-132080 | Vodafone | Incompl. |  | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_7A-8A | [5 empty] | as above | 0%
CA_18A-28A | 650110 650210 | LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28 | RP-141611 | KDDI | 09/2014 RAN#65 | KDDI | 100% | 100% | 100% | R5-145718 | 100% | 100% | 100% | R5-145374 R5-145375 R5-145376(email) R5-145377(email) R5-145855 | N/A |  | 100% | 100% | R5-145396 R5-145371 | Will be 100% complete if email agreement agrees the documents.
CA_19A-42C | 640129 640229 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42 | RP-141007 | NTT DOCOMO | 09/2014 RAN#65 | NTT Docomo | 10% | 0% | 0% |  | 100% | 0% | 0% | R5-145854 | tbd |  | 0% | 0%
CA_19A-42A | [5 empty] | NTT Docomo |  |  |  |  | 100% |  |  | R5-145854
CA_40D | 630129 630229 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | RP-140948 | China Mobile | 09/2014 RAN#65 | Intel | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_40D | 640135 640235 | Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | RP-141127 | TeliaSonera | 09/2014 RAN#65 | Intel | 0%
CA_41A-41C CA_41C-41A | 620138 620238 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL | RP-140101 | Sprint, Alcatel-Lucent | 09/2014 RAN#65 | Intel | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%
CA_41A-41A |  | Additional BW combination set 1 |  |  |  | Intel | 0%
CA_41D | 610122 610222 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL | RP-140100 | Alcatel-Lucent | 09/2014 RAN#65 | Intel | 0% | 0% | 0% |  | 0% | 0% | 0% |  | tbd |  | 0% | 0%