## CA 3DL WI conf status RAN5#66
[8 empty] | TS 36.508 |  |  | TS 36.521-1 |  |  |  | TS 36.521-2 | TS 36.523-2
CA Configuration | UID | Core WI Name | WID | RAN4 rapport. | RAN4 Compl | RAN5 company | RAN5 Compl | RF | SIG | Tdoc | Ch. 0-5 Gen | Ch. 6 Tx | Ch. 7 Rx | Tdoc | ICS proforma tables | ICS proforma tables |  | Comments
CA_1A-3A-5A | 620150 620250 | LTE Advanced 3 Band Carrier Aggregation(3DL/1UL) for Band 1, Band 3 and Band 5 | RP-141454 | SK Telecom | 09/2014 RAN#65 | Intel | 75% | 0% | 0% |  | 100% | 100% | 80% | R5-150862 R5-150829 R5-152032 | 100% | 0% | 36.521-2: R5-152029
CA_1A-3A-8A | 620124 620224 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8 | RP-141654 | KT | 09/2014 RAN#65 | KT | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-150862 | 100% | 0% | 36.521-2: R5-152029
CA_1A-8A |  | Additional BW combination set 2 |  |  |  | Ericsson | 100% |  |  | not needed | 100% |  |  | R5-152043 |  |  | not needed
CA_3A-8A |  | Additional BW combination set 2 |  |  |  | Ericsson | 100% |  |  | not needed | 100% |  |  | R5-152043 |  |  | not needed
CA_1A-3A-19A | 640128 640128 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19 | RP-141004 | NTT DOCOMO | 09/2014 RAN#65 | NTT Docomo | 25% | 0% | 0% |  | 100% | 0% | 0% | R5-145854 | 100% | 0% | 36.521-2: R5-152029
CA_1A-3A-20A | 620151 620251 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20 | RP-141222 | Vodafone | 09/2014 RAN#65 |  | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-150862 | 100% | 0% | 36.521-2: R5-152029 | Responsible company needs to be the same as in CA_1A-7A-20A
CA_1A-3A |  | Additional BW combination set or not? (refer to comments) |  |  |  | as above | 25% |  |  |  | 100% |  |  | R5-152043 | 100% |  | 36.521-2: R5-152029 | From the core WID it is unclear if there is a need to define additional BW combination set for this configuration or is it already covered.
CA_1A-20A | [5 empty] | Keysight | 100% | 100% | 100% | 36.508 RF - No CR needed 35.508 SIG- R5-150480 | 100% | 100% | 100% | R5-150522 | 100% | 100% | 36.521-2: R5-150524 36.523-2: R5-150481
CA_1A-3A-26A | 630143 630243 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 26 | RP-140194 | China Telecom | 12/2014 RAN#66 |  | 50% | 0% | 0% |  | 100% | 100% |  | R5-150862 R5-152043 | 100% |  | 36.521-2: R5-152029
CA_1A-5A-7A | 620125 620225 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7 | RP-141462 | LG Uplus | 09/2014 RAN#65 |  | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-150862 R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_1A-5A |  | Additional BW combination set |  |  |  | Ericsson | 100% |  |  | not needed | [6 empty] | not needed
CA_1A-7A |  | Additional BW combination set |  |  |  | as above | 0% |  |  | not needed | [7 empty] | Not in Rel-12 36.101 specification, is this removed from the WID (RAN5#67)??
CA_1A-7A-20A | 620152 620252 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 7 and Band 20 | RP-141223 | Vodafone | 09/2014 RAN#65 | Keysight | 75% | 100% | 0% | 36.508 RF - No CR needed | 100% | 100% | 20% | R5-150522 R5-150861 R5-150862 R5-150863 | 100% | 0% | 36.521-2: R5-150904 | Responsible company needs to be the same as in CA_1A-3A-20A
CA_1A-20A |  | Also in CA_1A-3A-20A |  |  |  | Keysight | 100% | 100% | 100% | 36.508 RF - No CR needed 35.508 SIG- R5-150480 | 100% | 100% | 80% | R5-150522 | 100% | 100% | 36.521-2: R5-150524 36.523-2: R5-150481
CA_1A-18A-28A | 630144 630244 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28 | RP-141610 | KDDI | 12/2014 RAN#66 | KDDI | 75% | 100% | 0% |  | 100% | 100% | 80% | R5-150862 R5-150452 R5-150456 R5-153938 | 100% |  | 36.521-2: R5-152029 | Operation in B28 is to be restricted to 703 – 733 MHz Uplink, and 758 – 788 MHz Downlink for this CA combination
CA_1A-19A-21A | 630127 630227 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21 | RP-141193 | NTT DOCOMO | 09/2014 RAN#65 | NTT Docomo | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-145854 R5-150862 | 100% | 0% | 36.521-2: R5-152029
CA_1A-41C | 640133 640233 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 41 and Band 41 | RP-141789 | KDDI | 12/2014 RAN#66 | KDDI | 25% | 0% | 0% |  | 100% |  |  | R5-150453 R5-150870 | 100% |  | 36.521-2: R5-152029 | UL only on B1
CA_1A-41A | [5 empty] | KDDI | 100% | 100% | 100% | R5-151319r1 | 100% | 100% | 100% | R5-150453 R5-150870 R5-151858 R5-151859 R5-151937 | 100% | 100% | R5-150432 36.521-2: R5-152029
CA_1A-42C | 640131 640231 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42 | RP-141006 | NTT DOCOMO | 09/2014 RAN#65 | NTT Docomo | 25% | 0% | 0% |  | 100% | 0% | 0% | R5-145854 | 100% | 0% | 36.521-2: R5-152029
CA_1A-42A | [5 empty] | NTT Docomo | 25% | 0% | 0% |  | 100% |  |  | R5-145854 | 100% |  | 36.521-2: R5-152029
CA_2A-2A-5A | 630139 630239 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 5 | RP-140165 | Intel | 12/2014 RAN#66 | Intel | 40% | 0% | 0% |  | 100% | 0% | 80% | R5-150829 R5-152032 | 100% |  | 36.521-2: R5-152029
CA_2A-2A-13A | 600138 600238 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13 | RP-141435 | Verizon | 09/2014 RAN#65 | Keysight | 75% | 100% | 0% | 36.508 RF - No CR needed | 100% | 100% | 20% | R5-150827 | 100% | 0% | 36.521-2: R5-150564 | 36.521-1 Section 7: Missing adding minimum conformance requirements for band combination and checking test points (only ΔRIB information added)
CA_2C-29A | 650150 650250 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 29 | RP-141448 | AT&T | 12/2014 RAN#66 |  | 25% | 0% | 0% |  | 100% | 0% |  | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_2C | [6 empty] | 25% | 0% | 0% |  | 100% | 0% |  | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_2A-4A-4A | 630138 630238 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4 | RP-141236 | T-Mobile USA | 09/2014 RAN#65 |  | 75% | 0% | 0% |  | 100% | 100% | 80% | R5-150862 R5-152043 R5-151930 | 100% | 0% | 36.521-2: R5-152029
CA_2A-4A-5A | 620126 620226 | TE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5 | RP-140186 | U.S. Cellular | 09/2014 RAN#65 | Ericsson | 70% | 0% | 0% |  | 100% | 100% | 0% | R5-150862 R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_2A-4A-12A | 620127 620227 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12 | RP-140189 | U.S. Cellular | 09/2014 RAN#65 | Intel | 75% | 0% | 0% |  | 100% | 100% | 80% | R5-150862 R5-152032 R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_2A-4A-13A | 600137 600237 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13 | RP-141434 | Verizon | 09/2014 RAN#65 | Intel | 75% | 0% | 0% |  | 100% | 100% | 80% | R5-150862 R5-152032 R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_2A-4A-29A | 650152 650252 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 29 | RP-141668 | AT&T | 12/2014 RAN#66 | AT4 Wireless | 50% |  |  |  | 100% | 100% | 0% | R5-150862 R5-152043 | 100% |  | 36.521-2: R5-152029
CA_2A-5A-12A | 620128 620228 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12 | RP-140190 | U.S. Cellular | 09/2014 RAN#65 |  | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-150862 R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_2A-5A-13A | 630141 630241 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 13 | RP-140167 | Intel | 12/2014 RAN#66 | Intel | 50% |  |  |  | 100% | 100% | 0% | R5-150862 R5-150829 | 100% |  | 36.521-2: R5-152029
CA_2A-5A-30A | 600131 600231 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30 | RP-131696 | AT&T | 09/2014 RAN#65 | Intertek | 75% | 0% | 0% |  | 100% | 100% | 80% | R5-150862 R5-152043 R5-151930 | 100% | 0% | 36.521-2: R5-152029
CA_2A-30A | [5 empty] | Intertek | 85% |  | 100% | R5-150682 | 100% | 100% | 50% | R5-150816, R5-150817, R5-150112, R5-150818 | 100% | 100% | R5-150830, R5-150685
CA_5A-30A | [5 empty] | Intertek | 85% |  | 100% | R5-150684 | 100% | 100% | 50% | R5-150823, R5-150824, R5-150135, R5-15136 | 100% | 100% | R5-150832, R5-150687
CA_2A-12B | 620129 620229 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 12 | RP-131654 | AT&T | 09/2014 RAN#65 | Keysight | 25% | 100% | 0% | R5-151658 | 100% | 0% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_12B | [5 empty] | Keysight | 25% |  |  |  | 100% |  |  | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_2A-12A-30A | 620130 620236 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30 | RP-141211 | AT&T | 09/2014 RAN#65 | Intel | 25% | 0% | 0% |  | 100% | 100% | 80% | R5-150862 R5-150829 R5-152032 | 100% | 0% | 36.521-2: R5-152029
CA_12A-30A | [5 empty] | Intel | 90% | 100% | 100% | R5-151967 | 100% | 0% | 100% | R5-152032 R5-152043 | 100% |  | 36.521-2: R5-152029
CA_2A-29A-30A | 600133 600233 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30 | RP-141212 | AT&T | 09/2014 RAN#65 | ZTE | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-150862 R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_29A-30A | [5 empty] | ZTE | 25% |  |  |  | 100% |  |  | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_3A-7A-20A | 620131 620231 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 20 | RP-141224 | Vodafone | 09/2014 RAN#65 |  | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-150862 R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_3A-7C | 630126 630226 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7 | RP-141196 | Nokia Networks | 09/2014 RAN#65 |  | 25% | 0% | 0% |  | 100% | 0% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_3A-42C | 640130 640230 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | RP-141005 | NTT DOCOMO | Incompl. | NTT Docomo | 25% | 0% | 0% |  | 100% | 0% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029 | Still incomplete, but kept in Rel-12 with an exception
CA_3A-42A | [5 empty] | NTT Docomo | 25% |  |  |  | 100% |  |  | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_3C-7A | 630128 630228 | LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7 | RP-141126 | TeliaSonera | 09/2014 RAN#65 |  | 25% | 0% | 0% |  | 100% | 0% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_4A-4A-5A | 630140 630240 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 4 and Band 5 | RP-140166 | Intel | 12/2014 RAN#66 | Intel | 75% | 0% | 0% |  | 100% | 100% | 80% | R5-150829 R5-152032 | 100% |  | 36.521-2: R5-152029
CA_4A-4A-7A | 640124 640224 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 4 and Band 7 | RP-140662 | Rogers Wireless | 12/2014 RAN#66 |  | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_4A-4A-12A | 630137 630237 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12 | RP-141709 | T-Mobile USA | 09/2014 RAN#65 |  | 75% | 0% | 0% |  | 100% | 100% | 80% | R5-152043 R5-151930 | 100% | 0% | 36.521-2: R5-152029
CA_4A-4A-13A | 600139 600239 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 13 | RP-141433 | Verizon | 09/2014 RAN#65 | Ericsson | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA-4A-5A-12A | 620133 620233 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12 | RP-140191 | U.S. Cellular | 09/2014 RAN#65 |  | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_4A-5A-13A | 630142 630242 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 13 | RP-140168 | Intel | 12/2014 RAN#66 | Intel | 75% | 0% | 0% |  | 100% | 100% | 80% | R5-150829 R5-152032 | 100% |  | 36.521-2: R5-152029
CA_4A-5A-30A | 600134 600234 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 30 | RP-141213 | AT&T | 09/2014 RAN#65 | Intertek | 75% | 0% | 0% |  | 100% | 100% | 80% | R5-152043 R5-151930 | 100% | 0% | 36.521-2: R5-152029
CA_4A-30A | [5 empty] | Intertek | 85% | 100% | 100% | R5-150683 | 100% | 100% | 80% | R5-150819, R5-150820, R5-150821, R5-150822 | 100% | 100% | R5-150831, R5-150686
CA_4A-7A-12A | 640123 640223 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 7 and Band 12 | RP-140661 | Rogers Wireless | 12/2014 RAN#66 |  | 25% | 0% | 0% |  | 100% | 0% | 0% | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_7A-12A | [6 empty] | 25% |  |  |  | 100% |  |  | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_4A-12B | 620134 620234 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12 | RP-131655 | AT&T | 09/2014 RAN#65 |  | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_4A-12A-30A | 620135 620235 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30 | RP-141214 | AT&T | 09/2014 RAN#65 | Intertek | 25% | 0% | 0% |  | 100% | 100% | 80% | R5-152043 R5-151930 | 100% | 0% | 36.521-2: R5-152029
CA_4A-29A-30A | 600136 600236 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30 | RP-141215 | AT&T | 09/2014 RAN#65 | ZTE | 25% | 0% | 0% |  | 100% | 100% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_7A-8A-20A | 620153 620253 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20 | RP-132080 | Vodafone | 12/2014 RAN#66 |  | 50% | 0% | 0% |  | 100% | 100% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_7A-8A | [5 empty] | as above | 25% |  |  |  | 100% |  |  | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_18A-28A | 650110 650210 | LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28 | RP-141611 | KDDI | 09/2014 RAN#65 | KDDI | 100% | 100% | 100% | R5-145718, R5-150743 | 100% | 100% | 80% | R5-145374 R5-145375 R5-145376(email) R5-145377(email) R5-145855 | 100% | 100% | R5-145396 R5-145371
CA_19A-42C | 640129 640229 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42 | RP-141007 | NTT DOCOMO | 09/2014 RAN#65 | NTT Docomo | 25% | 0% | 0% |  | 100% | 0% | 0% | R5-145854 | 100% | 0% | 36.521-2: R5-152029
CA_19A-42A | [5 empty] | NTT Docomo | 25% |  |  |  | 100% | 0% | 0% | R5-145854 | 100% |  | 36.521-2: R5-152029
CA_25A-41C | 650146 650246 | LTE Advanced inter-band DL Carrier Aggregation (3DL/1UL) in Band 25A and Band 41C | RP-141673 | Alcatel-Lucent, Sprint | 12/2014 RAN#66 |  | 25% |  |  |  | 100% | 0% | 0% | R5-152043 | 100% |  | 36.521-2: R5-152029 | WI title in the WID is also "LTE Advanced inter-band DL Carrier Aggregation in Band 25 and Band 41" and in the 3GPP Work Plan "LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41"
CA_25A-41A | [6 empty] | 25% |  |  |  | 100% | 0% | 0% | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_26A-41C | 640134 640234 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 26, Band 41 and Band 41 | RP-141780 | KDDI | 12/2014 RAN#66 | KDDI | 75% |  |  |  | 100% | 0% | 0% | R5-150455 R5-150871 | 100% |  | 36.521-2: R5-152029
CA_26A-41A | [5 empty] | KDDI | 75% | 100% | 100% | R5-151967 | 100% | 0% | 0% | R5-150455 R5-150871 | 100% |  | 36.521-2: R5-152029
CA_39C_41A | 650148 650248 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 39, Band 39 and Band 41 | RP-141288 | China Mobile | 12/2014 RAN#66 | China Mobile | 25% |  |  |  | 100% | 0% | 0% | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_39A-41C | 640126 640226 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 39, Band 41 and Band 41 | RP-142301 | China Mobile | 12/2014 RAN#66 | China Mobile | 25% |  |  |  | 100% | 0% | 0% | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_40D | 630129 630229 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | RP-140948 | China Mobile | 09/2014 RAN#65 | Intel | 50% | 100% | 0% | R5-150895 | 100% | 0% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029
CA_40D | 640135 650054 | Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL | RP-141127 | TeliaSonera | 09/2014 RAN#65 | Intel | 50% | 100% |  | R5-150895 | 100% |  |  | R5-152043 | 100% |  | 36.521-2: R5-152029
CA_41A-41C CA_41C-41A | 620138 620238 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL | RP-140101 | Sprint, Alcatel-Lucent |  | Intel | 50% | 100% | 0% | R5-150895 | 100% | 0% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029 | Still incomplete, but kept in Rel-12 with an exception
CA_41A-41A |  | Additional BW combination set 1 |  |  |  | Intel | 100% |  |  |  | 100% |  |  | R5-152043 |  |  | 36.521-2: R5-152029
CA_41D | 610122 610222 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL | RP-140100 | Alcatel-Lucent |  | Intel | 50% | 100% | 0% | R5-150895 | 100% | 0% | 0% | R5-152043 | 100% | 0% | 36.521-2: R5-152029 | Still incomplete, but kept in Rel-12 with an exception