## Status
3GPP TSG-RAN WG5 Meeting #74 | [5 empty] | R5-171458
Athens, Greece, 13 - 17 February 2017
Title: | Work plan to update LTE test cases for Band > 64 (AP#73.02)
Source: | Ericsson
Document for: | Information
Introduction
At RAN5#73 the following action point was created:
AP#73.02 | SIG | Update test cases impacted by Extended Band based on analysis performed by TF160 and updates done in TS 36.508. Ericsson to coordinate work allocation. | Qualcomm, Anritsu, Ericsson, Intel, Keysight, R&S, TF160 | R5-168086 | RAN5#74 | Pending
At RAN5#74 29 CRs were agreed to update the majority of the 257 impacted test cases. The activity is planned to be completed at RAN5#75. The remaining test cases concerns Inter-RAT test scenarios.
Status:
Overall completeness | 79.77%
Number of impacted test cases | 257
Number of completed test cases | 205
Remaining test cases to be fixed | 52

## Details Impacted TCs
Work plan: Band > 64 impacted legacy LTE test cases
See work sheet "Actions" for IEs that need to be added for impacted test cases to handle band > 64. |  |  |  | IEs using type definition FreqBandIndicator |  |  |  | IEs using type definition ARFCN-ValueEUTRA
Impacted test cases / areas | Responsible | CR | Status | freqBandIndicator (SystemInformationBlockType1) | multiBandInfoList (SystemInformationBlockType1-v8h0-Ies, InterFreqCarrierFreqInfo-v8h0) | bandEUTRA (SupportedBandEUTRA) | bandEUTRA-r10 (BandParameters-r10) | carrierFreq (FreqPriorityEUTRA, MeasObjectEUTRA) | dl-CarrierFreq (CarrierFreqEUTRA, InterFreqCarrierFreqInfo, MobilityControlInfo) | ul-CarrierFreq (CarrierFreqEUTRA, SystemInformationBlockType2, MobilitControlInfo) | carrierFreq-r9 (MeasResult2EUTRA-r9) | carrierFreq-r10 (RLF-Report-r9, RSTD-InterFreqInfo-r10) | dl-CarrierFreq-r10 (SCellToAddMod-r10, CandidateCellInfo-r10) | ul-CarrierFreq-r10 (RadioResourceConfigCommonSCell-r10) | eutra (RedirectedCarrierInfo) | eutra-r9 (ProximityIndication-r9-IEs) | earfcn (eutra-FrequencyAndPriorityInfoList in UTRA SysInfoType19 ) | Other changes | Comment
Idle mode
Correction to Idle Mode PLMN selection test cases to support Band > 64
6.1.1.3 | Ericsson | R5-171434 | OK |  |  |  |  | OK | OK
6.1.1.3a | Ericsson |  | OK |  |  |  |  | OK | OK | [5 empty] | OK
Correction to Idle Mode Cell selection and reselection test cases to support Band > 64 Part 1
6.1.2.5 | Anritsu | R5-171339, R5-171340 | OK |  |  |  |  | OK | OK
6.1.2.7 | Anritsu |  | OK |  |  |  |  | OK | OK
6.1.2.13 | Anritsu |  | OK |  |  |  |  | OK | OK
6.1.2.15 | Anritsu |  | OK |  |  |  |  | OK | OK
6.1.2.15a | Anritsu |  | OK |  |  |  |  | OK | OK
6.1.2.15b | Anritsu |  | OK |  |  |  |  | OK | OK
6.1.2.16 | Anritsu |  | OK |  |  |  |  | OK | OK
6.1.2.17 | Anritsu |  | OK |  |  |  |  | OK | OK
Correction to Idle Mode Cell selection and reselection test cases to support Band > 64 - Part 2
6.1.2.18 | Ericsson | R5-171110 | OK |  |  |  |  | OK | OK
6.1.2.19 | Ericsson |  | OK | OK | OK | [12 empty] | OK | Already handle Band > 64 in 36.523-1 v13.3.0. Only alignment of conditions needed.
6.1.2.20 | Ericsson |  | OK | OK | OK |  |  | OK | OK | [8 empty] | OK | Already handle Band > 64 in 36.523-1 v13.3.0. Only alignment of conditions needed.
6.1.2.21 | Ericsson |  | OK | OK | OK |  |  | OK | OK | [8 empty] | OK | Already handle Band > 64 in 36.523-1 v13.3.0. Only alignment of conditions needed.
6.1.2.22 | Ericsson |  | OK | OK | OK | [12 empty] | OK | Already handle Band > 64 in 36.523-1 v13.3.0. Only alignment of conditions needed.
6.1.2.23 | Ericsson |  | OK | OK | OK | [7 empty] | OK | OK |  |  |  | OK | ul-CarrierFreq-r10 + alignment of conditions needed.
Correction to Idle Mode Inter-RAT PLMN selection test cases to support Band > 64
6.2.1.3 | TBD |  | To Do | [13 empty] | x |  | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
6.2.3.3 | TBD |  | To Do | [13 empty] | x |  | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
6.2.3.3a | TBD |  | To Do | [13 empty] | x |  | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
6.2.3.4 | TBD |  | To Do | [13 empty] | x |  | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
6.2.3.4a | TBD |  | To Do | [13 empty] | x |  | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
6.2.3.5a | TBD |  | To Do | [13 empty] | x |  | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
6.2.3.13 | TBD |  | To Do | [13 empty] | x |  | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
6.2.3.31 | TBD |  | To Do | [13 empty] | x |  | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
6.2.3.33 | TBD |  | To Do | [13 empty] | x |  | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
6.2.3.34 | TBD |  | To Do |  | x |  |  | x | [10 empty] | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
6.2.3.35 | TBD |  | To Do |  | x | [11 empty] | x |  | TBD- if there is a use case for HO from UTRA to LTE with LTE band > 64.
Correction to Idle Mode Closed Subscriber Group cells test cases to support Band > 64
6.3.3 | - | - | OK | [13 empty] | No Need |  | Assumes there is no use case for HO from UTRA to LTE with LTE band > 64.
6.3.4 | - | - | OK | [13 empty] | No Need |  | Assumes there is no use case for HO from UTRA to LTE with LTE band > 64.
6.4.1 | - | - | OK |  |  |  |  | No Need | No Need | [7 empty] | No Need |  | Assumes there is no use case for HO from UTRA to LTE with LTE band > 64.
MAC
Correction to MAC test cases test cases to support Band > 64
7.1.2.10.1 | Ericsson | R5-171435 | OK | [9 empty] | OK
7.1.2.11.1 | Ericsson |  | OK | [9 empty] | OK
7.1.2.11.4 | Ericsson |  | OK | [9 empty] | OK
7.1.3.11.1 | Ericsson |  | OK | [9 empty] | OK
7.1.3.11.4 | Ericsson |  | OK | [9 empty] | OK
7.1.3.11.5 | Ericsson |  | OK | [9 empty] | OK
7.1.3.16a | - | - | OK | [9 empty] | OK | [5 empty] | No change needed. Already handle Band > 64 in 36.523-1 v13.3.0
RLC & PDCP
No impact |  |  | OK | [15 empty] | No impact
RRC
Correction to RRC connection management procedures test cases to support Band > 64
8.1.3.4 | Ericsson | R5-171439 | OK |  |  |  |  | OK | OK | [5 empty] | OK
8.1.3.5 | Ericsson |  | OK |  |  |  |  | OK | OK
8.1.3.11 | Ericsson |  | OK |  |  |  |  | OK | OK | [5 empty] | OK
8.1.3.11a | Ericsson |  | OK | [11 empty] | OK
8.1.3.12 | Ericsson |  | OK |  |  |  |  | OK | OK
8.1.3.12a | Ericsson |  | OK |  |  |  |  | OK | OK
8.1.3.7 | TBD |  | To Do | [13 empty] | x |  | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
Correction to RRC Radio resource reconfiguration test cases to support Band > 64
8.2.2.3.1 | Keysight | R5-171442 | OK | [9 empty] | OK | OK
8.2.2.4.1 | Keysight |  | OK |  |  |  |  | OK | OK |  |  |  |  | OK
8.2.2.5.1 | Keysight |  | OK | [9 empty] | OK
8.2.2.6.2 | Keysight |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.2.7.1 | Keysight |  | OK | [9 empty] | OK | OK
Correction to RRC Handover test cases to support Band > 64 - Part 1
8.2.4.1 | Rohde & Schwarz | R5-171953 | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.2 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.3 | Rohde & Schwarz |  | OK | [14 empty] | OK | TBD - R&S feedback that the test case is impacted
8.2.4.5 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | OK | [7 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.6 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.7 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.8 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.9 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK
8.2.4.10 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | OK
8.2.4.13 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.13a | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.14 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.14a | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.15 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.15a | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to RRC Handover test cases to support Band > 64 - Part 2
8.2.4.16.1 | Ericsson | R5-171441 | OK | [9 empty] | OK
8.2.4.17.1 | Ericsson |  | OK |  |  |  |  | OK | OK |  |  |  | OK |  |  |  |  | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.18.1 | Ericsson |  | OK | [9 empty] | OK |  |  |  |  | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.19.1 | Ericsson |  | OK |  |  |  |  | OK |  |  |  |  | OK |  |  |  |  | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.20.1 | Ericsson |  | OK | [9 empty] | OK |  |  |  |  | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.21.1 | Ericsson |  | OK |  |  |  |  | OK |  |  |  |  | OK |  |  |  |  | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.23.1 | Ericsson |  | OK |  |  |  |  | OK | OK |  |  |  | OK |  |  |  |  | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.25.1 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.25.2 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.2.4.25.4 | Ericsson |  | OK |  |  |  |  | OK | OK
8.2.4.25.5 | Ericsson |  | OK |  |  |  |  | OK | OK
8.2.4.25.6 | Ericsson |  | OK |  |  |  |  | OK | OK
8.2.4.25.7 | Ericsson |  | OK |  |  |  |  | OK | OK
8.2.4.26 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to RRC Intra E-UTRAN measurements test cases to support Band > 64 - Part 1
8.3.1.1 | Rohde & Schwarz | R5-171455 | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.2 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.3 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.3a | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.4 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.5 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.6 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.7 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.8 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.9 | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.9a | Rohde & Schwarz |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to RRC Intra E-UTRAN measurements test cases to support Band > 64 - Part 2
8.3.1.10 | MCC TF160 | R5-171145 | OK |  |  |  |  | OK
8.3.1.11 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.11a | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.12 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.12a | MCC TF160 |  | OK |  |  |  |  | OK | OK
8.3.1.13a | MCC TF160 |  | OK |  |  |  |  | OK | OK
8.3.1.14a | MCC TF160 |  | OK |  |  |  |  | OK | OK
8.3.1.15 | MCC TF160 |  | OK |  |  |  |  | OK | OK
8.3.1.15a | MCC TF160 |  | OK |  |  |  |  | OK | OK | OK
8.3.1.16a | MCC TF160 |  | OK |  |  |  |  | OK | OK | OK
Correction to RRC Intra E-UTRAN measurements test cases to support Band > 64 - Part 3
8.3.1.17.1 | Ericsson | R5-171114 | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.17.2 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.17.3 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.18.1 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.18.2 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.21 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.22.1 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.22.2 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.23 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.24 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.25 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.26 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.27 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.28 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.29 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.30 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.1.31 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to RRC Inter-RAT measurements test cases to support Band > 64
8.3.2.1 | Ericsson | R5-171115 | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.2 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.3 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.3a | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.4 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.5 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.6 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.7 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.8 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.9 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.10 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.2.11 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to RRC Measurements for self optimized networks test cases to support Band > 64
8.3.3.1 | MCC TF160 | R5-171147 | OK |  |  |  |  | OK | [9 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.3.2 | MCC TF160 |  | OK |  |  |  |  | OK
8.3.3.3 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.3.4 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to RRC Measurement for CSG, Hybrid and Open cells test cases to support Band > 64
8.3.4.1 | MCC TF160 | R5-171148 | OK |  |  |  |  | OK
8.3.4.2 | MCC TF160 |  | OK |  |  |  |  | OK
8.3.4.3 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.4.4 | MCC TF160 |  | OK |  |  |  |  | OK | Ok | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.3.4.5 | MCC TF160 |  | OK | [12 empty] | OK |  |  | Needs update: Band >64 included, but not correct. 'eutra-r9' need to be set to maxEARFCN for Band >64.
Correction to RRC Inter-RAT handover UTRA to E-UTRA test cases to support Band > 64
8.4.2.2 | TBD |  | To Do |  |  |  |  | x | x | [9 empty] | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
8.4.2.4 | TBD |  | To Do |  |  |  |  | x | x | [9 empty] | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
8.4.2.7 | TBD |  | To Do |  |  |  |  | x | x |  |  |  | x | [5 empty] | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
Correction to RRC Inter-RAT mobility E-UTRA to GERAN test cases to support Band > 64
8.4.3.2 | TBD |  | To Do |  |  |  |  | x | x | [8 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.4.3.3 | TBD |  | To Do |  |  |  |  | x | x | [8 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to RRC Inter-RAT handover E-UTRA to and 1xRTT test cases to support Band > 64
8.4.5.4 | TBD |  | To Do |  |  |  |  | x | x | [8 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.4.7.5 | TBD |  | To Do |  |  |  |  | x | x | [8 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.4.7.6 | TBD |  | To Do |  |  |  |  | x | x | [8 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.4.7.7 | TBD |  | To Do |  |  |  |  | x | x | [8 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.4.7.8 | TBD |  | To Do |  |  |  |  | x | x | [8 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.4.7.10 | TBD |  | To Do |  |  |  |  | x | x | [8 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to RRC Radio link failure test cases to support Band > 64
8.5.1.7.1 | Ericsson | R5-171440 | OK | [9 empty] | OK
8.5.4.1 | Ericsson |  | OK |  |  | OK | OK | [11 empty] | No change needed. Already handle Band > 64 in 36.523-1 v13.3.0
8.5.4.2 | Ericsson |  | OK |  |  | OK | OK | [11 empty] | No change needed. Already handle Band > 64 in 36.523-1 v13.3.0
8.5.2.1 | TBD |  | To Do | [13 empty] | x |  | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
Correction to RRC MDT test cases to support Band > 64
8.6.1.1 | Ericsson | R5-171443 | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.1.2 | Ericsson |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.2.1 | Ericsson |  | OK | [7 empty] | OK
8.6.2.2 | Ericsson |  | OK | [7 empty] | OK
8.6.2.3a | Ericsson |  | OK | [7 empty] | OK
8.6.2.9 | Ericsson |  | OK | [7 empty] | OK
8.6.2.10 | Ericsson |  | OK | [7 empty] | OK
8.6.2.11 | Ericsson |  | OK | [7 empty] | OK
8.6.2.12 | Ericsson |  | OK | [7 empty] | OK
Correction to RRC Logged RLF test cases to support Band > 64
8.6.4.1 | MCC TF160 | R5-171144 | OK | [7 empty] | OK | OK | [5 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.4.2 | MCC TF160 |  | OK | [7 empty] | OK | OK | [5 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.4.3 | MCC TF160 |  | OK | [8 empty] | OK
8.6.4.4 | MCC TF160 |  | OK |  |  |  |  | OK | OK |  | OK | OK | [5 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.4.5 | MCC TF160 |  | OK | [8 empty] | OK | [5 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.4.7 | MCC TF160 |  | OK | [7 empty] | OK | OK
8.6.4.8 | MCC TF160 |  | OK | [8 empty] | OK
8.6.4.9 | MCC TF160 |  | OK | [8 empty] | OK | [5 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.4.10 | MCC TF160 |  | OK | [8 empty] | OK
8.6.4.11 | MCC TF160 |  | OK | [8 empty] | OK
Correction to RRC Inter-RAT Logged RLF test cases to support Band > 64
8.6.5.1 | TBD |  | To Do |  |  |  |  | x | x |  |  | x | [5 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.5.1a | TBD |  | To Do |  |  |  |  | x | x |  |  | x | [5 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.5.2 | TBD |  | To Do |  |  |  |  | x | x |  |  | x | [5 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.5.3 | TBD |  | To Do | [8 empty] | x | [5 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.5.4 | TBD |  | To Do |  |  |  |  | x | x |  |  | x
Correction to RRC Logged Handover Failure test cases to support Band > 64
8.6.6.1 | Keysight | R5-171444 | OK | [7 empty] | OK | OK | [5 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.6.2 | Keysight |  | OK |  |  |  |  | OK | OK |  | OK | OK | [5 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.6.4 | Keysight |  | OK | [7 empty] | OK | OK
8.6.6.5 | Keysight |  | OK | [7 empty] | OK | OK | [5 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.6.6 | Keysight |  | OK | [7 empty] | OK | OK | [5 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.6.7 | Keysight |  | OK |  |  |  |  | OK | OK |  | OK | OK | [5 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to RRC Inter-RAT Logged Handover Failure test cases to support Band > 64
8.6.7.1 | TBD |  | To Do | [7 empty] | x | x | [5 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.7.2 | TBD |  | To Do | [7 empty] | x | x | [5 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.7.3 | TBD |  | To Do | [7 empty] | x | x | [5 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.7.4 | TBD |  | To Do |  |  |  |  | x | x |  | x | x | [5 empty] | x | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to RRC Connection Establishment Failure test cases to support Band > 64
8.6.8.2 | Keysight | R5-171445 | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
8.6.8.5 | Keysight |  | OK | [7 empty] | OK
8.6.8.6 | Keysight |  | OK | [7 empty] | OK
8.6.10.1 | Keysight |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
EMM
Correction to EMM test cases to support Band > 64
9.2.1.2.13 | Ericsson | R5-171450 | OK | [11 empty] | OK
ESM
No impact |  |  | OK | [15 empty] | No impact
General tests
Correction to Emergency test cases to support Band > 64
11.2.12 | Ericsson | R5-171452 | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
11.2.11 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
E-UTRA radio bearer tests
No impact |  |  | OK | [15 empty] | No impact
Multi layer procedures
Correction to Multi layer Call setup and RRC connection reconfiguration test cases to support Band > 64
13.1.18 | Qualcomm | R5-171140 | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.2.1 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
Correction to Multi layer Intra-system mobility test cases to support Band > 64
13.4.1.2 | Qualcomm | R5-171592 | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.1.3 | Qualcomm |  | OK |  |  |  |  | OK | OK | OK | [7 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.1.4 | Qualcomm |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.1.5 | Qualcomm |  | OK |  |  |  |  | OK | OK
Correction to Multi layer Inter-system mobility packet test cases to support Band > 64
13.4.2.1 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.2.4 | TBD |  | To Do | [13 empty] | x |  | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.2.2 | Qualcomm | R5-171142 | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.2.6 | Qualcomm |  | OK |  |  |  |  | OK | OK
13.4.2.7 | Qualcomm |  | OK |  |  |  |  | OK | OK
13.4.2.8 | Qualcomm |  | OK |  |  |  |  | OK | OK
Correction to Multi layer Inter-system mobility voice test cases to support Band > 64
13.4.3.3 | Qualcomm | R5-171143 | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.5 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.21 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.22 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.23 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.24 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.25 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.26 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.27 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.28 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.30 | Qualcomm |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
13.4.3.1 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.2 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.4 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.6 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.7 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.8 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.9 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.10 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.11 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.13 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.14 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.15 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.16 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.18 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.19 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
13.4.3.20 | TBD |  | To Do | [14 empty] | x | TBD if there is a use case for HO from UTRA to LTE with LTE band > 64.
ETWS, MM DSMIPv6, Home (e)NB
No impact | - | - | OK | [15 empty] | No impact
MBMS
Correction to MBMS test cases to support Band > 64
17.1.3 | MCC TF160 | R5-171150 | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
17.3.1.3 | MCC TF160 |  | OK |  |  |  |  | OK | OK
17.3.3.3 | MCC TF160 |  | OK |  |  |  |  | OK | OK
17.4.3 | MCC TF160 |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
17.4.4 | MCC TF160 |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
17.4.5 | MCC TF160 |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
17.4.6 | MCC TF160 |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
17.4.9.1 | MCC TF160 |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
17.4.9.2 | MCC TF160 |  | OK | [14 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
17.4.11.1 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
PWS, Device to Device, Tunnel management procedure UE to ePDG
No impact | - | - | OK | [15 empty] | No impact
SC-PTM
Correction to SC-PTM test cases to support Band > 64
21.1.3 | MCC TF160 | R5-171574 | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
21.1.5 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
21.3.3 | MCC TF160 | R5-171573 | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
21.3.4 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
21.3.5 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
21.3.6 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
21.3.7 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
21.3.10 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
21.3.12 | MCC TF160 |  | OK |  |  |  |  | OK | OK | [8 empty] | OK | dl-CarrierFreq indirect via call to MeasObjectEUTRA-GENERIC(Freq) in 36.508 for measObjectId
NB-IoT
No impact | - | - | OK | [15 empty] | No impact

## Actions
Note: IEs within paranthesis indicate the IEs where the IE field is included in
| IEs used to signal band or frequency for Band <= 64 | Associated IEs used to signal Band > 64 and that need to be added/updated in test cases that currently refer to Band <= 64 IEs
IEs using FreqBandIndicator | freqBandIndicator (SystemInformationBlockType1) | freqBandIndicator-v9e0 (SystemInformationBlockType1-v9e0-IEs)
| multiBandInfoList (SystemInformationBlockType1-v8h0-Ies, InterFreqCarrierFreqInfo-v8h0) | multiBandInfoList-v9e0 (SystemInformationBlockType1-v9e0-IEs)
| bandEUTRA (SupportedBandEUTRA) | bandEUTRA-v9e0 (SupportedBandEUTRA-v9e0)
| bandEUTRA-r10 (BandParameters-r10) | bandEUTRA-v1090 (BandParameters-v1090)
IEs using ARFCN-ValueEUTRA | carrierFreq (FreqPriorityEUTRA, MeasObjectEUTRA) | carrierFreq-v9e0 (FreqPriorityEUTRA-v9e0, MeasObjectEUTRA-v9e0)
| dl-CarrierFreq (CarrierFreqEUTRA, InterFreqCarrierFreqInfo) | dl-CarrierFreq-v9e0 (CarrierFreqEUTRA-v9e0, InterFreqCarrierFreqInfo-v9e0)
| ul-CarrierFreq (CarrierFreqEUTRA, SystemInformationBlockType2) | ul-CarrierFreq-v9e0 (CarrierFreqEUTRA-v9e0, , SystemInformationBlockType2-v9e0)
| carrierFreq-r9 (MeasResult2EUTRA-r9) | carrierFreq-v9e0 (MeasResult2EUTRA-v9e0)
| carrierFreq-r10 (RLF-Report-r9, RSTD-InterFreqInfo-r10) | carrierFreq-v1090 (RLF-Report-r9, RSTD-InterFreqInfo-r10)
| dl-CarrierFreq-r10 (SCellToAddMod-r10, CandidateCellInfo-r10) | dl-CarrierFreq-v1090 (SCellToAddMod-r10, CandidateCellInfo-r10)
| ul-CarrierFreq-r10 (RadioResourceConfigCommonSCell-r10) | ul-CarrierFreq-v1090 (RadioResourceConfigCommonSCell-r10)
| eutra (RedirectedCarrierInfo) | eutra-v9e0 (RedirectedCarrierInfo-v9e0)
| eutra-r9 (ProximityIndication-r9-IEs) | eutra-r9-v9e0 (ProximityIndication-r9-IEs)
| earfcn (eutra-FrequencyAndPriorityInfoList in UTRA SysInfoType19 ) | Change only needed if there is a use case for HO from UTRA to LTE with LTE band > 64