## Sheet1
PHASE | NUMBER OF TEST CASES/SECTIONS TO CREATE or EDIT | COMMENT |  |  | NUMBER ASSIGNED PER PHASE
PHASE 1 | 63 | Release 14 Updates of Existing Release 13 MCPTT Test Cases (36.579-2) |  |  | 55
PHASE 2 | 16 | New Release 14 MCPTT Test Cases (36.579-2) |  |  | 16
PHASE 3 | 48 | Release 14 MCVideo Test Cases (36.579-6) |  |  | 1
PHASE 4 | 35 | Release 14 MCData Test Cases (36.579-7), maybe MCPTT Server (36.579-3) |  |  | 0
ALL PHASES | 49 | Updates to 36.579-1, 36.579-4, and 36.579-5 |  |  | 9
TOTAL | 211 |  |  |  | 72
36.579-1
Clause | Title | Assigned Author | Target Date For First Draft | Target Date For Final Draft | PHASE
5 | Common Test Environment
5.1 | General
5.2 | Reference test conditions
5.3 | Generic test procedures for UE MCPTT operation
5.3.1 | General |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.3.2 | Generic Test Procedure for MCPTT Authorization/Configuration and Key Generation |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.3.3 | Generic Test Procedure for MCPTT pre-established session establishment CO |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4 | Generic test procedures for UE operation over EUTRA/EPS
5.4.1 | General |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.1A | UE APN/PDN support assumptions |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.2 | Generic Test Procedure for MCPTT UE registration |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.3 | Generic Test Procedure for MCPTT CO communication in E-UTRA |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.4 | Generic Test Procedure for MCPTT CT communication in E-UTRA |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.5 | Generic Test Procedure for MCPTT CO communication over ProSe direct one-to-one communication out of E-UTRA coverage-establishment |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.6 | Generic Test Procedure for MCPTT CT communication over ProSe direct one-to-one communication out of E-UTRA coverage-establishment |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.7 | Generic Test Procedure for MCPTT communication over ProSe direct one-to-one communication out of E-UTRA coverage - release by the SS |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.8 | Generic Test Procedure for MCPTT communication over ProSe direct one-to-one communication out of E-UTRA coverage - release by the UE |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.9 | Generic Test Procedure for MCPTT communication in E-UTRA / Change of cells |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.10 | Generic Test Procedure for MCPTT CT communication over ProSe direct one-to-many communication out of E-UTRA coverage / Announcing/Discoveree procedure for group member discovery |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.11 | Generic Test Procedure for MCPTT CO communication over ProSe direct one-to-many communication out of E-UTRA coverage / Monitoring/Discoverer procedure for group member discovery / One-to-many communication |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.4.12 | Generic Test Procedure for MCPTT communication over MBMS |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.5 | Default message and other information elements content
5.5.1 | General |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.5.2 | Default SIP message and other information elements |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.5.3 | Default SDP message and other information elements |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.5.4 | Default HTTP message and other information elements |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.5.5 | Default MCPTT call control Off-network messages and other information elements |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.5.6 | Default MCPTT media plane control messages and other information elements |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.5.7 | Default MCPTT group management messages and other information elements |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.5.8 | Default MCPTT configuration management messages and other information elements |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.5.9 | Default miscellaneous messages and other information elements |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.5.10 | Common MCPTT test USIM parameters |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.6 | Reference configurations
5.6.1 | General |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.6.2 | Key material for provisioning of End-to-end communication security |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5.6.3 | XML schema for MCPTT location information |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
36.579-2
Clause | Title | Assigned Author | Target Date For First Draft | Target Date For Final Draft | PHASE
5 | MCPTT Client Configuration
5.1 | Configuration / Authentication / User Authorisation / UE Configuration / User Profile |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 1
5.2 | Configuration / Group Creation / Group Regroup Creation / Group Regroup Teardown |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 1
5.3 | Configuration / Group Affiliation / Remote change / De-affiliation / Home MCPTT system | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
5.4 | Configuration / Pre-established Session Establishment / Pre-established Session Modification / Pre-established Session Release | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
5.5 | Configuration / Determination of MCPTT Service Settings / Current Active MCPTT Settings / De-subscribe | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6 | On-network Test Scenarios
6.1 | Group Calls
6.1.1 | Pre-arranged Group Call
6.1.1.1 | On-network / On-demand Pre-arranged Group Call / Automatic Commencement Mode / Floor Control / Upgrade to Emergency Group Call / Cancel Emergency State / Upgrade to Imminent Peril Group Call / Cancel Imminent Peril State / Client Originated (CO) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.2 | On-network / On-demand Pre-arranged Group Call / Automatic Commencement Mode / Floor Control / Upgrade to Emergency Group Call / Cancel Emergency State / Upgrade to Imminent Peril Group Call / Cancel Imminent Peril State / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.3 | On-network / On-demand Pre-arranged Group Call / Manual Commencement Mode / Client Originated (CO) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.4 | On-network / On-demand Pre-arranged Group Call / Manual Commencement Mode / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.5 | On-network / Pre-arranged Group Call using pre-established session / Client originated Pre-established Session Release with associated MCPTT session / Client Originated (CO)) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.6 | On-network / Pre-arranged Group Call using pre-established session / Automatic Commencement Mode / Server originated Pre-established Session Release with associated MCPTT session / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.7 | On-network / Pre-arranged Group Call using pre-established session / Manual Commencement Mode / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.8 | On-network / Pre-arranged Broadcast Group Call / Client Originated (CO) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.9 | On-network / Pre-arranged Broadcast Group Call / Client Terminated (CT) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.10 | On-network / Broadcast Group Call with Temporary Group / Client Originated (CO) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.11 | On-network / Pre-arranged Emergency Group Call / Client Originated (CO) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.12 | On-network / Pre-arranged Emergency Group Call / Client Terminated (CT) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.13 | On-network / Pre-Arranged Imminent Peril Group Call / Client Originated (CO) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.14 | On-network / Pre-Arranged Imminent Peril Group Call / Client Terminated (CT) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.15 | On-network / Emergency Alert / Cancel Emergency Alert / Client Originated (CO) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.1.16 | On-network / Emergency Alert / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.2 | Chat Group Calls
6.1.2.1 | On-network / On-demand Chat Group Call / Client Origination (CO) |  |  |  | PHASE 1
6.1.2.2 | On-network / Chat Group Call Using Pre-established Session Including Emergency and Imminent Peril Calls / Client Server originated Pre-established Session Release with associated MCPTT session / Client Origination (CO) |  |  |  | PHASE 1
6.1.2.3 | On-network / Chat Group Call / Late Entry |  |  |  | PHASE 1
6.1.2.4 | On-network / Chat Group Call / Rejection Upon Join Attempt / Join Attempt Successful / De-affiliation |  |  |  | PHASE 1
6.1.2.5 | On-network / Chat Group Broadcast Group Call / Client Originated (CO) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.2.6 | On-network / Chat Group Broadcast Group Call / Client Terminated (CT) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.2.7 | On-network / Chat Group Emergency Group Call / Client Originated (CO) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.2.8 | On-network / Chat Group Emergency Group Call / Client Terminated (CT) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.2.9 | On-network / Chat Group Imminent Peril Group Call / Client Originated (CO) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.2.10 | On-network / Chat Group Imminent Peril Group Call / Client Terminated (CT) | Mediatek | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.1.3 | Conference Event Package
6.1.3.1 | On-network / Conference Event Package / Subscription to Conference Event Package /Termination of subscription | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.1.4 | Remote Change of Selected Group
6.1.4.1 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Originated (CO) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.1.4.2 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2 | Private Calls
6.2.1 | On-network / Private Call / On-demand / Automatic Commencement Mode / With Floor Control / Upgrade to Emergency Call / Cancellation of Emergency on User request / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.2 | On-network / Private Call / On-demand / Automatic Commencement Mode / With Floor Control / Upgrade to Emergency Call / Cancellation of Emergency on User request / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.3 | On-network / Private Call / On-demand / Automatic Commencement Mode / Without Floor Control / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.4 | On-network / Private Call / On-demand / Automatic Commencement Mode / Without Floor Control / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.5 | On-network / Private Call / Emergency Private Call / On-demand / Automatic Commencement Mode / Force of automatic commencement mode / Without Floor Control / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.6 | On-network / Private Call / Emergency Private Call / On-demand / Manual Commencement Mode / Force of automatic commencement mode / Without Floor Control / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.7 | On-network / Private Call / On-demand / Manual Commencement Mode / Without Floor Control / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.8 | On-network / Private Call / On-demand / Manual Commencement Mode / Without Floor Control / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.9 | On-network / Private Call / Within a pre-established session / Automatic Commencement Mode / Without Floor Control / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.10 | On-network / Private Call / Within a pre-established session / Automatic Commencement Mode / Without Floor Control / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.11 | On-network / Private Call / Within a pre-established session / Manual Commencement Mode / Without Floor Control / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
6.2.12 | On-network / Private Call / Private Call Call-Back Request / Private Call Call-Back Cancel Request / Client Originated (CO) / Private call call-back fulfilment | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.13 | On-network / Private Call / Private Call Call-Back Request / Private Call Call-Back Cancel Request / Client Terminated (CT) / Private call call-back fulfilment | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.14 | On-network / Private Call / Ambient listening call / Remotely initiated Ambient listening call / Remotely initiated ambient listening call release / Success / Client Originated (CO) / Server initiated ambient call release | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.15 | On-network / Private Call / Ambient listening call / Remotely initiated Ambient listening call / Remotely initiated ambient listening call release / Success / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.16 | On-network / Private Call / Ambient listening call / Locally initiated Ambient listening call / Locally initiated ambient listening call release / Success / Client Originated (CO) / Server initiated ambient call release | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.17 | On-network / Private Call / Ambient listening call / Locally initiated Ambient listening call / Locally initiated ambient listening call release / Success / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.18 | On-network / Private Call / Ambient Listening Call / Remote Initiated Ambient Listening Call Using Pre-Established Session / Ambient Listening Call Release / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.19 | On-network / Private Call / Ambient Listening Call / Remote Initiated Ambient Listening Call Using Pre-Established Session / Ambient Listening Call Release / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.20 | On-network / Private Call / First-To-Answer Call / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.21 | On-network / Private Call / First-To-Answer Call / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.22 | On-network / Private Call / First-To-Answer Call Using Pre-Established Session / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.2.23 | On-network / Private Call / First-To-Answer Call Using Pre-Established Session / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 2
6.3 | Location
6.3.1 | On-network / Location / Event Triggered Location Information Report |  |  |  | PHASE 1
6.3.2 | On-network / Location / On-demand Location Information Request |  |  |  | PHASE 1
6.4 | MBMS
6.4.1 | On-network / MBMS / MBMS Bearer Announcement / MBMS Bearer Listening Status / Transition to MBMS from Unicast / MBMS Floor Control / Transition to Unicast from MBMS | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7 | Off-network
7.1 | Group Calls
7.1.1 | Off-network / Group Call / Floor Control / Upgrade to Emergency Call / Downgrade from Emergency / Upgrade to Imminent Peril / Downgrade from Imminent Peril / Release Call / Client Originated (CO) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
|  | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.2 | Off-network / Group Call / Floor Control / Upgrade to Emergency Call / Downgrade from Emergency / Upgrade to Imminent Peril / Downgrade from Imminent Peril / Release Call / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.3 | Off-network / Group Call / Leave Group Call when GROUP CALL PROBE sent / Initiate Group Call for Released Call / Receive GROUP CALL ACCOUNCEMENT for Released call / No GROUP CALL ACCOUNCEMENT for Released Call / Receive Response to GROUP CALL PROBE | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.4 | Off-network / Group Call / MCPTT User Acknowledgement Required / With Confirm Indication / MCPTT User Reject / MCPTT User Accept / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.5 | Off-network / Group Call / MCPTT User Acknowledgement Required / Without Confirm Indication / MCPTT User Reject / MCPTT User Accept / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.6 | Off-network / Group Call / Merge Two Calls | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.7 | Off-network / Group Call / Emergency Call / Imminent Peril Call/ Client Originated (CO) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.8 | Off-network / Group Call / Emergency Call / Imminent Peril Call/ Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.9 | Off-network / Group Call / Emergency Alert / Emergency Alert Retransmission / Cancel Emergency Alert / Client Originated (CO) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.10 | Off-network / Group Call / Emergency Alert / Emergency Alert Retransmission / Cancel Emergency Alert / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.11 | Off-network / Group Call / Broadcast Group Call / Broadcast Group Call Retransmitting / Broadcast Group Call Release / Client Originated (CO) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.12 | Off-network / Group Call / Broadcast Group Call / MCPTT User Ack Not Required / Originator Releases Call / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.1.13 | Off-network / Group Call / Broadcast Group Call / MCPTT User Ack Required / MCPTT User Reject / MCPTT User Accept / MCPTT User Releases Call / Client Terminated (CT) | NIST | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.2 | Private Calls
7.2.1 | Off-network / Private Call / Automatic Commencement Mode / No Response to Private Call Setup Request / Private call setup success / With Floor Control / Upgrade to Emergency Call / Cancellation of Emergency on User request / Release Call / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.2.2 | Off-network / Private Call / Automatic Commencement Mode / No Response to Private Call Setup Accept / Private call setup success / With Floor Control / Upgrade to Emergency Call / Cancellation of Emergency on User request / Release Call / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.2.3 | Off-network / Private Call / Automatic Commencement Mode / Upgrade to Emergency Call Reject / Downgrade from Emergency Call Failure / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.2.4 | Off-network / Private Call / Manual Commencement Mode / Call Released before establishment completion / Call request Rejected / Call establishment successful / Client Originated (CO) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
7.2.5 | Off-network / Private Call / Manual Commencement Mode Call / Released before establishment completion / User does not answer to Ringing / User Rejects call request / Call establishment successful / Client Terminated (CT) | Samsung | 3GPPRAN5#81 (Nov 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 1
36.523-1
Clause | Title | Assigned Author | Target Date For First Draft | Target Date For Final Draft | PHASE
19.1.9 | ProSe Direct Communication / Pre-configured authorisation / UE out of coverage on the frequency used for sidelink communication / Isolated one-to-one ProSe direct communication / Success/Direct link keepalive/Release upon User request / MO | Samsung | FFS |  | FFS
19.1.10 | ProSe Direct Communication / Pre-configured authorisation / UE out of coverage on the frequency used for sidelink communication / Isolated one-to-one ProSe direct communication / Success/Direct link keepalive/Release upon User request / MT | Samsung | FFS |  | FFS
19.2.6 | One-to-many ProSe direct communication / Pre-configured authorisation / Off-network / ProSe Direct Discovery for public safety use / Announcing UE procedure for group member discovery | Samsung | FFS |  | FFS
19.2.7 | One-to-many ProSe direct communication / Pre-configured authorisation / Off-network / ProSe Direct Discovery for public safety use / Discoverer UE procedure for group member discovery | Samsung | FFS |  | FFS
19.2.8 | One-to-many ProSe direct communication / Pre-configured authorisation / Off-network / ProSe Direct Discovery for public safety use / Discoveree UE procedure for group member discovery | Samsung | FFS |  | FFS
36.579-3
Clause | Title | Assigned Author | Target Date For First Draft | Target Date For Final Draft | PHASE
5 | MCPTT Client Configuration
5.1 | MCPTT Server - MCPTT Client / Configuration / Authentication / User Authorisation / UE Configuration / User Profile | NIST | FFS |  | FFS
6 | MCPTT Server - MCPTT Client operation
6.1 | MCPTT Server - MCPTT Client / On-demand Pre-arranged Group Call / Automatic Commencement Mode / Floor Control | NIST | FFS |  | FFS
7 | MCPTT Server - MCPTT Server operation
7.1 | MCPTT Server - MCPTT Server / On-demand Pre-arranged Group Call / Automatic Commencement Mode / Floor Control / Controlling Server | NIST | FFS |  | FFS
7.2 | MCPTT Server - MCPTT Server / On-demand Pre-arranged Group Call / Automatic Commencement Mode / Floor Control / Participating Server | NIST | FFS |  | FFS
36.579-4
Clause | Title | Assigned Author | Target Date For First Draft | Target Date For Final Draft | PHASE
4 | Recommended Test Case Applicability |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A.1 | Guidance for completing the ICS proforma
A.1.1 | Purposes and structure |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A.1.2 | Abbreviations and conventions |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A.1.3 | Instructions for completing the ICS proforma |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A.2 | Identification of the MCPTT Client/Server Equipment
A.2.1 | Date of the statement |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A.2.2 | MCPTT Client/Server Under Test (CUT/SUT) identification |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A.2.3 | Product supplier |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A.2.4 | The Organisation responsible for the Product testing |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A.2.5 | ICS contact person |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A.3 | Identification of the protocol |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A.4 | ICS proforma tables
A.4.1 | Implementation Types |  |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
36.579-5
Clause | Title | Assigned Author | Target Date For First Draft | Target Date For Final Draft | PHASE
4 | Test system architecture | TF 160 |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
5 | Test models | TF 160 |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
6 | System interface | TF 160 |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
7 | Test methods and design considerations | TF 160 |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
8 | Other SS requirements with TTCN-3 impact | TF 160 |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
9 | IXIT Proforma | TF 160 |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
10 | Postambles | TF 160 |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
A | Test Suites | TF 160 |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
B | Style Guide | TF 160 |  | 3GPPRAN5#85 (Nov 2019) | ALL PHASES
36.579-6
Clause | Title | Assigned Author | Target Date For First Draft | Target Date For Final Draft | PHASE
5 | MCVideo Client Configuration
5.1 | Configuration / Authentication / User Authorization / UE Configuration / User Profile / Key Generation |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
5.2 | Configuration / Group Creation / Group ReGroup Creation / Group ReGroup Teardown |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
5.3 | Configuration / Group Affiliation / Remote change / De-affiliation / Home MCVideo system |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
5.4 | Configuration / Pre-established Session Establishment / Pre-established Session Modification / Pre-established Session Release |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
5.5 | Configuration / Determination of MCVideo Service Settings / Current Active MCVideo Settings / De-subscribe |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6 | On-Network Test Scenarios
6.1 | Group Calls
6.1.1 | Pre-arranged Group Call
6.1.1.1 | On-network / On-demand Pre-arranged Group Call / Automatic Commencement Mode / Transmission Control / Upgrade to Emergency Group Call / Cancel Emergency State / Upgrade to Imminent Peril Group Call / Cancel Imminent Peril State / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.1.2 | On-network / On-demand Pre-arranged Group Call / Automatic Commencement Mode / Transmission Control / Upgrade to Emergency Group Call / Cancel Emergency State / Upgrade to Imminent Peril Group Call / Cancel Imminent Peril State / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.1.3 | On-network / On-demand Pre-arranged Group Call / Manual Commencement Mode / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.1.4 | On-network / On-demand Pre-arranged Group Call / Manual Commencement Mode / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.1.5 | On-network / Pre-arranged Emergency Group Call / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.1.6 | On-network / Pre-arranged Broadcast Group Call / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.1.7 | On-network / Broadcast Group Call with Temporary Group / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.1.8 | On-network / Pre-arranged Broadcast Group Call / Client Originated (CO) | NIST | 3GPPRAN5#80 (Aug 2018) | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.1.9 | On-network / Pre-arranged Emergency Group Call / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.1.10 | On-network / Pre-Arranged Imminent Peril Group Call / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.1.11 | On-network / Pre-Arranged Imminent Peril Group Call / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.2 | Chat Group Call
6.1.2.1 | On-network / On-demand Chat Group Call / End Chat Group Call / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.2.2 | On-network / Chat Group Call / Upgrade to Emergency Chat Group Call / Cancel Emergency Chat Group Call / Upgrade to Imminent Peril Chat Group Call / Cancel Imminent Peril Chat Group Call / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.2.3 | On-network / Chat Group Call / Upgrade to Emergency Chat Group Call / Cancel Emergency Chat Group Call / Upgrade to Imminent Peril Chat Group Call / Cancel Imminent Peril Chat Group Call / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.1.2.4 | On-network / On-demand Chat Group Call / Emergency Call / Imminent Peril Call /Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.2 | Subscription to Conference Events Package
6.2.1 | On-network / Conference Event Package / Subscription to Conference Event Package / Termination of subscription |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.3 | Remote Change of an MCVideo User's selected Group
6.3.1 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.3.2 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.4 | Private Calls
6.4.1 | On-network / Private Call / On-demand / Automatic Commencement Mode / With Transmission Control / Upgrade to Emergency Call / Cancellation of Emergency on User request / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.4.2 | On-network / Private Call / On-demand / Automatic Commencement Mode / With Transmission Control / Upgrade to Emergency Call / Cancellation of Emergency on User request / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.4.3 | On-network / Private Call / On-demand / Automatic Commencement Mode / Without Transmission Control / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.4.4 | On-network / Private Call / On-demand / Automatic Commencement Mode / Without Transmission Control / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.4.5 | On-network / Private Call / Emergency Private Call / On-demand / Automatic Commencement Mode / Force of automatic commencement mode / Without Transmission Control / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.4.6 | On-network / Private Call / Emergency Private Call / On-demand / Manual Commencement Mode / Force of automatic commencement mode / Without Transmission Control / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.4.7 | On-network / Private Call / On-demand / Manual Commencement Mode / Without Transmission Control / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.4.8 | On-network / Private Call / On-demand / Manual Commencement Mode / Without Transmission Control / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.5 | Emergency Alert
6.5.1 | On-network / Emergency Alert / Emergency alert origination / Emergency alert cancellation / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
6.5.2 | On-network / Emergency Alert / Emergency alert origination / Emergency alert cancellation / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7 | Off-Network Test Scenarios
7.1 | Group Calls
7.1.1 | Off-network / Group Call / Transmission Control / Upgrade to Emergency Call / Downgrade from Emergency Call / Upgrade to Imminent Peril Call / Downgrade from Imminent Peril Call / Release call / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.1.2 | Off-network / Group Call / Transmission Control / Upgrade to Emergency Call / Downgrade from Emergency Call / Upgrade to Imminent Peril Call / Downgrade from Imminent Peril Call / Release call / Client Originated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.1.3 | Off-network / Group Call / Leave Group Call when GROUP CALL PROBE sent / Initiate Group Call for Released Call / Receive GROUP CALL ACCOUNCEMENT for Released call / No GROUP CALL ACCOUNCEMENT for Released Call / Receive Response to GROUP CALL PROBE |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.1.4 | Off-network / Group Call / MCVideo User Acknowledgement Required / With Confirm Indication / MCVideo User Reject / MCVideo User Accept / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.1.5 | Off-network / Group Call / MCVideo User Acknowledgement Required / Without Confirm Indication / MCVideo User Reject / MCVideo User Accept / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019)
7.1.6 | Off-network / Group Call / Merge Two Calls |  |  | 3GPPRAN5#85 (Nov 2019)
7.1.7 | Off-network / Group Call / Emergency Call / Imminent Peril Call/ Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019)
7.1.8 | Off-network / Group Call / Emergency Call / Imminent Peril Call/ Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.2 | Broadcast Call
7.2.1 | Off-network / Broadcast Group Call / Broadcast Group Call Retransmitting / Broadcast Group Call Release / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.2.2 | Off-network / Broadcast Group Call / User ack not required / Broadcast Group Call originator releases call / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.2.3 | Off-network / Broadcast Group Call / User ack required / call rejected / call accepted / terminating user releases call / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.3 | Private Call
7.3.1 | Off-network / Private Call / Automatic Commencement Mode / No Response to Private Call Setup Request / Private call setup success / With Transmission Control / Upgrade to Emergency Call / Downgrade from Emergency Call / Release Call / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.3.2 | Off-network / Private Call / Automatic Commencement Mode / No Response to Private Call Setup Accept / Private call setup success / With Transmission Control / Upgrade to Emergency Call / Downgrade from Emergency Call / Release Call / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.3.3 | Off-network / Private Call / Automatic Commencement Mode / Upgrade to Emergency Call Reject / Downgrade from Emergency Call Failure / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.3.4 | Off-network / Private Call / Manual Commencement Mode / Call Released before establishment completion / Call request Rejected / Call establishment successful / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.3.5 | Off-network / Private Call / Manual Commencement Mode Call / Released before establishment completion / User does not answer to Ringing / User Rejects call request / Call establishment successful / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.4 | Emergency Alerts
7.4.1 | Off-network / Emergency Alert transmitted by MCVideo Client / TEF2 expires / TEF1 expires / Cancel Emergency Alert / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
7.4.2 | Off-network / Emergency Alert transmitted by MCVideo Client / Emergency Alert retransmitted / Cancel Emergency Alert / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 3
36.579-7
Clause | Title | Assigned Author | Target Date For First Draft | Target Date For Final Draft | PHASE
5 | MCData Client Configuration
5.1 | Configuration / Authentication / User Authorization / UE Configuration / User Profile / Key Generation |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
5.2 | Configuration / Group Creation / Group ReGroup Creation / Group ReGroup Teardown |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
5.3 | Configuration / Group Affiliation / De-affiliation / Home MCData system |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
5.4 | Configuration / Determination of MCData Service Settings / Current Active MCData Settings / De-subscribe |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6 | On-Network Test Scenarios
6.1 | Short Data Service
6.1.1 | On-network / Short Data Service (SDS) / Standalone SDS Using Signaling Control Plane / One-to-one Standalone SDS / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.2 | On-network / Short Data Service (SDS) / Standalone SDS Using Signaling Control Plane / One-to-one Standalone SDS / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.3 | On-network / Short Data Service (SDS) / Standalone SDS Using Signaling Control Plane / Group Standalone SDS / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.4 | On-network / Short Data Service (SDS) / Standalone SDS Using Signaling Control Plane / Group Standalone SDS / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.5 | On-network / Short Data Service (SDS) / Standalone SDS Using Media Plane / One-to-one Standalone SDS / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.6 | On-network / Short Data Service (SDS) / Standalone SDS Using Media Plane / One-to-one Standalone SDS / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.7 | On-network / Short Data Service (SDS) / Standalone SDS Using Media Plane / Group Standalone SDS / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.8 | On-network / Short Data Service (SDS) / Standalone SDS Using Media Plane / Group Standalone SDS / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.9 | On-network / Short Data Service (SDS) / SDS Session / One-to-one SDS Session / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.10 | On-network / Short Data Service (SDS) / SDS Session / One-to-one SDS Session / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.11 | On-network / Short Data Service (SDS) / SDS Session / Group SDS Session / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.1.12 | On-network / Short Data Service (SDS) / SDS Session / Group SDS Session / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2 | File Distribution
6.2.1 | On-network / File Distribution (FD) / FD Using HTTP / One-to-one Standalone FD / Before TDU2 Timers Expires / FD Accept with Disposition Request / FD Reject / FD Defer / FD Accept without Disposition Request / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.2 | On-network / File Distribution (FD) / FD Using HTTP / One-to-one Standalone FD / Before TDU2 Timers Expires / FD Accept with Disposition Request / FD Reject / FD Defer / FD Accept without Disposition Request / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.3 | On-network / File Distribution (FD) / FD Using HTTP / Group Standalone FD / Before TDU2 Timers Expires / FD Accept with Disposition Request / FD Reject / FD Defer / FD Accept without Disposition Request / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.4 | On-network / File Distribution (FD) / FD Using HTTP / Group Standalone FD / Before TDU2 Timers Expires / FD Accept with Disposition Request / FD Reject / FD Defer / FD Accept without Disposition Request / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.5 | On-network / File Distribution (FD) / FD Using HTTP / One-to-one Standalone FD / After TDU2 Timers Expires / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.6 | On-network / File Distribution (FD) / FD Using HTTP / One-to-one Standalone FD / After TDU2 Timers Expires / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.7 | On-network / File Distribution (FD) / FD Using HTTP / Group Standalone FD / After TDU2 Timers Expires / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.8 | On-network / File Distribution (FD) / FD Using HTTP / Group Standalone FD / After TDU2 Timers Expires / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.9 | On-network / File Distribution (FD) / FD Using Media Plane / One-to-one Standalone FD / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.10 | On-network / File Distribution (FD) / FD Using Media Plane / One-to-one Standalone FD / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.11 | On-network / File Distribution (FD) / FD Using Media Plane / Group Standalone FD / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
6.2.12 | On-network / File Distribution (FD) / FD Using Media Plane / Group Standalone FD / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
7 | Off-Network Test Scenarios
7.1 | Short Data Service
7.1.1 | Off-network / Short Data Service (SDS) / Group Standalone SDS / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
7.1.2 | Off-network / Short Data Service (SDS) / Group Standalone SDS / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
7.1.3 | Off-network / Short Data Service (SDS) / One-to-one Standalone SDS / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
7.1.4 | Off-network / Short Data Service (SDS) / One-to-one Standalone SDS / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
7.1.5 | Off-network / Short Data Service (SDS) / Group Standalone SDS / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
7.1.6 | Off-network / Short Data Service (SDS) / One-to-one Standalone SDS / Client Originated (CO) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4
7.1.7 | Off-network / Short Data Service (SDS) / Expiry of Timer TFS3 (delivery and read) / Client Terminated (CT) |  |  | 3GPPRAN5#85 (Nov 2019) | PHASE 4