## Slide 1: RAN5 5G NR DELIVERY phases and targets (Update aT RAN5#80, Aug-18)
RAN5#80 meeting R5-185183
Gothenburg, Sweden, 20th-24th August 2018

## Slide 2: Introduction & CONTENT
The purpose of this document is to reflect the updated target dates and content of the RAN5 5GS delivery phases agreed at RAN5#80.
The document is used as base for setting the detailed targets in the work plans.
Content
RAN5 phase delivery targets
Content of NSA Option 3 (EN-DC) Phases
Content of SA Option 2 (SA NR) Phases

## Slide 3
RAN5 have decided to move the Option 5 Phase 1 target from Nov-18 to May-19
  Reason: RAN5 focus on delivery of Option 3 Phase 2 and Option 2 Phase 1 by Nov-18.
  Inputs from industry needed on:
    Can RAN5 assume that a UE supporting Option 5 also will support Option 2.
      This will have impact on the number of test cases that need to be developed for Option 5
SA Option 5 (SA E-UTRA) Phase 1 content
- Target RAN5#81 Nov-18

## Slide 4
RAN5 phases and targets
RAN5#79 May-18
  NSA Option 3 (EN-DC) Phase 1
RAN5#80 Aug-18
  NSA Option 3 (EN-DC) Phase 1.5
RAN5#81 Nov-18
  NSA Option 3 (EN-DC) Phase 2
  SA Option 2 (SA NR) Phase 1
RAN5#83 May-19
  NSA Option 3 (EN-DC) Phase 3
  SA Option 2 (SA NR) Phase 2
  SA Option 5 (SA E-UTRA) Phase 1 (moved 6 months, see slide 3)
  NSA Option 7 (NGEN-DC) Phase 1
  NSA Option 4 (NE-DC) Phase 1

## Slide 5: RAN5 phases and targets
Overview: Time line - RAN5 5G NR targets

## Slide 6
General considerations & Definitions
The RF, Demod/CSI reporting and RRM test cases can be divided into the following parts
  Test definition Test case description excluding MU (FR2) and TT (FR1 and FR2) part(s) i.e. non MU/TT parts of minimum requirements, Initial conditions, Test points, Test procedure, Specific message content etc.
  MU Measurement Uncertainty
  TT Test Tolerances
  Complete FR1 test case Test definition + MU + TT
  Complete FR2 test case Test definition + MU + TT
NOTE!
  The completion targets for EN-DC FR2 test cases are set based on the RAN5 MU/TT targets as described in R5-183257.
  Until the MU/TT becomes available it is important that the parts of test definition of the FR2 test cases that are NOT dependent on MU/TT are progressed as far as possible.
Content of RAN5 5GS PHASES

## Slide 7
INCLUDED:
  EN-DC configurations: LTE 1CC + NR FR1 1CC
  Protocol - TS 38.523-x
    54 NR Layer 2 test cases: 23 MAC, 17 RLC and 14 PDCP
    12 RRC test cases for single NR cell scenarios
    3 NAS EPC test cases (all)
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable LTE+NR FR1 MCG+SCG and Split bearer testing
  UE test functions - TS 38.509
    UE test loop mode A and UE test loop mode B.
NOT INCLUDED:
  No RF FR1 test cases (TS 38.521-1, TS 38.521-3) due to pending completion of outstanding details in core specifications (TS 38.101-1 and TS 38.101-3).
  No RF FR2, Demod/CSI reporting or RRM test cases (TS 38.521-2, TS 38.521-3, TS 38.533).
  Protocol test cases for EN-DC NR multi-cell scenarios, EN-DC NR CA, dedicated BWPs, SRB3, measurement test cases
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#87 (May-18)
Note 3: TT needs one more meeting cycle
NSA Option 3 (EN-DC) Phase 1 content
- Target RAN5#79 MAY-18
Completed @ RAN5#79

## Slide 8
CONTENT:
  EN-DC configurations: RF: LTE 1CC + NR FR1 1CC
    Protocol: LTE 1CC + NR FR1 1CC; and LTE 1CC + NR FR2 1CC
    Test frequencies for 1 LTE+FR1 Intra-Band Contiguous; 18 LTE & FR1 Inter-band and 9 LTE & FR2 Inter-band EN-DC configurations (see next slide)
  RF - TS 38.521-3, TS 38.522, TS 38.521-1, TR 38.903, TR 38.905
    Five (5) completed RF Test cases (four transmitter and one receiver):
      6.5B.3.3.1 General Spurious Emissions for Inter-band EN-DC within FR1
      6.5B.2.3.1 Spectrum emissions mask for Inter-band EN-DC within FR1
      6.5B.2.3.3 Adjacent Channel Leakage Ratio for Inter-band EN-DC within FR1
      6.3B.1.3 Min Output Power for EN-DC for Inter-band EN-DC within FR1
      7.3B.2.3 Reference sensitivity for Inter-band EN-DC within FR1
  Protocol - TS 38.523-x (overall number of completed test cases Phase 1 & Phase 1.5)
    64 (+10) NR Layer 2 test cases: 33 (+10) MAC, 17 RLC and 14 PDCP
    12 RRC test cases for single NR cell scenarios
    6 (+6) RRC test cases for multi NR cell scenarios
    3 NAS EPC test cases (all included in Phase 1 delivery)
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
NSA Option 3 (EN-DC) Phase 1.5 content
RAN5#80 Aug-18
Completed @ RAN5#80

## Slide 9
Test frequencies included in Phase 1.5 delivery:
  LTE+FR1 Intra-band contiguous
    DC_(n)41
  LTE+FR1 Inter-band
    DC_1A_n28A, DC_1A_n77A, DC_1A_n78A, DC_1A_n79A
    DC_3A_n77A, DC_3A_n78A, DC_3A_n79A
    DC_19A_n77A, DC_19A_n78A, DC_19A_n79A
    DC_20A_n78A
    DC_21A_n77A, DC_21A_n78A, DC_21A_n79A
    DC_25A_n41A
    DC_28A_n77A, DC_28A_n78A, DC_28A_n79A
  LTE+FR2 Inter-band
    DC_1A_n257A
    DC_3A_n257A
    DC_5A-n260A, DC_5A_n261A
    DC_13A_n257A
    DC_19A_n257A
    DC_21A_n257A
    DC_66A_n260A, DC_66A-n261A
NSA Option 3 (EN-DC) Phase 1.5 content
RAN5#80 Aug-18

## Slide 10
TARGETED TO BE INCLUDED:
  EN-DC configurations: LTE xCC + NR FR1 1CC, where x<=3; and LTE 1CC + NR FR2 1CC
  RF - TS 38.521-3, TS 38.522, TS 38.521-1 (Note 1), TS 38.521-2 (Note 1), TR 38.903, TR 38.905
    Test definition, MU and TT for LTE+NR FR1: Rx and Tx test cases not completed in NSA Opt.3 Phase 1.5, Note 2
    Test definition, MU and TT for LTE+NR FR2 RF MU/TT Target 1 and Target 2 test cases, Note 3
  Protocol - TS 38.523-x, TS 37.571-x
    Enhanced Layer 2 test coverage
    Enhanced RRC test coverage for NR multi-cell test scenarios, dedicated BWP, SRB3, measurements
    LTE 1CC + NR FR1 1CC and LTE 1CC + NR FR2 1CC test cases
    Enhanced test coverage for L1 st guconfitraions based on industry interest
    Positioning EN-DC test cases
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable FR2 testing (RF and protocol)
  UE test functions - TS 38.509
    UBF, SS-RSRPB UE reporting, UE Positioning test functionsNOT INCLUDED:
  RF MU/TT for RF MU/TT Target 3 test cases (TS 38.521-3)
  No LTE + NR FR1 or FR2 Demod/CSI reporting (TS 38.521-4) and No NR FR1 or FR2 RRM (TS 38.533)
  No IMS test cases (TS 34.229-x)
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#89 (Nov-18)
Note 3: Dependency: RAN4 progress until RAN4#89 (Nov-18) + RAN5 RF MU/TT progress. For RF MU/TT target 1 and target 2 test cases MU is planned to be completed by RAN5#NR3 (Oct-18) and TT is targeted to be completed by RAN5#81 (Nov-18) (Ref R5-183257)
NSA Option 3 (EN-DC) Phase 2 content
- Target RAN5#81 NOV-18

## Slide 11
NSA Option 3 (EN-DC) Phase 3 content
- Target RAN5#83 MAY-19
TARGETED TO BE INCLUDED:
  EN-DC configurations: LTE xCC + NR FR1/FR2 yCC, where x <= 4, y <=2
  RF - TS 38.521-3, TS 38.522, TS 38.521-1 (Note 1), TS 38.521-2 (Note 1), TS 38.521-4, TS 38.533, TR 38.903, TR 38.905
    TT part for RF MU/TT Target 3 test cases (TS 38-521-3), Note 3
    Test definition and TT for LTE+NR FR1 Demod/CSI reporting (TS 38.521-4) and RRM (TS 38.533), Note 2
    Test definition for LTE+NR FR2 Demod/CSI reporting (TS 38.521-4) and LTE+NR FR2 RRM (TS 38.533), Note 2
    Positioning performance
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Remaining test cases not completed in NSA Opt.3 Phase 2
    LTE 1CC + NR FR1/FR2 2CC test cases, Note 5
    IMS IR.92 EN-DC test cases
    Test coverage enhancement for L1 configurations.
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable LTE xCC + NR FR1/FR2 yCC test cases, where x <= 4, y <=2
  UE test functions - TS 38.509
    TBD if any additional UE test functions needed
NOT INCLUDED:
  MU/TT part of LTE+NR FR2 Demod/CSI reporting (TS 38.521-4), Note 4
  MU/TT part of LTE+NR FR2 RRM (TS 38.533), Note 4
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#89 (May-19)
Note 3: MU part of RF MU/TT target 3 test cases are planned to be completed by RAN5#83 (May 19) and TT part by RAN5#84 (Aug-19). The TT part need thus to be completed after NSA Opt.3 Phase 3. Note 4: There will be a need for a NSA Opt.3 Phase 4 to be added when MU/TT targets for Demod/CSI and RRM test cases becomes available.
Note 5: For protocol test cases it is assumed that EN-DC configurations beyond LTE 1CC + NR FR1/FR2 2CC are implicitly tested by the RF test cases.

## Slide 12
TARGETED TO BE INCLUDED:
  SC FR1 and FR2
  RF - TS 38.521-1, TS 38.521-2, TR 38.903, TR 38.905
    Test definition, MU and TT for all NR FR1 Rx and Tx test cases (including UL MIMO, SUL), Note 1
    Test definition, MU and TT for NR FR2 RF MU/TT Target 1 and Target 2 test cases (including UL MIMO),, Note 2
  Protocol - TS 38.523-x
    Basic NR SA Layer 2 including SDAP, Idle Mode and RRC test cases, Note 3
    Basic NAS 5GC test cases, Note 3
  Test environment - TS 38.508-1, TS 38.508-2
    Common test environment to enable NR FR1 and FR2 testing
  UE test functions - TS 38.509
    UE test loop mode A and UE test loop mode B for SA NR
    UBF, SS-RSRPB UE reporting, UE Positioning test functions, SDAP test loop
NOT INCLUDED:
  RF MU/TT for RF MU/TT Target 3 test cases (TS 38.521-3)
  No NR FR1 or FR2 Demod/CSI reporting (TS 38.521-4)
  No NR FR1 or FR2 RRM (TS 38.533)
Note 1: Dependency: RAN4 progress until RAN4#89 (Nov-18)
Note 2: Dependency: RAN4 progress until RAN4#89 (Nov-18) + RAN5 RF MU/TT progress. For RF MU/TT target 1 and 2 test cases MU is planned to be completed by RAN5#NR3 (Oct-18) and TT is targeted to be completed by RAN5#81 (Nov-18) (Ref R5-183257)
Note 3: Dependency: RAN2/CT1 progress until RAN2#104 & CT1#113 (Nov-18)
SA Option 2 (SA NR) Phase 1 content
- Target RAN5#81 Nov-18

## Slide 13
SA Option 2 (SA NR) Phase 2 content
- Target RAN5#83 MAY-19
TARGETED TO BE INCLUDED:
  SC FR1 and FR2 + CA configurations and Synchronous NR-NR DC for FR1 xCC,FR2 xCC, (FR1+FR2) xCC:, where x<=4
  RF - TS 38.521-1, TS 38.521-2, TS 38.521-3 (FR1+FR2), TS 38.521-4, TS 38.533, TR 38.903, TR 38.905
    Test definition and MU/TT for NR FR2 Rx and Tx RF MU/TT target 3 test cases where MU/TT analysis completed (including UL MIMO), Note 2
    Test definition and MU/TT for NR FR1 Demod/CSI reporting (TS 38.521-4), Note 1
    Test definition and MU/TT for NR FR1 RRM (TS 38.533) test definition and TT, Note 1
    Test definition for NR FR2 Demod/CSI reporting (TS 38.521-4), Note 1
    Test definition for NR FR2 RRM (TS 38.533), Note 1
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    For CA / DC protocol testing it is assumed that max 2CC need to be covered.
    Enhanced test coverage for NR SA Layer 2 including SDAP, idle mode and RRC test cases, Note 3
    Synchronous NR-NR DC and SUL
    Inter-RAT to/from LTE
    SA NR positioning test cases
    5GS IMS, Note 4
  Test environment - TS 38.508-1, TS 38.508-2
    Common test environment to enable to enable NR FR1/FR2/FR1+FR2 CA configurations
  UE test functions - TS 38.509
    TBD if any additional UE test functions needed
NOT INCLUDED:
  MU/TT part of NR FR2 Demod/CSI reporting (TS 38.521-4), Note 2
  MU/TT part of NR FR2 RRM (TS 38.533), Note 2
Note 1: Dependency: RAN4 progress until RAN4#91 (May-19)
Note 2: Dependency: RAN4 progress until RAN4#91 (May-19) + RAN5 RF MU/TT progress. For RF MU/TT target 3 test cases MU is planned to be completed by RAN5#81 (Dec-18) and TT is targeted to be completed by RAN5#NR4 (Jan-19) (Ref R5-183257)
Note 3: There will be a need for a SA Opt.2 Phase 3 to be added when MU/TT targets for Demod/CSI and RRM test cases becomes available.
Note 4: Dependency: RAN2/CT1 progress until RAN2#106 & CT1#115 (May-19)

## Slide 14: REFERENCE slides
RAN5#79 (May-18) MU/TT targets

## Slide 15
FR2 MU/TT timeplan (RAN5#79)
At RAN5#79 RAN5 endorsed the following updated MU/TT targets as Best Effort (Ref:R5-183257)
  RF MU/TT Target 1: [MU] RAN5#NR3 (Oct-18) [TT] RAN5#81 (Nov-18,-2m)
  RF MU/TT Target 2: [MU] RAN5#NR3 (Oct-18,-4m) [TT] RAN5#81 (Nov-18, -6m)
  RF MU/TT Target 3: [MU] RAN5#81 (Nov-18, -6m) [TT] RAN5#84 (Jan-19, -7m)
  , where “-xm“ indicates a move of a target by x months compared to previous targets in R5-182092
RF MU/TT Target 1 test cases (regulatory):
  Max Output Power
  Ref Sensitivity
RF MU/TT Target 2 test cases (regulatory):
  Transmit OFF power
  Occupied bandwidth
  Adjacent Channel Leakage Ratio
  Spurious emissions for UE co-existence
  Spectrum emission mask
  General spurious emissions
  Receiver Spurious emissions
RF MU/TT Target 3 test cases: all other test cases
No Change at RAN5#80