## Slide 1: RAN5 5G NR STATUS, DELIVERY phases and targets (November-18)
3GPP TSG-RAN5#81 R5-186822
Spokane, US, 12th - 16th Nov 2018

## Slide 2: Introduction & CONTENT
The purpose of this document is to give high level status of RAN5 completed 5GS test cases and the targets for the next RAN5 5GS delivery phases.
Content
Definitions of RAN5 5GS delivery phases and targets
Status completed deliveries
Planning for next deliveries

## Slide 3
Definitions of RAN5 5GS delivery phases and targets
RAN5#79 May-18
  NSA Option 3 (EN-DC) Phase 1
RAN5#80 Aug-18
  NSA Option 3 (EN-DC) Phase 1.5
RAN5#81 Nov-18
  NSA Option 3 (EN-DC) Phase 2
  SA Option 2 (SA NR) Phase 1
RAN5#82 Feb-19
  NSA Option 3 (EN-DC) Phase 3 (new)
  SA Option 2 (SA NR) Phase 2 (new)
RAN5#83 May-19
  NSA Option 3 (EN-DC) Phase 4 (former 3)
  SA Option 2 (SA NR) Phase 3 (former 2)
  SA Option 5 (SA E-UTRA) Phase 1
  NSA Option 7 (NGEN-DC) Phase 1
  NSA Option 4 (NE-DC) Phase 1
RAN5#84 Aug-19 and beyond: FFS

## Slide 4
Definitions of RAN5 5GS delivery phases and targets
RF MU/TT Priority 1 test cases (regulatory):
  Max Output Power
  Ref Sensitivity
RF MU/TT Priority 2 test cases (regulatory):
  Transmit OFF power
  Occupied bandwidth
  Adjacent Channel Leakage Ratio
  Spurious emissions for UE co-existence
  Spectrum emission mask
  General spurious emissions
  Receiver Spurious emissions
RF MU/TT Priority 3 test cases: all other test cases
  The RAN5 targets for completing FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) are (Updated at RAN5-81)

## Slide 5: Definitions of RAN5 5GS delivery phases and targets
Overview: Time line - RAN5 5G NR deliveries and targets

## Slide 6: Status of completed deliveries
Overview of completed test cases by RAN5#81 (Nov-18)
  See attached document “5GS WP complete test cases v4.1” for details

## Slide 7
NSA Option 3 (EN-DC)
  RAN5 completed NSA Option 3 Phase 2 at RAN5#81 (Nov-18)
    INCLUDED:
    EN-DC configurations: LTE 1xCC + NR FR1 1CC
    New completed test cases
      20 new RF FR1 (5 Rx and 15 Tx) test cases
      10 first positioning protocol test cases
      2 new MAC test cases
      3 new RRC test cases
  See attached document “5GS WP complete test cases v4.1” for list of all completed NSA Option 3 test cases (including delivery Phases 1, 1.5 and 2)
  History:
    Phase 1 completed at RAN#79 (May-18)
    Phase 1.5 completed at RAN5#80 (Aug-18)
Status of completed deliveries

## Slide 8
SA Option 2 (SA NR)
  RAN5 completed NSA Option 2 Phase 1 at RAN5#81 (Nov-18)
    INCLUDED:
    Test environment
      Enhanced to support 5GC
      Various generic procedures introduced facilitating the overall test cases development
      Current version limited to one network slice/one PDU session/one default DRB and 5G-AKA authentication method (to be enhanced in next delivery)
    RF:
      13 RF FR1 (10 Tx and 3 Rx) single carrier test cases
    Protocol:
      2 Idle Mode test cases
      70 layer 2 test cases (38 MAC, 17 RLC, 14 PDCP and 1 SDAP; some test cases were introduced for NSA Option 3, but are applicable to SA Option 2 as well)
      2 RRC test cases
      5 5GC NAS test cases
  See attached document “5GS WP complete test cases v4.1” for the list of all completed SA Option 2 test cases
Status of completed deliveries

## Slide 9
General considerations & Definitions
The RF, Demod/CSI reporting and RRM test cases can be divided into the following parts
  Test definition Test case description excluding MU (FR2) and TT (FR1 and FR2) part(s) i.e. non MU/TT parts of minimum requirements, Initial conditions, Test points, Test procedure, Specific message content etc.
  MU Measurement Uncertainty
  TT Test Tolerances
  Complete FR1 test case Test definition + MU + TT
  Complete FR2 test case Test definition + MU + TT
NOTE!
  The completion targets for EN-DC FR2 test cases are set based on the RAN5 MU/TT targets as described in R5-183257.
  Until the MU/TT becomes available it is important that the parts of test definition of the FR2 test cases that are NOT dependent on MU/TT are progressed as far as possible.
Planning for next deliveries

## Slide 10
Planning for next deliveries:
NSA Option 3 (EN-DC) - Phase 3 content - Target RAN5#82 FEB-19
TARGETED TO BE INCLUDED:
  EN-DC configurations: LTE xCC + NR FR1/FR2 yCC, where x <= 3, y <=2
  RF - TS 38.521-3, TS 38.522, TS 38.521-1 (Note 1), TS 38.521-2 (Note 1), TS 38.521-4, TS 38.533, TR 38.903, TR 38.905
    Test definition, MU and TT for LTE+NR FR1: Rx and Tx test cases not completed in NSA Opt.3 Phase 2, Note 2
    Test definition, MU and TT for LTE+NR FR2 RF MU/TT Target 1, Target 2 test cases not completed in NSA Opt.3 Phase 2, Note 3
    Test definition and MU for LTE+NR FR2 RF MU/TT Target 3 test cases not completed in NSA Opt.3 Phase 2, Note 4
    Test definitions for LTE+NR FR1 and FR2 Demod/CSI reporting (TS 38.521-4) and RRM (TS 38.533), Note 2
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Remaining test cases not completed in NSA Opt.3 Phase 2
    LTE 1CC + NR FR1 1CC and LTE 1CC + NR FR2 1CC test cases not completed in NSA Opt.3 Phase 2
    LTE 1CC + NR FR1/FR2 2CC test cases, Note 5
    Enhanced test coverage for L1 configurations based on industry interest
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable LTE xCC + NR FR1/FR2 yCC test cases, where x <= 3, y <=2
NOT INCLUDED:
  MU/TT part of LTE+NR FR2 Demod/CSI reporting (TS 38.521-4), Note 3
  MU/TT part of LTE+NR FR2 RRM (TS 38.533), Note 3
  IMS test cases (TS 34.229-x)
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#88 (Feb-19)
Note 3: Dependency: RAN4 progress until RAN4#89 (Nov-18) + RAN5 RF MU/TT progress. For RF MU/TT target 1 and target 2 test cases MU is planned to be completed by RAN5#4-NR-Adhoc (Jan-19) and TT is targeted to be completed by RAN5#82 (Feb-19)
Note 4: MU part of RF MU/TT target 3 test cases are planned to be completed by RAN5#82 (Feb-19) and TT part by RAN5#5-NR-Adhoc (Apr-19). The TT part need thus to be completed after NSA Opt.3 Phase 3.
Note 5: For protocol test cases it is assumed that EN-DC configurations beyond LTE 1CC + NR FR1/FR2 2CC are implicitly tested by the RF test cases.

## Slide 11
Planning for next deliveries:
NSA Option 3 (EN-DC) - Phase 4 content - Target RAN5#83 MAY-19
TARGETED TO BE INCLUDED:
  EN-DC configurations: LTE xCC + NR FR1/FR2 yCC, where x <= 4, y <=2
  RF - TS 38.521-3, TS 38.522, TS 38.521-1 (Note 1), TS 38.521-2 (Note 1), TS 38.521-4, TS 38.533, TR 38.903, TR 38.905
    TT part for RF MU/TT Target 3 test cases (TS 38-521-3), Note 3
    Test definition, MU and TT for LTE+NR FR2 RF MU/TT Target 3 test cases not completed in NSA Opt.3 Phase 3, Note 2
    Test definition and TT for LTE+NR FR1 Demod/CSI reporting (TS 38.521-4) and RRM (TS 38.533) not completed in Phase 3, Note 2
    Test definition for LTE+NR FR2 Demod/CSI reporting (TS 38.521-4) and RRM (TS 38.533) not completed in Phase 3, Note 2
    Positioning performance
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    Remaining test cases not completed in NSA Opt.3 Phase 3
    IMS IR.92 EN-DC test cases, Note 5
    Test coverage enhancement for L1 configurations.
  Test environment - TS 36.508, TS 38.508-1, TS 38.508-2
    Common test environment to enable LTE xCC + NR FR1/FR2 yCC test cases, where x <= 4, y <=2
NOT INCLUDED:
  MU/TT part of LTE+NR FR2 Demod/CSI reporting (TS 38.521-4), Note 4
  MU/TT part of LTE+NR FR2 RRM (TS 38.533), Note 4
Note 1: The TS 38.521-3 referenced clauses in TS 38.521-1 and TS 38.521-2 need to be completed as part of the TS 38.521-3 target.
Note 2: Dependency: RAN4 progress until RAN4#89 (May-19)
Note 3: MU part of RF MU/TT target 3 test cases are planned to be completed by RAN5#82 (Feb-19) and TT part by RAN5#5-NR-Adhoc (Apr-19). The TT part need thus to be completed after NSA Opt.3 Phase 3. Note 4: There will be a need for a NSA Opt.3 Phase 5 to be added when MU/TT targets for Demod/CSI and RRM test cases becomes available.
Note 5: IMS EN-DC depends on availability of GSMA update of IR.92/IR.94 for EN-DC.

## Slide 12
Planning for next deliveries:
SA Option 2 (SA NR) - Phase 2 content- Target RAN5#82 Feb-19
TARGETED TO BE INCLUDED:
  CA configurations for FR1 xCC, where x<=4
  RF - TS 38.521-1, TR 38.905, TS 38.521-4, TS 38.533
    Test definition, MU and TT for all NR FR1 CA Rx and Tx test cases (including SUL)
    Test definition and MU for NR FR2 Rx and Tx RF MU/TT target 3 test cases where MU/TT analysis completed (including UL MIMO), Note 3
    Test definition and TT for NR FR1 Demod/CSI reporting (TS 38.521-4), Note 2
    Test definition and TT for NR FR1 RRM (TS 38.533), Note 2
  Protocol - TS 38.523-x, TS 34.229-x
    For CA protocol testing it is assumed that max 2CC need to be covered.
    Enhanced test coverage for NR SA Layer 2 including SDAP, idle mode, RRC test cases, 5GC, Note 1
    SUL
    Inter-RAT to/from LTE (reselection, handover and redirection)
    5GS IMS (EPS Fallback), Note 1
  Test environment - TS 38.508-1, TS 38.508-2
    Common test environment to enable NR FR1 CA configurations & IMS registration
NOT INCLUDED:
  SA NR positioning test cases
  Synchronous NR-NR DC
Note 1: Dependency: RAN2/CT1 progress until RAN2#105 & CT1#114 (Feb-19)
Note 2: Dependency: Limited to “RAN4 Phase I” described in RP-182149 and RAN4 progress until RAN4#88-Bis (Oct-18)
Note 3: Dependency: RAN4 progress until RAN4#91 (Feb-19) + RAN5 RF MU/TT progress. For RF MU/TT target 3 test cases MU is planned to be completed by RAN5#82 (Feb-19) and TT is targeted to be completed by RAN5#5-NR-Adhoc (Apr-19).

## Slide 13
Planning for next deliveries:
SA Option 2 (SA NR) - Phase 3 content - Target RAN5#83 MAY-19
TARGETED TO BE INCLUDED:
  SC FR2 + CA configurations and Synchronous NR-NR DC for FR1 xCC,FR2 xCC, (FR1+FR2) xCC:, where x<=4
  RF - TS 38.521-1, TS 38.521-2, TS 38.521-3 (FR1+FR2), TS 38.521-4, TS 38.533, TR 38.903, TR 38.905
    Test definition and MU/TT for NR FR2 Rx and Tx RF MU/TT target 3 test cases not completed in Phase 2, Note 2
    Test definition and TT for NR FR1 Demod/CSI reporting not completed in Phase 2 (TS 38.521-4), Note 1
    Test definition and TT for NR FR1 RRM not completed in Phase 2 (TS 38.533), Note 1
    Test definition for NR FR2 Demod/CSI reporting (TS 38.521-4), Note 1
    Test definition for NR FR2 RRM (TS 38.533), Note 1
  Protocol - TS 38.523-x, TS 34.229-x, TS 37.571-x
    For DC protocol testing it is assumed that max 2CC need to be covered.
    Synchronous NR-NR DC and SUL
    SA NR positioning test cases
    5GS IMS, Note 4
  Test environment - TS 38.508-1, TS 38.508-2
    Common test environment to enable to enable NR FR1/FR2/FR1+FR2 CA configurations
NOT INCLUDED:
  MU/TT part of NR FR2 Demod/CSI reporting (TS 38.521-4), Note 2
  MU/TT part of NR FR2 RRM (TS 38.533), Note 2
Note 1: Dependency: RAN4 progress until RAN4#91 (May-19)
Note 2: Dependency: RAN4 progress until RAN4#91 (May-19) + RAN5 RF MU/TT progress. For RF MU/TT target 3 test cases MU is planned to be completed by RAN5#81 (Dec-18) and TT is targeted to be completed by RAN5#NR4 (Jan-19)
Note 3: There will be a need for a SA Opt.2 Phase 43 to be added when MU/TT targets for Demod/CSI and RRM test cases becomes available.
Note 4: Dependency: RAN2/CT1 progress until RAN2#106 & CT1#115 (May-19) and availability of GSMA profile for 5GS IMS

## Slide 14
Content: FFS
Question raised by RAN5: Can RAN5 assume that a UE supporting SA Option 5 will also support SA Option 2?
  One UE vendor and two operators have indicated in GCF that RAN5 cannot assume that a UE supporting SA Option 5 will also support SA Option 2.
   This indicates that RAN5 should NOT make such assumption
Planning for next deliveries:
SA Option 5 (SA E-UTRA) - Phase 1 content - Target RAN5#83 May-19

## Slide 15
Content: FFS
Planning for next deliveries:
NSA Options 4 & 7 (NE-DC & NGEN-DC) - Phase 1 content - Target RAN5#83 May-19