## Slide 1: RAN5 5G NR STATUS, DELIVERY phases and targets (NOV-19)
3GPP TSG-RAN5#85 R5-197892
Reno, Nevada, USA, 18 – 22 Nov, 2019

## Slide 2: Introduction & CONTENT
The purpose of this document is to give high level status of RAN5 completed 5GS test cases and the targets for the next RAN5 5GS delivery phases.
Content
Definitions of RAN5 5GS delivery phases and target dates
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) targets
Progress - Completed deliveries
Planning content for next deliveries
  NSA Option 3 (EN-DC)
  SA Option 2 (SA NR)
  SA Option 5, NSA Option 4 (NE-DC), NSA Option 7 (NGEN-DC)

## Slide 3: Definitions of RAN5 5GS delivery phases and target dates
Overview: Time line - RAN5 5G NR deliveries versus RAN5 meeting
  NSA Option 3 Phase 6 and SA Option 2 Phase 5 was completed at RAN5#85
  Based on the feedback on an anonymous MNO poll at RAN5#84 the RAN5 plan for deployment plans options 4, 5 and 7 and on NR-DC is:
    Start of option 4, 5 and 7 at RAN5#87 (Work plans RAN5#86, completion RAN5#89)
    NR-DC completion for SA Option 2 planned at RAN5#88

## Slide 4: DETAILS Option 4, 5, 7 PLAN
Task | Target
Re-confirming MNO earliest date for conformance test cases to support deployments | Jan-20 (send out request by Dec-19)
Complete impacted work plans for options 4, 5 and 7 | RAN5#86 (Feb-20)
Intermediate delivery of test cases and common test environment for option 4,5 and 7 | RAN5#87 (May-20) & RAN5#88 (Aug-20)
Complete option 4, 5 and 7 conformance tests | RAN5#89 (Nov-20)
It is recommended to request a re-confirmation from MNOs before the RAN5 start the work considering the high impact (especially for signaling/TTCN aspects).

## Slide 5: DETAIL NR-DC PLAN
Task | Target
Complete impacted RF/SIG work plans for synchronous NR-DC including assignment of WP TCs/Tasks | RAN5#85 (Nov-19)
Complete RRM work plan for synchronous NR-DC including assignment of WP TCs/Tasks | RAN5#86 (Feb-20)
Complete synchronous NR-DC FR1-FR2 RF/SIG test cases | RAN5#87 (May-20)
Complete synchronous NR-DC FR1-FR2 RRM test cases | RAN5#88 (Aug-20)
MNO: Mid-20, FR1-FR1 & FR1-FR2
RAN4 completion target for NR-DC RRM (TS 38.133) for NR-DC is Feb-20 (core is completed)
Out of scope of RAN5 5G/NR WI:
  NR-DC Demodulation and CSI reporting (introduced in RAN4 under a separate Rel-16 WI (NR_perf_enh)
  FR1-FR1 (no NR-DC FR1-FR1 configurations included in TS 38.101-1)
 RAN5 5G/NR WI scope: Synchronous NR-DC for FR1-FR2,

## Slide 6
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) Target Completion Update (R5-199584)
RF MU/TT Priority 1 test cases (regulatory):
  Max Output Power (complete for EIRP/TRP)
  Ref Sensitivity (complete)
RF MU/TT Priority 2 test cases (regulatory):
  Transmit OFF power
  Occupied bandwidth
  Adjacent Channel Leakage Ratio
  Spurious emissions for UE co-existence
  Spectrum emission mask (complete)
  General spurious emissions
  Receiver Spurious emissions (not testable at this time)
RF MU/TT Priority 3 test cases: all other test cases
  The RAN5 targets for completing FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) (Updated at RAN5-85)

## Slide 7: Progress - Completed deliveries
SA Option 2 Phase 5 and NSA Option 3 Phase 6 were completed at RAN5#85
  For additional details of progress for different areas see R5-197890
Completed test cases:
  For details see attached document “5GS WP complete test cases v8.0” for details

## Slide 8
Planning for next deliveries:
NSA Option 3 (EN-DC) - Phase 7 content - Target RAN5#86 FEB-20
EN-DC configurations: LTE xCC + NR FR1/FR2 yCC, where x <= 4, y <=2
Test case completion targets
  RF EN-DC test cases (38.521-3), Note 1
    Define Wgap for EN-DC intra-band contiguous test cases & Complete the test cases
    Update and align test config and test procedure definitions for pending EN-DC FR1 and FR2 tests with >=2 NR CCs.
  Demodulation and CSI reporting (38.521-4):
    Complete MU analysis for FR2 Demod and CSI test cases
  RRM (38.533):
    Not completed LTE+NR FR1 test cases
    FR2 test cases where RAN4 requirements and MU/TT completed by Feb-20.
  Protocol
    Complete test cases for EN-DC FR2 Band Combinations
    Complete test case for failure information
    Resolve FR2 Measurement interference issues and FR2 Power levels in test cases
    IMS IR.92 EN-DC test cases, Note 2
Other targets
  Common test environment (TS 38.508-1)
    E-UTRA + NR CA 2CC test frequencies with two bands (NR CA 2CC Intra-band contiguous or non-contiguous) for protocol testing.
    Add test frequencies for additional EN-DC configurations
Note 1: EN-DC FR2 test progress dependent on MU/TT analysis completion and other open items impacting SA FR2 tests. See slide 6.
Note 2: The need for EN-DC IMS test cases on top of the existing E-UTRA IMS test cases depends on if GSMA adds any additional EN-DC specific requirements in IR.92 v13.0 and/or IR.94 v14.0 for EN-DC.

## Slide 9
SC FR1+ SC FR2 + NR CA configurations for FR1 xCC,FR2 xCC, (FR1+FR2) xCC:, where x<=4 for FR1 and x<=8 for FR2
Test case completion targets
  RF FR1 (38.521-1):
    Not completed RF FR1 test cases for UL-MIMO and CA (Especially 2DL and 3DL CA Rx test cases)
    RF FR1 test cases for SUL
  RF FR2 (38.521-2):(Single carrier only)
    Not completed RF FR2 priority 1 and 2 test cases including Beam Correspondence, Transmit OFF power, OBW, ACLR, General Spurious, Spurious co-existence and Rx Spurious. Note 1.
    Not completed RF FR2 priority 3 test cases including MU/TT (TS 38.521-3)
  Demodulation and CSI reporting (38.521-4):
    Complete MU analysis for FR2 Demod and CSI test cases. See Note 1.
  RRM (38.533): Note 1
    Completed remaining FR1 test cases
    FR2 test cases where RAN4 requirements and MU/TT completed by Feb-20. See Note 1.
  Protocol test cases (38.523-1, 37.571-2):
    RRC: Complete remaining test cases (Deprioritization, processing delay, Failure scenario, CA FR2 Band Combinations)
    RRC: Resolve interference issues in FR1 measurement Intra-Freq test cases and complete FR2 power levels
    Idle mode: Resolve and update FR1 and FR2 power levels; and complete remaining test cases
    Multilayer/Services: Complete remaining IMS Emergency services and UAC test cases; and resolve FR2 power levels.
  Other targets
    Progress of synchronous NR-DC RF and protocol test cases (target completion RAN5#87, May-20)
    Common test environment (TS 38.508-1)
      Complete generic test procedure for synchronous NR-DC
      NR Intra-band Contiguous and Non-Contiguous CA test frequencies for protocol testing
      Add test frequencies for additional NR CA and NR DC configurations
    Submit TS 34.229-5 on IMS over 5GS for RAN one-step-approval
Note 1: RF/Demod/RRM FR1 priority 1 test cases are test cases with only RAN5 dependencies, i.e. completed in RAN4 by March-19. RF/Demod/RRM FR1 priority 2 test cases are test cases not completed in RAN4 by March-19 (RF/Demod/RRM priorities as agreed at RAN5#82, ref: R5-192832).
Note 2: See slide 6 for MU/TT targets and definition of RF FR2 priority 1, 2 and 3 test cases.
Planned content:
SA Option 2 (SA NR) - Phase 6 - Target RAN5#86 FEB-20

## Slide 10
See slide 5 for further details
Planned content:
SA Option 5 (SA E-UTRA) - Phase 1 - Target RAN5#87 (May-20)

## Slide 11
See slide 5 for further details
Planned content:
NSA Option 4 & 7 (NE-DC & NGEN-DC) - Phase 1 - Target RAN5#87 (May-20)