## Slide 1: Demod/CSI reporting Performance - RAN5#86-e (Feb-20) EN-DC (Option 3)
Progress - Current WP completion at 90%
  FR1
    CRs with Critical corrections/updates impacting already GCF/PTCRB validated test cases were agreed in this meeting.
    7 more FR1 test cases are now 100% complete
    Target for remaining FR1 test cases moved to RAN5#87
  FR2
    1 new FR2 SDR test case was introduced in this meeting.
    The isolation procedure for FR2 UE direction search was added to Annex H of 38.521-4.
    The baseline MU table consisting of applicable MU elements for mode1 (added noise) and mode 2 (noise free) was endorsed to be included in 38.903. MU values are pending further analysis.
Open issues for RAN5 attention
  MU analysis for FR2 Demod and CSI test cases

## Slide 2: Demod/CSI reporting Performance - RAN5#86-e (Feb-20) SA NR (Option 2)
Progress – Current WP completion at 90%
  For DEMOD and CSI, SA and NSA test cases are combined in the same test case except for SDR test cases. Same status as NSA applies
Open issues for RAN5 attention
  same as NSA