## Slide 1: RAN5 5G NR STATUS, DELIVERY phases and targets (MAY-20)
3GPP TSG-RAN5#87-e R5-201562
Electronic Meeting, 18th – 29th May 2020

## Slide 2: Introduction & CONTENT
The purpose of this document is to give high level status of RAN5 completed 5GS test cases and the targets for the next RAN5 5GS delivery phases.
Content
Definitions of RAN5 5GS delivery phases and target dates
SA Option 5 and NSA Options 4 & 7 Way Forward
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) targets
Progress - Completed deliveries
Planning content for next deliveries
  NSA Option 3 (EN-DC)
  SA Option 2 (SA NR)

## Slide 3: Definitions of RAN5 5GS delivery phases and target dates
Overview: Time line - RAN5 5G NR deliveries versus RAN5 meeting
  NSA Option 3 Phase 8 and SA Option 2 Phase 7 were completed at RAN5#87-e
  SA Option 5 and NSA Options 4 and 7
    See next slide for further details on RAN5#87-e endorsed way forward
    First delivery phase can start at RAN5#89

## Slide 4: SA Option 5 and NSA Options 4 & 7 Way FORWARD
RAN5#87-e endorsed the following way forward (R5-202556) for SA Option 5 (SA E-UTRA/5GC) and NSA Options 4 (NE-DC) and 7 (NGEN-DC)
Work plans & contributions
  1st step: Interested companies to submit discussion paper for overall option 4, 5 and 7 analysis and impact on WP by RAN5#88-e.
    Dependent on impact on current work plans RAN5 may decide to merge option 4, 5 and 7 into existing work plans or introduce as separate work plans.
  2nd step: Detailed work plans for option 4, 5 and 7 developed by interested companies by RAN5#89.
  3rd step: CRs for option 4, 5 and 7 can be submitted to RAN5 after the work plans for option 4, 5 and 7 have been endorsed by RAN5.
Meeting priorities
  SA Option 2 and NSA Option 3 have higher priority @RAN5 meetings than option 4, 5 and 7
Impact on completion of 5GS Rel-15 WI
  In case options 4, 5 and 7 are not completed when NR SA and EN-DC are considered completed, and the activity level is low for options 4, 5 and 7, RAN5 may decide to close the Rel-15 5GS work item and leave remaining parts for options 4, 5 and 7 for TEI (with CRs using WI code “TEI15_test, 5GS_NR_LTE-UEConTest” and using dedicated agend

## Slide 5
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) Target Completion Update (R5--201782)

## Slide 6: Progress - Completed deliveries
SA Option 2 Phase 7 and NSA Option 3 Phase 8 were completed at RAN5#87-e
  For additional details of progress for different areas see R5-201559
Completed test cases:
  For details see attached document “5GS WP complete test cases v10.0” for details
  Completion vs FR1, FR2 and configurations with FR1 and FR2 (FR1+FR2)

## Slide 7
Planning for next deliveries:
NSA Option 3 (EN-DC) - Phase 9 content - Target RAN5#88-e Aug-20
EN-DC configurations: LTE xCC + NR FR1/FR2 yCC, where x <= 4, y <=2
Test case completion targets
  RF EN-DC test cases (38.521-3):
    Complete remaining EN-DC FR1 (anchor-agnostic) and FR2 tests with >=2 NR CCs
  Demodulation and CSI reporting (38.521-4):
    Complete remaining FR1 test cases
    Complete MU analysis for FR2 Demod and CSI test cases
  RRM (38.533):
    Complete remaining FR1 test cases
    Complete FR2 test cases where RAN4 requirements and MU/TT completed by Aug-20.
  Protocol (34.229-5, 38.523-1):
    Layer 2: Complete remaining MAC test case (1 FR1, 2 FR2)
    RRC: Complete remaining EN-DC test cases with NR single carrier (6 FR2), with NR CA (7 FR1, 8 FR2, 3 FR1+FR2)
Other targets
  Common test environment (TS 38.508-1)
    Complete common radio conditions OTA testing (chapter 4)
    Complete common test equipment requirements for conducted and OTA tests (clause 6)
    Complete test equipment requirements and signal levels for Performance (chapter 5), Protocol (chapter 6) and RRM (chapter 7)
    Complete cell configurations in clause 6.3.1
  IMS:
    Discussion paper on impact of IR.92 V13.0 and need on additional EN-DC IMS test cases on on top of the existing E-UTRA IMS test cases .

## Slide 8
SC FR1+ SC FR2 + NR CA configurations for FR1 xCC, FR2 xCC, (FR1+FR2) xCC, where x<=4 for FR1 and x<=8 for FR2
Test case completion targets
  RF FR1 (38.521-1):
    Complete remaining FR1 test cases
  RF FR2 (38.521-2):
    Complete remaining single carrier test cases (CA test cases targeted for RAN5#89-e, Nov-20)
  RF FR2 (38.521-3):
    Complete chapter 5 for FR1+FR2
  Demodulation and CSI reporting (38.521-4):
    Complete MU analysis for FR2 Demod and CSI test cases.
  RRM (38.533):
    Complete remaining FR1 test cases
    Complete FR2 test cases where RAN4 requirements and MU/TT completed by Aug-20.
  Protocol test cases (34.229-5, 38.523-1):
    Layer 2: Complete remaining single carrier MAC (2 FR1, 2 FR2) and PDCP (1 FR1, 1 FR2) test cases; and NR-DC MAC (2) and PDCP (2) test cases.
    RRC: Complete remaining NR single carrier (12 FR1, 34 FR2), NR CA (12 FR1, 19 FR2, 24 FR1+FR2) and NR-DC (17 FR1+FR2) test cases
    Idle mode: Resolve FR2 power levels (35 test cases)
    Multilayer/Services: Complete remaining IMS Emergency services (1) and UAC (1) test cases. 2 UAC and 2 IMS emergency new tests need final confirmation for availability of IMS relevant generic procedures.
    IMS: Complete 10-15 IMS test cases.
  Other targets
    Common test environment (TS 38.508-1)
      Complete common test equipment requirements for conducted and OTA tests (clause 6)
      Complete test equipment requirements and signal levels for Performance (chapter 5), Protocol (chapter 6) and RRM (chapter 7)
      Complete cell configurations in clause 6.3.1
    IMS:
      Dependencies of EPS fallback test cases on IMS over 5GS to be clarified
      GSMA profile NG.114 still in draft stage (no update since June 2019)
Planned content:
SA Option 2 (SA NR) - Phase 8 - Target RAN5#88-e AUG-20