## Slide 1: RAN5 5G NR STATUS, DELIVERY phases and targets (AUGUST-20)
3GPP TSG-RAN5#88-e R5-203627
Electronic Meeting, 17th – 28th August 2020

## Slide 2: Introduction & CONTENT
The purpose of this document is to give high level status of RAN5 completed 5GS test cases and the targets for the next RAN5 5GS delivery phases.
Content
Definitions of RAN5 5GS delivery phases and target dates
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) targets
Progress - Completed deliveries
Planning content for next deliveries
  NSA Option 3 (EN-DC)
  SA Option 2 (SA NR)

## Slide 3: Definitions of RAN5 5GS delivery phases and target dates
Overview: Timeline - RAN5 5G NR deliveries versus RAN5 meeting
  NSA Option 3 Phase 9 and SA Option 2 Phase 8 were completed at RAN5#88-e
  SA Option 5 and NSA Options 4 and 7
    At RAN5#87-e a way forward was endorsed by RAN5 in R5-202556. The first step of the way forward was for interested companies to submit discussion paper for overall option 4, 5 and 7 analysis and impact on WP by RAN5#88-e.
    As there was no input submitted to RAN5#88-e then the current work plan targets will be limited to SA option 2 and NSA option 3. SA option 5 and NSA Options 4 and 7 are FFS.

## Slide 4
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) Target Completion Update (R5-203771)

## Slide 5: Progress - Completed deliveries
SA Option 2 Phase 8 and NSA Option 3 Phase 9 were completed at RAN5#88-e
  For additional details of progress for different areas see R5-203626
Completed test cases:
  Completion vs FR1, FR2 and configurations with FR1 and FR2 (FR1+FR2)
  For details see attached document “5GS WP complete test cases v11.0” for details

## Slide 6
Planning for next deliveries:
NSA Option 3 (EN-DC) - Phase 10 content - Target RAN5#89-e NOV-20
EN-DC configurations: LTE xCC + NR FR1/FR2 yCC, where x <= 4, y <=2
Test case completion targets
  FR1 RF/Performance/RRM
    Complete remaining EN-DC FR1 (anchor-agnostic) test cases (38.521-3).
    Complete remaining FR1 RRM test cases (38.533).
  FR2 RF/Performance/RRM
    All FR2 test cases will not be feasible to complete by RAN5#89-e.
    Progress remaining FR2 test cases (38.521-3).
      EN-DC FR2 test progress dependent on MU/TT analysis completion and other open items impacting SA FR2 tests (38.521-4).
    Progress FR2 RRM test cases where RAN4 requirements and MU/TT completed by Nov-20 (38.533).
  Protocol (34.229-5, 38.523-1):
    RRC: Complete remaining EN-DC test cases with NR single carrier (4 FR2), with NR 2CC CA (3 FR1, 8 FR2, 4 FR1+FR2).
Other targets
  Common test environment (TS 38.508-1):
    If further details needed for OTA test equipment requirements (clause 4 and 6); signal levels for Performance (chapter 5), Protocol (chapter 6) and RRM (chapter 7); and cell configurations (clause 6.3.1). If no further details needed, then will editor’s notes be removed.

## Slide 7
SC FR1; SC FR2; NR CA configurations for FR1 xCC, FR2 xCC, (FR1+FR2) xCC, where x<=4 for FR1 and x<=8 for FR2; and NR DC configurations xFR1CC+xFR2FR2, where xFR1 =1 and xFR1 <=8 or xFR1 =2 and xFR1 <=4
Test case completion targets
  FR1 RF/Performance/RRM
    Complete remaining FR1 test cases (38.521-1).
    Complete remaining FR1 RRM test cases (38.533).
  FR2 RF/Performance/RRM
    All FR2 test cases will not be feasible to complete by RAN5#89-e.
    Progress remaining FR2 RF single carrier and CA test cases (38.521-1).
    Progress test tolerance analysis considering SNR testability issue pending for FR2 Demod and CSI test cases (38.521-4).
    Progress FR2 RRM test cases where RAN4 requirements and MU/TT completed by Nov-20 (38.533).
  Protocol test cases (34.229-5, 38.523-1):
    Layer 2: Complete remaining single carrier MAC (1 FR1, 1 FR2) and PDCP (1 FR1, 1 FR2) test cases.
    Idle mode: Resolve FR2 power levels (35 test cases).
    RRC: Complete remaining NR single carrier (2 FR1, 30 FR2), NR CA (21 FR2, 8 FR1+FR2) and NR-DC (10 FR1+FR2) test cases.
    Multilayer/Services: Complete remaining IMS Emergency services (1) and UAC (2) test cases.
    IMS: Complete IMS test cases (89 test cases remains).
Other targets
  Common test environment (TS 38.508-1)
    If further details needed for OTA test equipment requirements (clause 6); signal levels for Performance (chapter 5), Protocol (chapter 6) and RRM (chapter 7); and cell configurations (clause 6.3.1). If no further details needed, then will editor’s notes be removed.
Planning for next deliveries:
SA Option 2 (SA NR) - Phase 9 - Target RAN5#89-e NOV-20