## Cover sheet
3GPP TSG-RAN WG5 Meeting #90-e | [10 empty] | R5-210697
Electronic Meeting, 22nd February - 5th March 2021
Agenda Item: | 7.4.2
Source: | Huawei, Hisilicon
Title: | WP UE Conformance Test Aspects - Rel-16 NR Mobility Enhancement
Work item code: | NR_Mob_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the work item is to define the UE conformance requirements corresponding to WID on NR R16 Mobility Enhancement with Unique identifier 800087. The RAN5 areas of RRM and Protocol conformance test specifications with NR R16 Mobility Enhancement operation will be covered. At the RAN#88 meeting in June 2020 the Rel-16 RAN5 work item for UE Conformance Test Aspects for NR Mobility Enhancement was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 35% (+22%) | 0 | 12
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 44.3% (+31.4%) | 0 | 9
FR1 |  | 40.4% (+25.1%) | 0 | 9
FR2 |  | 50.9% (+41.9%) | 0 | 5
FR1 + FR2
NSA Option 3 (EN-DC) |  | 14.5% (+3.5%) | 0 | 3
FR1 |  | 14.5% (+3.5%) | 0 | 3
FR2 |  | 14.5% (+3.5%) | 0 | 3
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 60% (+20%) |  |  | 60% (+20%) |  |  | 60% (+20%) | [5 empty] | 60% (+20%) |  |  | 60% (+20%)
Common ICS | 38.508-2 | 60% (+20%) |  |  | 60% (+20%) |  |  | 60% (+20%) | [5 empty] | 60% (+20%) |  |  | 60% (+20%)
NR RF/RRM
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 31.8% (+27.9%) | 0 | 12 | 36.1% (+27.2%) | 0 | 9 | 48% (+48%) | 0 | 5 |  |  |  | 0% | 0 | 3 | 0% | 0 | 3
Applicability Protocol test cases | 38.523-2 | 17.7% (+13.3%) |  |  | 20% (+10%) |  |  | 20% (+20%) | [5 empty] | 10% (+10%) |  |  | 10% (+10%)
Test suites (TTCN) | 38.523-3
5 References
[1] RP-200893 | New WID on UE conformance test aspects for NR mobility enhancements; Huawei, Hisilicon
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - Rel-16 NR Mobility Enhancement | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_Mob_enh-UEConTest
WP Scope: |  | Conformance test specifications for the core requirements of NR R16 Mobility Enhancement. The RAN5 areas of RRM and Protocol conformance test specifications are to be covered | [13 empty] | vs Area
WP Resp: |  | Wu, Yuchun (Huawei) |  |  | wuyuchun@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 40.4% (+25.1%) | 50.9% (+41.9%) |  | 14.5% (+3.5%) | 14.5% (+3.5%)
[15 empty] | 15 | 11 | 0 | 8 | 8 | 0
[15 empty] | 9.8 | 5.8 | 0 | 3.8 | 3.8 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | Update to RRC messages and IEs |  | RAN5#90-e (Feb-21) | R5-206403 R5-210687 R5-210688 R5-210689 R5-211456 |  | 0.5 | 60% (+20%) | 60% (+20%) | 60% (+20%) |  | 60% | 60% |  | 60% | 60%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | A.4.3.8 | Mobility Capabilities | Add UE capability |  | RAN5#90-e (Feb-21) | R5-206404 R5-211457 |  | 0.1 | 60% (+20%) | 60% (+20%) | 60% (+20%) |  | 60% | 60% |  | 60% | 60%
NR RF/RRM
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.101-x and 38.533. |  | TBD |  |  | 0.1
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.533 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.533 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.533 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
Layer 2
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
3 | Y | 38.523-1 | 7.1.3.4.3 | PDCP handover / DAPS handover with key change / Status reporting | **** TP1: [Ref: 38.323, cl.4.2.2, 5.8 and 5.9] WITH: UE in NR RRC_CONNECTED state and supporting DAPS handover WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for DAPS handover with key change THEN: PDCP entity associated with a DAPS bearer shall perform ciphering/deciphering, Integrity protection/verification under two sets of keys **** TP2: [Ref: 38.323, cl.5.4.1] WITH: UE in NR RRC_CONNECTED state and supporting DAPS handover and receiving an RRCReconfiguration message including a reconfigurationWithSync for DAPS handover with key change WHEN: upper layer requests a uplink data switching THEN: UE shall send a PDCP status report for the DAPS bearer **** TP3: [Ref: 38.323, cl.5.4.1] WITH: UE in NR RRC_CONNECTED state and supporting DAPS handover and receiving an RRCReconfiguration message including a reconfigurationWithSync for DAPS handover with key change WHEN: upper layer requests a PDCP entity reconfiguration and the associated RLC entity is released for a radio bearer THEN: UE shall send a PDCP status report for the DAPS bearer |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
RRC
4 |  | 38.523-1 | 8.1.4.3 | DAPS handover | Sub-clause heading |  | RAN5#91-e (May-21) | R5-206405 |  | 0 | 100% | 100% |  |  | 100% | 100%
5 | Y | 38.523-1 | 8.1.4.3.1 | DAPS handover / Success | **** TP1: [TS 38.300 9.2.3.1 and 9.2.3.2.1 and TS 38.331 clause 5.3.5.5.2] WITH: UE in NR RRC_CONNECTED state and supporting DAPS handover WHEN: UE receives an RRCReconfiguration message including a reconfigurationWithSync for handover and dapsConfig is configured for a DRB THEN: UE performs DAPS handover to the target cell and keeps DL/UL reception/transmission with the source gNB for the DRB configured with dapsConfig **** TP2: [TS 38.300 9.2.3.1] WITH: UE in NR RRC_CONNECTED state and supporting DAPS handover and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for any DRB WHEN: UE has performed random access procedure to the target cell successfully THEN: UE transmits an RRCReconfigurationComplete message and switches the uplink user data transmission to the target gNB **** TP3: [TS 38.331 clause 5.3.5.3] WITH: UE in NR RRC_CONNECTED state and supporting DAPS handover and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for any DRB WHEN: UE receives an RRCReconfiguration message including a daps-SourceRelease THEN: UE releases the radio link with the source cell | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-206405 |  | 1 | 85% (+5%) | 85% (+5%) |  |  | 85%
6 | Y | 38.523-1 | 8.1.4.3.2 | DAPS handover / Success / Radio Link Failure in source | **** TP1: [ TS 38.300 9.2.3.1 and 9.2.3.2.1, TS 38.331 clause 5.3.5.5.2, 5.3.5.3.] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for a DRB WHEN: Timer T310 configured by using the value for target's timer T310 expires in source THEN: UE suspends all DRBs in the source and releases the source connection and continue the handover procedure to target **** TP2: [ TS 38.300 9.2.3.1 and 9.2.3.2.1, TS 38.331 clause 5.3.5.5.2, 5.3.5.3.] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for a DRB WHEN: random access problem is indicated from source MCG MAC THEN: UE suspends all DRBs in the source and releases the source connection and continue the handover procedure to target **** TP3: [ TS 38.300 9.2.3.1 and 9.2.3.2.1, TS 38.331 clause 5.3.5.5.2, 5.3.5.3.] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for a DRB WHEN: The maximum number of retransmissions has been reached in source MCG RLC THEN: UE suspends all DRBs in the source and releases the source connection and continue the handover procedure to target | China Telecommunications | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
7 | Y | 38.523-1 | 8.1.4.3.3 | DAPS handover / Failure / source link available / Radio Link Failure in source | **** TP1: [ TS 38.300 9.2.3.1 and 9.2.3.2.1, TS 38.331 clause 5.3.5.8.3, 5.7.5.3 ] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration message including a reconfigurationWithSync for handover to the neighbour cell and a dapsConfig configured for a DRB WHEN: T304 of the MCG expires and the source link has not been released THEN: UE falls back to source cell configuration, resumes the connection with source cell, and reports DAPS HO failure via the source without triggering RRC connection re-establishment **** TP2: [ TS 38.300 clause 9.2.7, TS 38.331 clause 5.3.5.8.3, clause 5.3.7 ] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration with a dapsConfig configured for any DRB and T304 of the MCG expires and radio link failure has occurred in source cell WHEN: UE finds a suitable cell before T311 expires THEN: UE stays in RRC_CONNECTED and selects a suitable cell and then initiates RRC re-establishment **** TP3: [ TS 38.300 clause 9.2.7, TS 38.331 clause 5.3.5.8.3, clause 5.3.7 ] WITH: UE in NR RRC_CONNECTED state and having received an RRCReconfiguration with a dapsConfig configured for any DRB and T304 of the MCG expires and radio link failure has occurred in source cell WHEN: UE can not find a suitable cell before T311 expires THEN: UE enters RRC_IDLE |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
8 |  | 38.523-1 | 8.1.4.4 | Conditional handover | Sub-clause heading |  | RAN5#91-e (May-21) | R5-211458 |  | 0 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
9 | Y | 38.523-1 | 8.1.4.4.1 | Conditional handover / Success / A3 / A5 / A3+A5 | **** TP1: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving an RRCReconfiguration message including ConditionalReconfiguration WHEN: any CHO execution condition is not satisfied THEN: UE maintains connection with source gNB and starts evaluating the CHO execution conditions for the candidate cell(s) **** TP2: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.13.1, 5.3.5.13.4 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover WHEN: UE receives an RRCReconfiguration message including ConditionalReconfiguration and only event A3 is configured as conditional handover trigger event THEN: UE starts evaluating the CHO execution condition A3 and perform conditional handover to the neighbor cell triggered in conditional configuration execution **** TP3: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.13.1, 5.3.5.13.4 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover WHEN: UE receives an RRCReconfiguration message including ConditionalReconfiguration and only event A5 is configured as conditional handover trigger event THEN: UE starts evaluating the CHO execution condition A5 and perform conditional handover to the neighbor cell triggered in conditional configuration execution **** TP4: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.13.1, 5.3.5.13.4 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover WHEN: UE receives an RRCReconfiguration message including ConditionalReconfiguration and both event A3 and event A5 are configured as conditional handover trigger events THEN: UE starts evaluating the CHO execution condition A3 and A5 and perform conditional handover to the neighbor cell triggered in conditional configuration execution **** TP5: [ TS 38.300 clause 9.2.3.4, 9.2.3.4.2 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover WHEN: UE perform conditional handover procedure successfully THEN: UE releases stored CHO configurations | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211458 |  | 1 | 80% (+80%) | 80% (+80%) |  |  | 80% | 80%
10 | Y | 38.523-1 | 8.1.4.4.2 | Conditional handover / modify conditional handover configuration | **** TP1: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.3, 5.3.5.13.3 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE received another RRCReconfiguration message with adding a new entry in the CondReconfigToAddModList before any CHO execution condition is satisfied THEN: UE add the new entry within the VarConditionalReconfig and apply the latest conditional handover configurations **** TP2: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.3, 5.3.5.13.4 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE received another RRCReconfiguration message with modifying an exsisting entry in the CondReconfigToAddModList before any CHO execution condition is satisfied THEN: UE replace the exsisting entry with the value received and apply the latest conditional handover configurations **** TP3: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.5.1, 5.3.5.3, 5.3.5.13.2 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE received another RRCReconfiguration message with condConfigToRemoveList before any CHO execution condition is satisfied THEN: UE removes the entry with the matching condConfigId included in the condConfigToRemoveList and apply the latest conditional handover configurations | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211459 |  | 1 | 80% (+80%) | 80% (+80%) |  |  | 80% | 80%
11 | Y | 38.523-1 | 8.1.4.4.3 | Conditional handover / Failure | **** TP1: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.7.3 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving a RRCReconfiguration message including ConditionalReconfiguration WHEN: UE detects conditional handover failure and finds a selectable cell which is the candidate cell included in ConditionalReconfiguration before T311 expires THEN: UE applies the stored condRRCReconfig associated to the selected cell and perform conditional handover to the selected cell **** TP2: [ TS 38.300 clause 9.2.3.4 and TS 38.331 clause 5.3.7.6, 5.3.11 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving a RRCReconfiguration message including ConditionalReconfiguration WHEN: UE detects conditional handover failure and can not find any selectable cell before T311 expires THEN: UE goes to RRC_IDLE and release the stored conditional handover configurations | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211460 |  | 1 | 80% (+80%) | 80% (+80%) |  |  | 80% | 80%
12 | Y | 38.523-1 | 8.1.4.4.4 | Conditional handover / Handover / Handover Failure | **** TP1: [ TS 38.300 9.2.3.4.1 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover and receiving an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE receiving an RRCReconfiguration message including a reconfigurationWithSync for legacy handover to a neighbour cell THEN: UE performs handover procedure **** TP2: [ TS 38.300 9.2.3.1 and TS 38.331 clause 5.3.7.3] WITH: UE having stored ConditionalReconfiguration and receiving another RRCReconfiguration message including a reconfigurationWithSync for legacy handover to a neighbour cell WHEN: UE detects handover failure and find a selectable cell which is the candidate cell included in ConditionalReconfiguration before T311 expires THEN: UE applies the stored condRRCReconfig associated to the selected cell and perform conditional handover to the selected cell **** TP3: [ TS 38.300 9.2.3.1, TS 38.331 clause 5.3.11 ] WITH: UE having stored ConditionalReconfiguration and receiving another RRCReconfiguration message including a reconfigurationWithSync for handover to a neighbour cell WHEN: UE detects handover failure and can not find any selectable cell before T311 expires THEN: UE goes to RRC_IDLE and release the stored conditional handover configurations |  | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
13 | Y | 38.523-1 | 8.1.5.6.6 | Radio link failure / T312 expiry | **** TP1: [ TS 38.331 clause 5.5.4.1 ] WITH: UE in NR RRC_CONNECTED state and receiving an RRCReconfiguration message including a t312 and a EventTriggerConfig with useT312 configured as ‘ture’ WHEN: T312 of the MCG expires and T310 of the MCG doesn’t expire THEN: RLF is triggered and UE performs RRC connection re-establishment | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
14 |  | 38.523-1 | 8.2.3.17 | Conditional PSCell change | Sub-clause heading |  | RAN5#91-e (May-21) |  |  | 0 | 0% |  | 0% |  |  |  |  | 0% | 0%
15 | Y | 38.523-1 | 8.2.3.17.1 | Conditional PSCell change / Success | **** TP1: [ TS 37.340 clause 10.6 ] WITH: UE in RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PScell change WHEN: any CPC execution condition is not satisfied THEN: UE maintains connection with source PScell and continue to evaluate the CPC execution conditions **** TP2: [ TS 37.340 clause 10.6 ] WITH: UE in NR RRC_CONNECTED state and supporting conditional handover WHEN: UE perform conditional PScell change successfully THEN: UE releases stored CPC configurations | Huawei, Hisilicon | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0% | 0%
16 | Y | 38.523-1 | 8.2.3.17.2 | Conditional PSCell change / Failure | **** TP1: [ TS 37.340 clause 7.7 ] WITH: UE in RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PScell change WHEN: CPC execution failure happen THEN: UE suspends SCG transmissions for all radio bearers and reports the SCG Failure Information to the MN **** TP2: [ TS 37.340 clause 7.7 ] WITH: UE in RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PScell change WHEN: radio link failure is detected for MCG during the execution of CPC THEN: the UE initiates the RRC connection re-establishment procedure |  | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0% | 0%
17 | Y | 38.523-1 | 8.2.3.17.3 | Conditional PSCell change / PCell change / PSCell change | **** TP1: [ TS 37.340 clause 10.6 ] WITH: UE in RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PScell change WHEN: UE receives PCell change command THEN: UE executes the PCell change procedure, regardless of any previously received CPC configuration **** TP2: [ TS 37.340 clause 10.6 ] WITH: UE in RRC_CONNECTED state with EN-DC and receiving an RRCReconfiguration message for conditional PScell change WHEN: UE receives PSCell change command THEN: UE executes the SPCell change procedure, regardless of any previously received CPC configuration |  | RAN5#91-e (May-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
19 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add applicability for NR MobEnc Layer 2 TCs |  | RAN5#91-e (May-21) |  |  | 0.1 | 10% (+7.5%) | 10% (+5%) | 10% (+10%) |  | 10% | 10% |  | 10% | 10%
20 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add applicability for NR MobEnc RRC TCs |  | RAN5#91-e (May-21) | R5-206406 R5-211461 |  | 0.1 | 20% (+17.5%) | 30% (+25%) | 10% (+10%) |  | 30% | 30% |  | 10% | 10%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.