## CA_41C-48D (5DL-2UL)
Work plan for RAN5 Rel-15 CA Sub-WI Group 52035
| Rel-14 Sub-WI Group Name |  |  | CA_41C-48D (5DL-2UL) | [14 empty] | Note! The columns T to W are used to calculate relative completeness vs areas and overall. Do not remove!
| Company |  |  | C Spire
| Contact |  |  | Ivy Kelly
| Target completion |  |  | RAN5#92-e (8-21) | [5 empty] | Format: RAN5#xx (mmm-yy)
| Comments | [8 empty] | Enter comments if needed, e.g. If there are open issues etc.
| Work plan scope |  |  | Downlink CA(s) and associated Uplink CA(s)
| New CA configuration(s) introduced by the work plan |  |  | 5DL/2UL: DL-CA_41C-48D / UL-CA_41C (Rel-15: 52035) 5DL/1UL: DL-CA_41C-48D (Rel-15: 51211) 4DL/2UL: DL-CA_41C-48C / UL-CA_41C (Rel-15: 42099) 4DL/1UL: DL-CA_41A-48D (Rel-15: 41327) 4DL/1UL: DL-CA_41C-48C (Rel-15: 41326) 3DL/2UL: DL-CA_41C-48A / UL-CA_41C (Rel-15: 32085) 3DL/1UL: DL-CA_41A-48C (Rel-15: 31306) 3DL/1UL: DL-CA_41C-48A (Rel-15: 31307) 2DL/1UL: DL-CA_41A-48A (Rel-15: 21122)
| New Fallback CA configuration(s) introduced by the work plan |  |  | -
| Other applicable CA Fallback configuration(s) that are not included in this Work Plan, but are covered by other CA work plans or by other RAN5 work item(s). |  |  | 3DL/1UL: DL-CA_48D (Rel-14: 31201) 2DL/2UL: DL-CA_41C BW set 2 / UL-CA_41C BW set 2 (Rel-12) 2DL/1UL: DL-CA_41C BW set 2 (Rel-12) 2DL/1UL: DL-CA_48C (Rel-14: 21078)
Overall Sub-WI
| Overall completeness |  |  | 91.76% | [14 empty] | Overall sum of item weights |  |  | 127
| Common RF,RRM and Protocol |  |  | 100% | [14 empty] | Sum of item weights for common RF,RRM and protocol area |  |  | 4
| RF completeness |  |  | 88.98% | [14 empty] | Sum of item weights for the RF area |  |  | 95
| RRM completeness |  |  | 100% | [14 empty] | Sum of item weights for the RRM area |  |  | 27
| Protocol completeness |  |  | 100% | [14 empty] | Sum of item weights for the protocol area |  |  | 1
| Note! Do not insert any new rows above this row as the exact positioning of the information above is critical to generate the overall work plan. | [17 empty] | Note! The columns below are used to calculate relative completeness vs areas and overall. Don't remove!
Rel.Weight | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | x1 | x2 | x3 | x4 | x5 | x6 | x7 | Item Overall Completeness | y1 | y2 | y3 | y4
| RF, RRM and Protocol testing common area (TS 36.508) |  |  |  | keep
Item Rel. Weight | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | x1: Detailed Completion Status per area | Item Overall Completeness | Item Accumulated Weight | Item Area Relative Completeness | Item Relative Completeness
[5 empty] | keep | [5 empty] | Test Freq. | Ref. System Config. | GenericTest proc. | Def. Mess. Cont. | Connection Diagrams | Other Areas
[5 empty] | keep | [12 empty] | <- Compl.Weights | bar: x1 to x7
| RF, RRM and Protocol testing common area |  |  |  | keep
1 | 36.508 - (4) Common | 36.508 | 4.3.1 | Test frequencies | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | - Add test frequencies for the new CA configuration in sub-clause 4.3.1.x . - Check if reference system configurations in sub-clause 4.4 need to be updated. |  | RAN5#92-e (8-21) |  | 41A, 41C, 41D, 48A, 48C, 48D test frequencies already in 4.2.1.9/9A &16/16A. No RF changes needed to 4.4 | x1: 100%; x2: 100% | 100% | 2 | 25% | 0.7874% | 1
1 | 36.508 - (4) Common | 36.508 | 4.4 | Reference system configurations | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C | No specific RF changes needed |  | RAN5#92-e (8-21) | [10 empty] | 0 | 0% | 0% | 0
1 | 36.508 - (4) Common | 36.508 | 4.6 | Default RRC message and information elements contents | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C | If this is the first CA configuration of this type of CA configuration then: - Check if there is a need to update the RRC default messages in sub-clause 4.6 for the new type of CA configurations . |  | RAN5#92-e (8-21) |  | Not new CA types | x2: 100% | 100% | 1 | 25% | 0.7874% | 1
1 | 36.508 - (6) Common SIG | 36.508 | 6.2.3.2 | Test frequencies for CA signalling test | DL-CA_41A-48A | Add test frequencies for the new CA configuration for CA signalling tests in sub-clause 6.2.3.2. |  | RAN5#92-e (8-21) | R5-205109 | CR R5-205109 approved to add to T6.2.3.2-2 | x1: 100% | 100% | 1 | 25% | 0.7874% | 1
1 | 36.508 - (6) Common SIG | 36.508 | 6.3 | Reference system configurations | DL-CA_41C-48D DL-CA_41A-48D DL-CA_41C-48C | No specific changes needed |  | RAN5#92-e (8-21) | [10 empty] | 0 | 0% | 0% | 0
1 | 36.508 - (7) Common RRM | 36.508 | 7.2 | RRM Reference system configurations | DL-CA_41C-48D DL-CA_41A-48D DL-CA_41C-48C | No specific RRM changes needed |  | RAN5#92-e (8-21) | [10 empty] | 0 | 0% | 0% | 0
1 | 36.508 - Annex A | 36.508 | Annex A | Connection Diagrams | DL-CA_41C-48D DL-CA_41A-48D DL-CA_41C-48C UL-CA_41C | If this is the first CA configuration of this type of CA configuration then: - Check if there is a need to add connection diagram for the new CA configuration in Annex A. |  | RAN5#92-e (8-21) |  | No new CA type | x5: 100% | 100% | 1 | 25% | 0.7874% | 1
| End list of common RF, RRM and Protocol items (insert any additional item rows above this row) |  |  |  | keep
keep
RF / Performance testing area (TS 36.521-1) and associated applicability defintions (TS 36.521-2)
Item Rel. Weight | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | x1: Detailed Completion Status per area | Item Overall Completeness | Item Accumulated Weight | Item Area Relative Completeness | Item Relative Completeness | Item Rel. Weight for calculation
[5 empty] | keep | [5 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT / TR 36.905 | ICS / TC appli. | Other Areas
[5 empty] | keep | [5 empty] | 1 | 5 | 5 | 2 | 2 | 2 | 2 | <- Compl.Weights
| RF test cases (clauses 6 and 7) |  |  |  | keep
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.2A.1 | UE Maximum Output Power for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | Previously completed. | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.3A.1 | Maximum Power Reduction (MPR) for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.3A.1_1 | Maximum Power Reduction (MPR) for CA (intra-band contiguous DL CA and UL CA) for UL 64QAM | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.4A.1 | Additional Maximum Power Reduction (A-MPR) for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. - Add test point analysis to TR 36.905. |  | RAN5#92-e (8-21) |  | Previously completed. | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.4A.1_1 | Additional Maximum Power Reduction (A-MPR) for CA (intra-band contiguous DL CA and UL CA) for UL 64QAM | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | Previously completed. TMO Editorial CR approved for labeling Table in Section 6.2.4A.1_1.3.4 correctly: T6.2.4A.1.3.4-1 correction to T6.2.4A.1_1.3.4-1 | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.5 | Configured UE transmitted Output Power | DL-CA_41A-48A | - Add delta TIB for the new CA configuration in sub-clause 6.2.5. |  | RAN5#92-e (8-21) |  | Previously completed. | x1: 100% | 100% | 1 | 1.053% | 0.7874% | 1
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.5A.1 | Configured UE transmitted Output Power for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.2A.1 | Minimum Output Power for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.3A.1 | UE Transmit OFF power for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.4A.1.1 | General ON/OFF time mask for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.5A.1.1 | Power Control Absolute power tolerance for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.5A.2.1 | Power Control Relative power tolerance for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  |  | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.5A.3.1 | Aggregate power control tolerance for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.5) RF Tx | 36.521-1 | 6.5.1A.1 | Frequency error for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.5.2A.1.1_1 | EVM for CA (intra-band contiguous DL CA and UL CA) with UL 64QAM | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.5) RF Tx | 36.521-1 | 6.5.2A.2.1 | Carrier leakage for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.5) RF Tx | 36.521-1 | 6.5.2A.3.1 | In-band emissions for non allocated RB for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.1A.1 | Occupied bandwidth for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.2.1A.1 | Spectrum emission mask for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.2.2A.1 | Additional Spectrum Emission Mask for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | Previously completed. | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.6.2.2A.1_1 | Additional Spectrum Emission Mask for CA (intra-band contiguous DL CA and UL CA) for UL 64QAM | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | Previously completed. | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.2.3A.1 | Adjacent Channel Leakage power Ratio for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.6.2.3A.1_1 | Adjacent Channel Leakage power Ratio for CA (intra-band contiguous DL CA and UL CA) for UL 64QAM | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.3.1A.1 | Transmitter Spurious emissions for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.3.2A.1 | Spurious emission band UE co-existence for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. - Add test point analysis to TR 36.905. |  | RAN5#92-e (8-21) |  | Previously completed. | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.3.3A.1 | Additional spurious emissions for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) | R5-205107 | CS-TMO CR R5-205107 approved to correct table in 6.6.3.3A.1.4 | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.6.3.3A.1_1 | Additional spurious emissions for CA (intra-band contiguous DL CA and UL CA) for UL 64QAM | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) | R5-205107 | CS-TMO CR R5-205107 approved to add table in 6.6.3.3A.1_1.4 and correct reference in 6.6.3.3A.1_1.5 | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (6.7) RF Tx | 36.521-1 | 6.7A.1 | Transmit intermodulation for CA (intra-band contiguous DL CA and UL CA) | UL-CA_41C | - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 75% | 95% | 10 | 1% | 0.748% | 1
1 | 36.521-1 - (7.3) RF Rx | 36.521-1 | 7.3A.3 | Reference sensitivity level for CA (inter-band DL CA without UL CA) | DL-CA_41A-48A | - Check if specific minimum requirements need to be updated in sub-clause 7.3A.0 and in 7.3.3 (for delta RIB of the new CA configuration). - Add test points if needed (Test Configuration Table). - Add test requirements. - Add test point analysis to TR 36.905. |  | RAN5#92-e (8-21) |  | non0 (48) delta RIB found in 36.101; Need CR to add combo to T7.3A.3.5-1. | x1: 50%; x3: 100%; x4: 100%; x5: 25% | 80% | 10 | 0.8421% | 0.6299% | 1
1 | 36.521-1 - (7.3) RF Rx | 36.521-1 | 7.3A.5 | Reference sensitivity level for 3DL CA | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | - Check if specific minimum requirements need to be updated in sub-clause 7.3A.0 and in 7.3.3 (for delta RIB of the new CA configuration). - Add test points if needed (Test Configuration Table). - Add test requirements. - Add test point analysis to TR 36.905. |  | RAN5#92-e (8-21) |  | C-A/A-C configs in T7.3A.5.4.1-1 ok . Need CR to add combos to T7.3A.5.5-5. | x1: 25%; x3: 100%; x4: 100%; x5: 25% | 77.5% | 10 | 0.8158% | 0.6102% | 1
1 | 36.521-1 - (7.3) RF Rx | 36.521-1 | 7.3A.9 | Reference sensitivity level for 4DL CA | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. - Add test point analysis to TR 36.905. If the test case exist: - Check if specific minimum requirements need to be updated in sub-clause 7.3A.0. - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. - Add test point analysis to TR 36.905. |  | RAN5#92-e (8-21) |  | Default A-D/D-A in T7.3A.9.4.1-1 . No default C-C (41C-42C exists); default XC-YC in T7.3A.9.4.1-2 is TBD though not sure why - editorial CR?). Need CR to add 41C-48C w/o UL to T7.3A.9.4.1-1. Need CR to add all combos to T7.3A.9.5-5 | 25% | 100% | 50% | 100% | 25% | 100% |  | 72.06% | 17 | 0.7585% | 0.5674% | 1
1 | 36.521-1 - (7.3) RF Rx | 36.521-1 | 7.3A.10 | Reference sensitivity level for 5DL CA | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. - Add test point analysis to TR 36.905. If the test case exist: - Check if specific minimum requirements need to be updated in sub-clause 7.3A.0. - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. - Add test point analysis to TR 36.905. |  | RAN5#92-e (8-21) |  | Default C-D (no D-C) in T7.3A.10.4.1-1; test settings include D-C, though it's not marked. There appears to be no Ref sense table for C-D or D-C combos, although T7.3A.10.5-4 does have some A-E combos despite the table name. Perhaps add here (and change table name)? | 100% | 100% | 25% | 100% | 25% | 100% |  | 69.12% | 17 | 0.7276% | 0.5442% | 1
1 | 36.521-1 - (7.4) RF Rx | 36.521-1 | 7.4A.3 | Maximum input level for CA (inter-band DL CA without UL CA) | DL-CA_41A-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.4) RF Rx | 36.521-1 | 7.4A.3_H | Maximum input level for CA (inter-band DL CA without UL CA) for 256QAM in DL | DL-CA_41A-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.4) RF Rx | 36.521-1 | 7.4A.5 | Maximum input level for 3DL CA | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no band specific needed. | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.4) RF Rx | 36.521-1 | 7.4A.5_H | Maximum input level for 3DL CA for 256QAM in DL | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no band specific needed. | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.4) RF Rx | 36.521-1 | 7.4A.7 | Maximum input level for 4DL CA | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) |  | no band specific needed. T7.4A.7.4.1-1 has XA-YD/YD-XA nomenclature. C-C, A-D/D-A exist. | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (7.4) RF Rx | 36.521-1 | 7.4A.8 | Maximum input level for 5DL CA | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) | R5-210262 | no band specific needed. CR R5-210262 approved - adds default C-D & D-C combos in T7.4A.8.4.1-1 (test config table) and T7.4A.8.4.2-1 | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (7.5) RF Rx | 36.521-1 | 7.5A.3 | Adjacent Channel Selectivity (ACS) for CA (inter-band DL CA without UL CA) | DL-CA_41A-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no changes needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.5) RF Rx | 36.521-1 | 7.5A.5 | Adjacent Channel Selectivity (ACS) for 3DL CA | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no changes needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.5) RF Rx | 36.521-1 | 7.5A.7 | Adjacent Channel Selectivity (ACS) for 4DL CA | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) |  | no band specific needed. C-C, A-D, and D-A in T7.5A.7.4.1-1; T7.5A.7.4.1-1 has XA-YD/YD-XA nomenclature. | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (7.5) RF Rx | 36.521-1 | 7.5A.8 | Adjacent Channel Selectivity (ACS) for 5DL CA | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) |  | Need CR to add C-D and D-C to T7.5A.8.4.1-1. Any changes to T7.5A.8.4.2-1? | 100% | 100% | 25% | 100% | 25% | 100% |  | 69.12% | 17 | 0.7276% | 0.5442% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.1A.3 | In-band blocking for CA (inter-band DL CA without UL CA) | DL-CA_41A-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) | R5-205119 | CR R5-205119 approved - adds 48 to T7.6.1A.3.5-2 | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.1A.5 | In-band blocking for 3DL CA | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | No band specific. | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.1A.7 | In-band blocking for 4DL CA | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) |  | A-D, D-A, C-C are in T7.6.1A.7.4.1-1. T7.6.1A.7.5-3 and -5 has all needed | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.1A.8 | In-band blocking for 5DL CA | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) | R5-205120 | Need CR to add C-D and D-C to T7.6.1A.8.4.1-1. CR R5-205120 approved adds 48 to T7.6.1A.8.5-5. | 100% | 100% | 25% | 100% | 25% | 100% |  | 69.12% | 17 | 0.7276% | 0.5442% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.2A.3 | Out-of-band blocking for CA (inter-band DL CA without UL CA) | DL-CA_41A-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) | R5-205122 | CR R5-205122 approved adds B48 to Note 5 in T7.6.2A.3.5-2 to align to T7.6.2.1A-2 in 36.101. | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.2A.5 | Out-of-band blocking for 3DL CA | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) | R5-205131 | C-A and A-C are in T7.6.2A.5.4.1-1. CR R5-205131 approved adds 48 to T7.6.2A.5.5-4 and -5 with reference to notes | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.2A.7 | Out-of-band blocking for 4DL CA | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) | R5-205153 | A-D, D-A, C-C are in T7.6.2A.7.4.1-1. CR R5-205153 approved adds 41D, 48C, 48D to T7.6.2A.7.5-2 (with Note for 48) & Add 48 to Note 5 in T 7.6.2A.7.5-4 and 48 with Note 2 to T7.6.2A.7.5-5 | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.2A.8 | Out-of-band blocking for 5DL CA | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) | R5-205154 | Need CR to add C-D/D-C to T7.6.2A.8.4.1-1 and Table 7.6.2A.8.4.2-1. CR R5-205154 approved adds B48 to Note 5 in T7.6.2A.8.5-4, and 48 to T7.6.2A.8.5-5 with note 2. | 100% | 25% | 25% | 100% | 25% | 100% |  | 47.06% | 17 | 0.4954% | 0.3705% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.3A.3 | Narrow band blocking for CA (inter-band DL CA without UL CA) | DL-CA_41A-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.3A.5 | Narrow band blocking for 3DL CA | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no band specific; C-A/A-C in T7.6.3A.5.4.1-1. | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.3A.7 | Narrow band blocking for 4DL CA | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) |  | no band specific; C-C, D-A/A-D in T7.6.3A.7.4.1-1. | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.3A.8 | Narrow band blocking for 5DL CA | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) |  | no band specific; add C-D/D-C to T7.6.3A383431-1 and T6.3A.8.4.2-1 | 100% | 100% | 25% | 100% | 25% | 100% |  | 69.12% | 17 | 0.7276% | 0.5442% | 1
1 | 36.521-1 - (7.7) RF Rx | 36.521-1 | 7.7A.3 | Spurious response for CA (inter-band DL CA without UL CA) | DL-CA_41A-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.7) RF Rx | 36.521-1 | 7.7A.5 | Spurious response for 3DL CA | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.7) RF Rx | 36.521-1 | 7.7A.7 | Spurious response for 4DL CA | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) |  | no band specific | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (7.7) RF Rx | 36.521-1 | 7.7A.8 | Spurious response for 5DL CA | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) |  | no band specific | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (7.8) RF Rx | 36.521-1 | 7.8.1A.3 | Wideband intermodulation for CA (inter-band DL CA without UL CA) | DL-CA_41A-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no band specific | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.8) RF Rx | 36.521-1 | 7.8.1A.5 | Wideband intermodulation for 3DL CA | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#92-e (8-21) |  | no band specific; C-A/A-C in T7.8.1A.5.4.1-1. | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (7.8) RF Rx | 36.521-1 | 7.8.1A.7 | Wideband intermodulation for 4DL CA | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) |  | no band specific; D-A/A-D and C-C in T7.8.1A.7.4.1-1 and in T7.8.1A.7.4.2-1. | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (7.8) RF Rx | 36.521-1 | 7.8.1A.8 | Wideband intermodulation for 5DL CA | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. If the test case exist: - Check if specific minimum requirements need to be updated - Add test points (Test Configuration Table). - Add test requirement for the new CA configuration. |  | RAN5#92-e (8-21) |  | no band specific; need CR to add C-D/D-C to T7.8.1A.8.4.1-1 and T7.8.1A.8.4.2-1. | 100% | 100% | 25% | 100% | 25% | 100% |  | 69.12% | 17 | 0.7276% | 0.5442% | 1
| Perfomance test cases (clauses 8 and 9) |  |  |  | keep
1 | 36.521-1 - (8.1) General | 36.521-1 | 8.1.2 | Applicability of requirements | DL-CA_41C-48D DL-CA_41A-48D DL-CA_41C-48C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | - Add new BW combinations in section 8.1.2 if needed - If this is the first CA configuration of this CA configuration type, add it in section 8.1.2 |  | RAN5#92-e (8-21) |  | no new CA config type. 20 MHz is an acceptable BW combo for all test cases. | x7: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.1.1_A.1 | TDD PDSCH Single Antenna Port Performance for CA (2DL CA) | DL-CA_41A-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new CA config or BW combo | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.1.1_A.2 | TDD PDSCH Single Antenna Port Performance for CA (3DL CA) | DL-CA_41A-48C DL-CA_41C-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new CA config or BW combo | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.1.1_A.[3] | TDD PDSCH Single Antenna Port Performance for CA (4DL CA) | DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. Note! Consider combining 4 CC and 5 CC in the same test case. Justification: 4 and 5 CC needs to be tested in same time frame and is added as part of same WI. |  | RAN5#92-e (8-21) |  | no new CA config, no new test case | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.1.1_A.[4] | TDD PDSCH Single Antenna Port Performance for CA (5DL CA) | DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. Note! Consider combining 4 CC and 5 CC in the same test case. Justification: 4 and 5 CC needs to be tested in same time frame and is added as part of same WI. |  | RAN5#92-e (8-21) |  | no new CA config, no new test case | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.3.1_A.1 | TDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (2DL CA) | DL-CA_41A-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new BW combo needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.3.1_A.2 | TDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (3DL CA) | DL-CA_41A-48C DL-CA_41C-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new BW combo needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.3.1_A.[3] | TDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (4DL CA) | DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. Note! Consider combining 4 CC and 5 CC in the same test case. Justification: 4 and 5 CC needs to be tested in same time frame and is added as part of same WI. |  | RAN5#92-e (8-21) |  | no new CA config, no new test case | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.3.1_A.[4] | TDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (5DL CA) | DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. Note! Consider combining 4 CC and 5 CC in the same test case. Justification: 4 and 5 CC needs to be tested in same time frame and is added as part of same WI. |  | RAN5#92-e (8-21) |  | no new CA config, no new test case | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.4.2_A.1 | TDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (2DL CA) | DL-CA_41A-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new BW combo needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.4.2_A.2 | TDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (3DL CA) | DL-CA_41A-48C DL-CA_41C-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new BW combo needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.4.2_A.[3] | TDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (4DL CA) | DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. Note! Consider combining 4 CC and 5 CC in the same test case. Justification: 4 and 5 CC needs to be tested in same time frame and is added as part of same WI. |  | RAN5#92-e (8-21) |  | no new CA config, no new test case | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.2.4.2_A.[4] | TDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (5DL CA) | DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. Note! Consider combining 4 CC and 5 CC in the same test case. Justification: 4 and 5 CC needs to be tested in same time frame and is added as part of same WI. |  | RAN5#92-e (8-21) |  | no new CA config, no new test case | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (8.7) Sustained Data-rate | 36.521-1 | 8.7.2.1_A.1 | TDD sustained data rate performance for CA (2DL CA) | DL-CA_41A-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new BW combo needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (8.7) Sustained Data-rate | 36.521-1 | 8.7.2.1_A.2 | TDD Sustained data rate performance for CA (3DL CA) | DL-CA_41A-48C DL-CA_41C-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new BW combo needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (8.7) Sustained Data-rate | 36.521-1 | 8.7.2.1_A.3 | TDD sustained data rate performance for CA (4DL CA) | DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. Note! Consider combining 4 CC and 5 CC in the same test case. Justification: 4 and 5 CC needs to be tested in same time frame and is added as part of same WI. |  | RAN5#92-e (8-21) |  | no new CA config, no new test case | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (8.7) Sustained Data-rate | 36.521-1 | 8.7.2.1_A.5 | TDD sustained data rate performance for CA (5DL CA) | DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. Note! Consider combining 4 CC and 5 CC in the same test case. Justification: 4 and 5 CC needs to be tested in same time frame and is added as part of same WI. |  | RAN5#92-e (8-21) |  | no new CA config, no new test case. T8.7.2.1_A.5.3-3 incomplete (no test pts) - confer with colleagues | 100% | 100% | 25% | 100% | 25% | 100% |  | 69.12% | 17 | 0.7276% | 0.5442% | 1
1 | 36.521-1 - (8.7) Sustained Data-rate | 36.521-1 | 8.7.2.1_H.2 | TDD sustained data rate performance for CA (2DL CA) for 256QAM in DL | DL-CA_41A-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new BW combo needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (8.7) Sustained Data-rate | 36.521-1 | 8.7.2.1_H.3 | TDD sustained data rate performance for 256QAM in DL (3DL CA) | DL-CA_41A-48C DL-CA_41C-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new BW combo needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (9.1) General | 36.521-1 | 9.1 | Applicability of requirements | DL-CA_41C-48D DL-CA_41A-48D DL-CA_41C-48C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | - Add new BW combinations in section 9.1.1 if needed. - If this is the first CA configuration of the ne3 CA configuration type, add it in section 9.1.1 |  | RAN5#92-e (8-21) |  | no new CA config, no new BW combo | x7: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-1 - (9.6) CSI reporting | 36.521-1 | 9.6.1.2_A.1 | TDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (2DL CA) | DL-CA_41A-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new BW combo needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (9.6) CSI reporting | 36.521-1 | 9.6.1.2_A.2 | TDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (3DL CA) | DL-CA_41A-48C DL-CA_41C-48A | Add new BW combinations if needed |  | RAN5#92-e (8-21) |  | no new BW combo needed | x1: 100%; x3: 100%; x4: 100%; x5: 25% | 85% | 10 | 0.8947% | 0.6693% | 1
1 | 36.521-1 - (9.6) CSI reporting | 36.521-1 | 9.6.1.2_A.3 | TDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (4DL CA) | DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Add new test case. Note! Consider combining 4 CC and 5 CC in the same test case. Justification: 4 and 5 CC needs to be tested in same time frame and is added as part of same WI. |  | RAN5#92-e (8-21) |  | no new BW combo needed | 100% | 100% | 100% | 100% | 25% | 100% |  | 91.18% | 17 | 0.9598% | 0.7179% | 1
1 | 36.521-1 - (9.6) CSI reporting | 36.521-1 | 9.6.1.2_A.4 | TDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (5DL CA) | DL-CA_41C-48D | If this is the first CA configuration of this new CA configuration type then: - Add new test case. Note! Consider combining 4 CC and 5 CC in the same test case. Justification: 4 and 5 CC needs to be tested in same time frame and is added as part of same WI. |  | RAN5#92-e (8-21) |  | no new CA config, no new test case. 9.6.1.2_A.4.3 incomplete (test parms in min reqs still in square brackets) - confer with colleagues | 25% | 100% | 100% | 100% | 25% | 100% |  | 86.76% | 17 | 0.9133% | 0.6832% | 1
| RF General (TS 36.521-1 clauses 3 to 5 and Annexes, TS 36.521-2 ICS) |  |  |  | keep
1 | 36.521-1 - (3) General | 36.521-1 | 3 | Definitions, symbols and abbreviations | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Check if there is a need to update definitions, symbols, and abbreviations in clause 3. |  | RAN5#92-e (8-21) |  | No DSA impact | x7: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-1 - (4) General | 36.521-1 | 4.1 | Categorization of test requirements in CA | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Check if there is a need to update the categorization of test requirements in CA in sub-clause 4.1. |  | RAN5#92-e (8-21) |  | no new category | x7: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-1 - (5) General | 36.521-1 | 5.2A and 5.4.2A | Operating bands for CA in clause 5.2.A and channel bandwidths and bandwidth combination sets to clause 5.4.2A | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | Add CA operating band in clause 5.2A and CA Channel bandwidth ín clause 5.4.2A for the new CA configuration. |  | RAN5#92-e (8-21) |  | both bands exist in T5.2.A-1 & T5.2.A-2, T5.4.2A.1-1 & T5.4.2A.1-2 | x7: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-1 - Annex A | 36.521-1 | Annex A | Measurement Channels Tx, Rx and Performance TCs | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | - Check if there is a need to update Measurement Channels in Annex A for the Tx and Rx TCs for the new CA configuration. - Check if there is a need to update Measurement Channels in Annex A for the Performance TCs for the new CA configuration. |  | RAN5#92-e (8-21) |  | no changes needed | x7: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-1 - Annex C | 36.521-1 | Annex C | Downlink Physical Channels | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | Check if there is a need to update DL Physical Channels in Annex C for the new CA configuration. |  | RAN5#92-e (8-21) |  | no changes needed | x7: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-1 - Annex D | 36.521-1 | Annex D | Characteristics of the Interfering Signal | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C | Check if there is a need to update the characteristics of the Interfering Signal in Annex D for the new CA configuration. |  | RAN5#92-e (8-21) |  | no changes needed | x7: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-1 - Annex F | 36.521-1 | Annex F | Measurement uncertainties and Test Tolerances | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | Uncertainty of the test system and the allowed test tolerances is handled for each test case in the TS 36.521.1 section. | [12 empty] | 0 | 0% | 0% | 0
1 | 36.521-1 - Annex G | 36.521-1 | Annex G | Statistical Testing Tx, Rx and Performance TCs | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C | - Check if there is a need to update Statistical Testing in Annex G for the Tx and Rx TCs for the new CA configuration. - Check if there is a need to update Statistical Testing in Annex G for the Performance TCs for the new CA configuration. |  | RAN5#92-e (8-21) |  | no changes needed | x7: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-1 - Annex I | 36.521-1 | Annex I | Handling of different releases | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C | If this is the first CA configuration of this new CA configuration type then: - Check if there is a need to update the Handling of different releases in Annex I. |  | RAN5#92-e (8-21) |  | no changes needed | x7: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-2 - (A) ICS | 36.521-2 | Annex A | Implementation Conformance Statements for RF/RRM test cases | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | Update of CA Physical Layer Baseline Implementation Capabilities for new CA configuration in Annex A.4.6 |  | RAN5#92-e (8-21) | R5-206610 | CR [R5-205117, R5-206080 (withdrawn)] R5-206610 adds C-D combo to TA.4.6.3-1 &41-48 combos to TA.4.6.3-3 | x6: 100% | 100% | 2 | 1.053% | 0.7874% | 1
1 | 36.521-2 - (4.1) RF TC applicability | 36.521-2 | 4.1 | Applicability of new RF and performance test cases | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C | TC applicability of new RF, performance and RRM test cases is handled in the work plan under the TS 36.521-1 or TS 36.521-3 sections. | [12 empty] | 0 | 0% | 0% | 0
| End list of RF Misc items (insert any additional RF Misc item rows above this row) |  |  |  | keep
keep
RRM testing area (TS 36.521-3 & TS 37.571-1) and associated applicability definitions (TS 36.521-2 and TS 37.571-3)
Item Rel. Weight | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | x1: Detailed Completion Status per area | Item Overall Completeness | Item Accumulated Weight | Item Area Relative Completeness | Item Overall Relative Completeness
[5 empty] | keep | [5 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT | ICS / TC appli. | Other Areas
[5 empty] | keep | [5 empty] | 1 | 5 | 5 | 2 | 2 | 2 | 2 | <- Compl.Weights
| RRM test cases |  |  |  | keep
1 | 36.521-3 - (6.2) Random Access | 36.521-3 | 6.2.8 | E-UTRAN TDD - Non-Contention Based Random Access Test For SCell in sTAG | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48C / UL-CA_41C DL-CA_41C-48A / UL-CA_41C UL-CA_41C | Typically no updates needed to legacy test cases for a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group | x5: 100%; x7: 100% | 100% | 4 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (7.x) UE TT, TA... | 36.521-3 | 7.1.x and 7.2.x | Legacy TC(s) for CA 2CC UL for TDD and Transmit Timing Accuracy (7.1.4, 7.1.4_1, 7.1.4A, 7.1.7, 7.1.7A, 7.1.7B) and Timing Advance (7.2.5, 7.2.5A, 7.2.5B). | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48C / UL-CA_41C DL-CA_41C-48A / UL-CA_41C UL-CA_41C | Typically no updates needed to legacy test cases for a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group | x5: 100%; x7: 100% | 100% | 4 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (8.x) Meas Proc | 36.521-3 | 8.16.x (2CC) | Legacy TC(s) for CA 2CC DL for TDD and Measurement Procedures Performance (8.16.2, 8.16.4, 8.16.6, 8.16.8, 8.16.10, 8.16.12, 8.16.14, 8.16.16, 8.16.18, 8.16.18A ). | DL-CA_41A-48A | Typically no updates needed to legacy test cases for a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group | x5: 100%; x7: 100% | 100% | 4 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (8.x) Meas Proc | 36.521-3 | 8.16.x (3CC) | Legacy TC(s) for CA 3CC DL for TDD and Measurement Procedures Performance (8.16.30, 8.16.34, 8.16.38, 8.16.42). | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | Typically no updates needed to legacy test cases for a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group | x5: 100%; x7: 100% | 100% | 4 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (8.x) Meas Proc | 36.521-3 | 8.16.52 | 4DL TDD CA Event Triggered Reporting with 3 deactivated SCells in Non-DRX | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If a TC has not been introduced by any other CA configuration then: - Add new test case as per the requirements in TS36.133 for the new type of CA configuration. Else: - Typically no updates needed to existing test cases for adding a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group; no new test case needed; no test case mods needed. | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 17 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (8.x) Meas Proc | 36.521-3 | 8.16.56 | 4DL TDD CA Event Triggered Reporting on Deactivated SCell with PCell and SCell Interruptions in Non-DRX | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If a TC has not been introduced by any other CA configuration then: - Add new test case as per the requirements in TS36.133 for the new type of CA configuration. Else: - Typically no updates needed to existing test cases for adding a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group; no new test case needed; no test case mods needed. | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 17 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (8.x) Meas Proc | 36.521-3 | 8.16.58 | 4DL TDD CA activation and deactivation of know SCell in non-DRX | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If a TC has not been introduced by any other CA configuration then: - Add new test case as per the requirements in TS36.133 for the new type of CA configuration. Else: - Typically no updates needed to existing test cases for adding a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group; no new test case needed; no test case mods needed. | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 17 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (8.x) Meas Proc | 36.521-3 | 8.16.62 | 4DL TDD CA activation and deactivation of unknown SCell in non-DRX | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If a TC has not been introduced by any other CA configuration then: - Add new test case as per the requirements in TS36.133 for the new type of CA configuration. Else: - Typically no updates needed to existing test cases for adding a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group; no new test case needed; no test case mods needed. | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 17 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (8.x) Meas Proc | 36.521-3 | 8.16.70 | 5DL TDD CA activation and deactivation of unknown SCell in non-DRX | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If a TC has not been introduced by any other CA configuration then: - Add new test case as per the requirements in TS36.133 for the new type of CA configuration. Else: - Typically no updates needed to existing test cases for adding a new CA configiration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group; no new test case needed; no test case mods needed. | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 17 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (8.x) Meas Proc | 36.521-3 | 8.16.72 | 5DL TDD CA Event Triggered Reporting with Deactivated SCells in Non-DRX | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If a TC has not been introduced by any other CA configuration then: - Add new test case as per the requirements in TS36.133 for the new type of CA configuration. Else: - Typically no updates needed to existing test cases for adding a new CA configiration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group; no new test case needed; no test case mods needed. | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 17 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (8.x) Meas Proc | 36.521-3 | 8.16.74 | 5DL TDD CA Event Triggered Reporting on Deactivated SCell with PCell and SCell Interruptions in Non-DRX | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If a TC has not been introduced by any other CA configuration then: - Add new test case as per the requirements in TS36.133 for the new type of CA configuration. Else: - Typically no updates needed to existing test cases for adding a new CA configiration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group; no new test case needed; no test case mods needed. | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 17 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (8.x) Meas Proc | 36.521-3 | 8.16.78 | 5DL TDD CA activation and deactivation of know SCell in non-DRX | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If a TC has not been introduced by any other CA configuration then: - Add new test case as per the requirements in TS36.133 for the new type of CA configuration. Else: - Typically no updates needed to existing test cases for adding a new CA configiration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group; no new test case needed; no test case mods needed. | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 17 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (9.x) Meas Perf | 36.521-3 | 9.1.47 | 4DL TDD RSRP for E-UTRAN in Carrier Aggregation | DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If a TC has not been introduced by any other CA configuration then: - Add new test case as per the requirements in TS36.133 for the new type of CA configuration. Else: - Typically no updates needed to existing test cases for adding a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group; no new test case needed; no test case mods needed. | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 17 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (9.x) Meas Perf | 36.521-3 | 9.1.51 | 5DL TDD RSRP for E-UTRAN in Carrier Aggregation | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D | If a TC has not been introduced by any other CA configuration then: - Add new test case as per the requirements in TS36.133 for the new type of CA configuration. Else: - Typically no updates needed to existing test cases for adding a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group; no new test case needed; no test case mods needed. | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 17 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (9.x) Meas Perf | 36.521-3 | 9.1.x (2CC) | Legacy TC(s) for CA 2CC DL for TDD and Measurement Performance (9.1.7, 9.1.13, 9.1.19, 9.1.21, 9.1.24, 9.2.6, 9.2.12, 9.2.22, 9.2.24, 9.2.27). | DL-CA_41A-48A | Typically no updates needed to legacy test cases for a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group | x5: 100%; x7: 100% | 100% | 4 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (9.x) Meas Perf | 36.521-3 | 9.1.x (3CC) | Legacy TC(s) for CA 3CC DL for TDD and Measurement Performance (9.1.38, 9.1.40, 9.1.40_1, 9.2.39, 9.2.41). | DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A | Typically no updates needed to legacy test cases for a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. |  | RAN5#92-e (8-21) |  | no new band group | x5: 100%; x7: 100% | 100% | 4 | 3.704% | 0.7874% | 1
1 | 37.571-1 - (10) Pos Perf | 37.571-1 | 10.x | Legacy TC(s) for OTDOA RSTD Positioning Performance requirements | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | Typically no updates needed to legacy test cases for a new CA configuration. |  | RAN5#92-e (8-21) |  | no band specific info | x7: 100% | 100% | 2 | 3.704% | 0.7874% | 1
keep
| RRM General |  |  |  | keep
1 | 36.521-3 - (3) General | 36.521-3 | 3 | Definitions, symbols and abbreviations. | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41A-48D DL-CA_41C-48C | If the CA configuration is the first of one of the new CA configuration types (3DL/3UL, 4DL/1UL, 4DL/2UL, 5DL/1UL or 5DL/2UL) then check if there is a need to update definitions, symbols, and abbreviations in clause 3. |  | RAN5#92-e (8-21) |  | No DSA impact | x7: 100% | 100% | 2 | 3.704% | 0.7874% | 1
1 | 36.521-3 - (3) General | 36.521-3 | 3 | Groups of bands | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | Ensure that the operating bands of the CA configuration are covered in Clause 3.5.1 “Group of bands”. |  | RAN5#92-e (8-21) |  | 41 and 48 found in T3.5.1-1 | x7: 100% | 100% | 2 | 3.704% | 0.7874% | 1
1 | 36.521-3 - Annex A | 36.521-3 | Annex A | Measurement channels | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If the CA configuration is the first of one of the new CA configuration types (3DL/3UL, 4DL/1UL, 4DL/2UL, 5DL/1UL or 5DL/2UL) then check if there is a need to update Measurements Channels in Annex A for the new type of CA configuration. |  | RAN5#92-e (8-21) |  | Annex A has no CA relevance | x7: 100% | 100% | 2 | 3.704% | 0.7874% | 1
1 | 36.521-3 - Annex D | 36.521-3 | Annex D | OFDMA Channel Noise Generator (OCNG) | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If the CA configuration is the first of one of the new CA configuration types (3DL/3UL, 4DL/1UL or 5DL/1UL) then check if there is a need to update OFDMA Channel Noise Generator (OCNG) in Annex D for the new type of CA configuration. |  | RAN5#92-e (8-21) |  | Annex D has no CA relevance | x7: 100% | 100% | 2 | 3.704% | 0.7874% | 1
1 | 36.521-3 - Annex E | 36.521-3 | Annex E | Cell configuration mapping | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If the CA configuration is the first of one of the new CA configuration types (3DL/3UL, 4DL/1UL, 4DL/2UL, 5DL/1UL or 5DL/2UL) then check if there is a need to update Cell configuration mapping in Annex E for the new type of CA configuration. |  | RAN5#92-e (8-21) |  | TE-5 and TE-6 contain all CA configs | x7: 100% | 100% | 2 | 3.704% | 0.7874% | 1
1 | 36.521-3 - Annex F | 36.521-3 | Annex F | Uncertainty of the test system and test tollerances. | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | Uncertainty of the test system and the allowed test tolerances is handled for each test case in the TS 36.521-1 section of the work plan. | [12 empty] | 0 | 0% | 0% | 0
1 | 36.521-3 - Annex G | 36.521-3 | Annex G | Statistical Testing | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If the CA configuration is the first of one of the new CA configuration types (3DL/3UL, 4DL/1UL, 4DL/2UL, 5DL/1UL or 5DL/2UL) then: - Check if there is a need to update Statistical Testing in Annex G for the new type of CA configuration. |  | RAN5#92-e (8-21) |  | no band-specific or CA-specific info in Annex G. | x7: 100% | 100% | 2 | 3.704% | 0.7874% | 1
1 | 36.521-3 - Annex H | 36.521-3 | Annex H | Default Message Content | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If the CA configuration is the first of one of the new CA configuration types 3DL/3UL, 4DL/1UL, 4DL/2UL, 5DL/1UL or 5DL/2UL then: - Check if there is a need to update Default Message Contents in Annex G for the new type of CA configuration. |  | RAN5#92-e (8-21) |  | H.4.1 and H.4.2 tables are for >=3DL CA, so all configs should be covered. Otherwise, no band-specific or config-specific content. | x7: 100% | 100% | 2 | 3.704% | 0.7874% | 1
1 | 36.521-3 - Annex I | 36.521-3 | Annex I | RRM Requirements Exceptions | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | Check if the CA band combination is covered by the RRM condition in sub-clause I.4. |  | RAN5#92-e (8-21) |  | inter-band CA with UL band covered in I.4.3.1; nothing band/CA combo specific to add | x7: 100% | 100% | 2 | 3.704% | 0.7874% | 1
1 | 36.521-3 - Annex J | 36.521-3 | Annex J | Handling of different releases | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C | If this is the first CA configuration of this new CA configuration type then: - Check if there is a need to update the Handling of different releases in Annex J. |  | RAN5#92-e (8-21) |  | no changes needed | x7: 100% | 100% | 2 | 3.704% | 0.7874% | 1
1 | 37.571-3 - ICS | 37.571-3 | Annex A | Implementation Conformance Statements for positioning performance test cases | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | Check if there is a need to update the CA Physical Layer Baseline Implementation Capabilities for the new CA configuration in Annex A.4. |  | RAN5#92-e (8-21) |  | Nothing band or CA-related | x6: 100% | 100% | 2 | 3.704% | 0.7874% | 1
| End list of RF Misc ietms (insert any additional RRM Misc item rows above this row) |  |  |  | keep
keep
Protocol testing area (TS 36.523-1) and associated applicability defintions (TS 36.523-2)
Item Rel. Weight | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | x1: Detailed Completion Status per area | Item Overall Completeness |  | Item Area Relative Completeness | Item Relative Completeness
[5 empty] | keep | [5 empty] | TP & Conf. Req. | Test proc. | Mess . Cont. | ICS / TC appli. | Other Areas
[5 empty] | keep | [5 empty] | 2 | 5 | 2 | 1 | 1 | 1 | 1 | <- Compl.Weights
| Protocol test cases |  |  |  | keep
1 | Protocol | 36.523-1 |  | No new test cases needed. | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | [13 empty] | 0 | 0% | 0% | 0
| End list of SIG test cases (insert any additional SIG test case rows above this row) |  |  |  | keep
| Protocol General |  |  |  | keep
1 | 36.523-2 - ICS | 36.523-2 | Annex A | Implementation Conformance Statements for Protocol test cases | DL-CA_41C-48D / UL-CA_41C DL-CA_41C-48D DL-CA_41C-48C / UL-CA_41C DL-CA_41A-48D DL-CA_41C-48C DL-CA_41C-48A / UL-CA_41C DL-CA_41A-48C DL-CA_41C-48A DL-CA_41A-48A | - Update of CA Physical Layer Baseline Implementation Capabilities for new CA configuration in Annex A.4.3.3. |  | RAN5#92-e (8-21) | CR R5-205108 | CR R5-205108 approved adds C-D in TA.4.3.3.3-1; and to add all DL combos to TA.4.3.3.3-3. UL-CA_41C already in tables. | x4: 100% | 100% | 1 | 100% | 0.7874% | 1
| End list of SIG Misc items (insert any additional SIG Misc item rows above this row) |  |  |  | keep
Note on A25: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on S27: Used to calculate work areas relative impact on the item's completeness. Default value is 1. For a more work intesive area set to value >1.
Note on A39: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on S41: Used to calculate work areas relative impact on the item's completeness. Default value is 1. For a more work intesive area set to value >1.
Note on A145: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on S147: Used to calculate work areas relative impact on the item's completeness. Default value is 1. For a more work intesive area set to value >1.
Note on A182: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on S184: Used to calculate work areas relative impact on the item's completeness. Default value is 1. For a more work intesive area set to value >1.