## Slide 1: RAN5 5G NR STATUS, DELIVERY phases and targets (March-21)
3GPP TSG-RAN5#90-e R5-210977
Electronic Meeting, 22nd Feb – 5th March 2021

## Slide 2: Introduction & CONTENT
The purpose of this document is to give high level status of RAN5 completed 5GS test cases and the targets for the next RAN5 Rel-15 5GS work item delivery phase.
Content
Progress since previous report
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) targets
Planning for next delivery
  SA Option 2 (SA NR)
  NSA Option 3 (EN-DC)

## Slide 3: Progress SINCE PREVIOUS REPORT
SA NR (SA Option 2) Phase 10 completed. SA NR overall completion 85%
EN-DC (NSA Option 3) Phase 11 completed. EN-DC overall completion 92%
Target completion moved 3 months to RAN5#91-e (May-21)
More time may be needed to complete FR2 test cases
  See next slide for FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) Targets
For further details including list of completed test cases see RAN5 workplan in R5-210974

## Slide 4
FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) Target Completion Update (R5-210400)

## Slide 5
RF/Performance/RRM test cases:
  FR1
    RF: Complete remaining 1 (UL-MIMO) out of 121 FR1 test cases (TS 38.521-1).
    RRM: Complete remaining 1 out of 83 FR1 test cases (TS 38.533).
  FR2 & FR1+FR2:
    All FR2 test cases will not be feasible to complete by RAN5#91-e.
    RF: Progress remaining 201 out of 228 FR2 single carrier and CA test cases (TS 38.521-2).
    RF performance: Progress remaining 5 out of 9 FR2 test cases (TS 38.521-4).
      Progress test tolerance analysis considering SNR testability issue pending for FR2 Demod and CSI test cases (TS 38.521-4).
    RRM: Progress remaining 60 out of 63 FR2 and 7 out of 7 FR1+FR2 test cases (TS 38.533).
RAN Protocol test cases (TS 38.523-1):
  Layer 2: Complete remaining 1 out of 77 FR1, 1 out of 77 FR2 and 1 out of 7 FR1+FR2 test cases.
  Idle mode: Complete remaining 34 out of 59 FR2 test cases.
  RRC: Complete remaining 2 out of 84 FR1, 50 out of 84 FR2 and 12 out of 26 FR1+FR2 test cases.
  Multilayer/Services: Complete remaining 1 out of 27 FR1 and 5 out of 27 FR2 test cases.
    Progress of FR2 test cases pending solution for signal levels for OTA testing with 2 E-UTRA cells simultaneously active or 2 NR FR1 cells simultaneously active.
IMS Protocol test cases (TS 34.229-5):
  Progress 83 out of 121 IMS test cases (FR1 and FR2).
Plan for next delivery:
SA Option 2 (SA NR) - Phase 11 - Target RAN5#91-e MAY-21

## Slide 6
Plan for next deliverY:
NSA Option 3 (EN-DC) - Phase 12 content - Target RAN5#91-e MAY-21
RF/Performance/RRM test cases
  FR1:
    RF: Complete remaining 25 out of 127 FR1 (anchor-agnostic) test cases (TS 38.521-3).
  FR2 & FR1+FR2:
    All FR2 test cases will not be feasible to complete by RAN5#91-e.
    RF: Progress remaining 59 out of 69 FR2 and 1 out of 2 FR1+FR2 test cases (TS 38.521-3).
      Progress depending on progress of associated NR SA FR2 test cases.
    RF performance: Progress remaining 5 out of 9 FR2 test cases (TS 38.521-4).
      Progress test tolerance analysis considering SNR testability issue pending for FR2 Demod and CSI test cases (TS 38.521-4).
    RRM: Progress remaining 51 out of 53 FR2 and 5 out of 5 FR1+FR2 test cases (TS 38.533).
RAN Protocol test cases (TS 38.523-1):
  RRC: Complete remaining 4 out of 49 FR1, 8 out of 49 FR2 and 4 out of 4 FR1+FR2 test cases.