## Cover sheet
3GPP TSG-RAN WG5 Meeting #90-e | [10 empty] | R5-211153
Electronic Meeting, 22nd February - 5th March 2021
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP UE Conformance Test Aspects- Even further mobility enhancement for E-UTRAN after RAN5#90-e
Work item code: | LTE_feMob-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
In the RAN#88-e meeting, the new WID on UE Conformance Aspects - Even Further Mobility Enhancement for E-UTRAN (LTE_feMob-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 16% (+11%) | 0 | 7
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 15.6% (+10.6%) | 0 | 7
FDD |  | 15.6% (+10.6%) | 0 | 7
TDD |  | 15.6% (+10.6%) | 0 | 7
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 0% |  |  | 0% |  |  | 0%
LTE RF/RRM
Applicability RF, Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 11.4% (+11.4%) | 0 | 7 | 11.4% (+11.4%) | 0 | 7 | 11.4% (+11.4%) | 0 | 7
Applicability Protocol test cases | 36.523-2 | 5% (+5%) |  |  | 5% (+5%) |  |  | 5% (+5%)
Test suites (TTCN) | 36.523-3
5 References
[1] RP-200731 | New WID: UE Conformance Aspects - Even Further Mobility Enhancement for E-UTRAN, China Telecom, RAN #88-e, June 2020
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects- Even further mobility enhancement for E-UTRAN | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_feMob-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects- Even further mobility enhancement for E-UTRAN comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [12 empty] | vs Area
WP Resp: |  | Jingzhou Wu, China Telecom |  |  | wujingzhou@chinatelecom.cn | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD | TDD
[14 empty] | 15.6% (+10.6%) | 15.6% (+10.6%)
[14 empty] | 9 | 9
[14 empty] | 7.2 | 7.2
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE - RAN and CN
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 4,6 and 7 |  | Introduction of Signalling and RRM test environment and IEs if needed. |  | RAN5#92 (Aug-21) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
Layer 2
2 | Y | 36.523-1 | 7.1.3.5.6 | PDCP handover / DAPS handover with key change / Status reporting | **** TP1: [TS 36.323, 4.2.1, 5.6] WITH: UE in RRC_CONNECTED state and supporting DAPS handover WHEN: UE received RRCConnectionReconfiguration message includes the mobilityControlInfo for DAPS handover with key change THEN: PDCP entity associated with a DAPS bearer shall perform ciphering/deciphering under two sets of keys **** TP2: [TS 36.323 clause 5.3.1] WITH: UE in RRC_CONNECTED state and supporting DAPS handover and received RRCConnectionReconfiguration message includes the mobilityControlInfo for DAPS handover with key change WHEN: upper layers request uplink data switching during DAPS handover THEN: UE shall send a PDCP status report for the DAPS bearer **** TP3: [TS 36.323 clause 5.3.1] WITH: UE in RRC_CONNECTED state and supporting DAPS handover and received RRCConnectionReconfiguration message includes the mobilityControlInfo for DAPS handover with key change WHEN: upper layers reconfigure the PDCP entity to release DAPS and daps-SourceRelease is configured THEN: UE shall send a PDCP status report for the DAPS bearer | Ericsson | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  | 0% | 0%
RRC
|  | 36.523-1 | 8.2.4.30 | RRC connection reconfiguration / Handover / DAPS Handover | [5 empty] | 0
3 | Y | 36.523-1 | 8.2.4.30.1 | DAPS handover / Success | **** TP1: [TS 36.300 10.1.2.1 and 10.1.2.1.1 and TS 36.331 clause 5.3.5.4] WITH: UE in RRC_CONNECTED state and supporting DAPS handover WHEN: UE receives an RRCConnectionReconfiguration message includes the mobilityControlInfo for handover to the target cell and daps-HO is configured for any DRB THEN: UE performs DAPS handover to the target cell. For the DRB configured daps-HO, the UE continues to receive downlink data from both source and target eNBs for the DL and the UE transmits UL data to the source eNB. **** TP2: [TS 36.300 10.1.2.1] WITH: UE in RRC_CONNECTED state and supporting DAPS handover and having received RRCConnectionReconfiguration message includes the mobilityControlInfo for handover to the target cell and daps-HO is configured for any DRB WHEN: UE has performed random access procedure to the target cell successfully THEN: UE transmits an RRCReconfigurationComplete message and the UE switches its UL data transmission to the target eNB. **** TP3: [TS 36.300 clause 10.1.2.1.2 and TS 36.331 clause 5.3.5.3] WITH: UE in RRC_CONNECTED state and supporting DAPS handover and having received RRCConnectionReconfiguration message includes the mobilityControlInfo for handover to the target cell and daps-HO is configured for any DRB WHEN: UE receives an RRCConnectionReconfiguration message does not include the mobilityControlInfo and includes daps-SourceRelease THEN: UE stops to receive downlink data from source eNB and releases the radio link with source cell. | China Telecom | RAN5#92 (Aug-21) | R5-211452 |  | 1 | 80% (+80%) | 80% (+80%) |  | 80% | 80%
4 | Y | 36.523-1 | 8.2.4.30.2 | DAPS handover / Success / Radio Link Failure in source | **** TP1: [ TS 36.300 10.1.6, TS 36.331 clause 5.3.11.3] WITH: UE in RRC_CONNECTED state and supporting DAPS handover and having received RRCConnectionReconfiguration message includes the mobilityControlInfo for handover to the target cell and daps-HO is configured for any DRB WHEN: Timer T310 configured by using the value for target's timer T310 expires in source THEN: UE stops any data transmission or reception via the source link and releases the source link, but maintains the source RRC configuration and continue the handover procedure to target **** TP2: [ TS 36.300 10.1.6, TS 36.331 clause 5.3.11.3.] WITH: UE in RRC_CONNECTED state and supporting DAPS handover and having received RRCConnectionReconfiguration message includes the mobilityControlInfo for handover to the target cell and daps-HO is configured for any DRB WHEN: random access problem indication from source MCG MAC THEN: UE stops any data transmission or reception via the source link and releases the source link, but maintains the source RRC configuration and continue the handover procedure to target **** TP3: [ TS 36.300 10.1.6, TS 36.331 clause 5.3.11.3] WITH: UE in RRC_CONNECTED state and supporting DAPS handover and having received RRCConnectionReconfiguration message includes the mobilityControlInfo for handover to the target cell and daps-HO is configured for any DRB WHEN: indication from source MCG RLC, which is allowed to be sent on source PCell, that the maximum number of retransmissions has been reached for an DRB THEN: UE stops any data transmission or reception via the source link and releases the source link, but maintains the source RRC configuration and continue the handover procedure to target | ZTE | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  | 0% | 0%
5 | Y | 36.523-1 | 8.2.4.30.3 | DAPS handover / Failure / source link available / Radio Link Failure in source | **** TP1: [ TS 36.300 10.1.2.1, TS 36.331 clause 5.3.5.6 and 5.6.21] WITH: UE in RRC_CONNECTED state and supporting DAPS handover and having received RRCConnectionReconfiguration message includes the mobilityControlInfo for handover to the target cell and daps-HO is configured for any DRB WHEN: T304 expires (handover failure) and radio link failure has not been detected for the source MCG THEN: The UE falls back to source cell configuration, resumes the connection with source cell, and reports the DAPS handover failure via the source without triggering RRC connection re-establishment **** TP2: [ TS 36.300 clause 10.1.2.1, TS 36.331 clause 5.3.5.6 and 5.3.7] WITH: UE in RRC_CONNECTED state and supporting DAPS handover and having received RRCConnectionReconfiguration message includes the mobilityControlInfo for handover to the target cell and daps-HO is configured for any DRB and T304 expires (handover failure) and radio link failure has been detected for the source MCG WHEN: UE perform RRC re-establishment and selecting a suitable E-UTRA cell while T311 is running THEN: UE stays in RRC_CONNECTED and selects a suitable cell and then initiates RRC re-establishment **** TP3: [ TS 36.300 clause 10.1.2.1, TS 36.331 clause 5.3.5.6, clause 5.3.7.6] WITH: UE in RRC_CONNECTED state and supporting DAPS handover and having received RRCConnectionReconfiguration message includes the mobilityControlInfo for handover to the target cell and daps-HO is configured for any DRB and T304 expires (handover failure) and radio link failure has been detected for the source MCG WHEN: UE can not find a suitable cell before T311 expires THEN: UE enters RRC_IDLE | ZTE | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  | 0% | 0%
|  | 36.523-1 | 8.2.4.31 | RRC connection reconfiguration / Handover / Conditional Handover | [5 empty] | 0
6 | Y | 36.523-1 | 8.2.4.31.1 | Conditional handover / Success / A3 / A5 / A3+A5 | **** TP1: [TS 36.300 clause 10.1.2.1a, TS 36.331 clause 5.3.5.2, 5.3.5.3] WITH: UE in RRC_CONNECTED state and supporting conditional handover and receiving RRCConnectionReconfiguration message includes the conditionalReconfiguration WHEN: any CHO execution condition is not satisfied THEN: UE maintains connection with source gNB and starts evaluating the CHO execution conditions for the candidate cell(s) **** TP2: [ TS 36.300 clause 10.1.2.1a and TS 36.331 clause 5.3.5.2, 5.3.5.3, 5.3.5.9.4] WITH: UE in RRC_CONNECTED state and supporting conditional handover WHEN: UE receives RRCConnectionReconfiguration message includes the conditionalReconfiguration and ony event A3 is configured as conditional handover trigger event THEN: UE starts evaluating the CHO execution condition A3 and perform conditional handover to the neighbor cell triggered in conditional configuration execution **** TP3: [ TS 36.300 clause 10.1.2.1a and TS 36.331 clause 5.3.5.2, 5.3.5.3, 5.3.5.9.4] WITH: UE in RRC_CONNECTED state and supporting conditional handover WHEN: UE receives RRCConnectionReconfiguration message includes the conditionalReconfiguration and ony event A5 is configured as conditional handover trigger event THEN: UE starts evaluating the CHO execution condition A5 and perform conditional handover to the neighbor cell triggered in conditional configuration execution **** TP4: [ TS 36.300 clause 10.1.2.1a and TS 36.331 clause 5.3.5.2, 5.3.5.3, 5.3.5.9.4] WITH: UE in RRC_CONNECTED state and supporting conditional handover WHEN: UE receives RRCConnectionReconfiguration message includes the conditionalReconfiguration and both event A3 and event A5 are configured as conditional handover trigger events THEN: UE starts evaluating the CHO execution condition A3 and A5 and perform conditional handover to the neighbor cell triggered in conditional configuration execution **** TP5: [ TS 36.300 clause 10.1.2.1a ] WITH: UE in RRC_CONNECTED state and supporting conditional handover WHEN: UE perform conditional handover procedure successfully THEN: UE releases the stored CHO configurations after successful completion of RRC handover procedure. | China Telecom | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  | 0% | 0%
7 | Y | 36.523-1 | 8.2.4.31.2 | Conditional handover / modify conditional handover configuration | **** TP1: [ TS 36.300 clause 10.1.2.1a and TS 36.331 clause 5.3.5.3, 5.3.5.9.1, 5.3.5.9.2 ] WITH: UE in RRC_CONNECTED state and supporting conditional handover and receiving RRCConnectionReconfiguration message includes the conditionalReconfiguration WHEN: UE received another conditionalReconfiguration includes the condReconfigurationToRemoveList before any CHO execution condition is satisfied THEN: UE remove the entry with the matching condReconfigurationId from the condReconfigurationList within the VarConditionalReconfiguration **** TP2: [ TS 36.300 clause 10.1.2.1a and TS 36.331 clause 5.3.5.3, 5.3.5.9.1, 5.3.5.9.3 ] WITH: UE in RRC_CONNECTED state and supporting conditional handover and receiving RRCConnectionReconfiguration message includes the conditionalReconfiguration WHEN: UE received another conditionalReconfiguration includes the condReconfigurationToAddModList before any CHO execution condition is satisfied THEN: UE perform the conditional reconfiguration addition/modification procedure | Huawei, HiSilicon | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  | 0% | 0%
8 | Y | 36.523-1 | 8.2.4.31.3 | Conditional handover / Failure | **** TP1: [ TS 36.300 clause 10.1.2.1 and TS 38.331 clause 5.3.5.5.2, 5.3.5.3 and 5.3.7.3] WITH: UE in RRC_CONNECTED state and supporting conditional handover and network configured the UE to try CHO after HO/CHO failure and UE receiving an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE detects conditional handover failure and performs cell selection to a CHO candidate cell before T311 expires THEN: UE perform conditional handover to the selected cell **** TP2: [ TS 36.300 clause 10.1.2.1 and TS 38.331 clause 5.3.5.5.2, 5.3.5.3 and 5.3.7.3] WITH: UE in RRC_CONNECTED state and supporting conditional handover and network configured the UE to try CHO after HO/CHO failure and UE receiving an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE detects conditional handover failure and only finds a selectable cell which is not the candidate cell included in ConditionalReconfiguration before T311 expires THEN: UE initiate the connection re-establishment procedure in the selected cell **** TP3: [ TS 36.300 clause 10.1.2.1 and TS 38.331 clause 5.3.5.5.2, 5.3.5.3 and 5.3.7.6] WITH: UE in RRC_CONNECTED state and supporting conditional handover and network configured the UE to try CHO after HO/CHO failure and UE receiving an RRCReconfiguration message including a ConditionalReconfiguration WHEN: UE detects conditional handover failure and can not find any selectable cell before T311 expires THEN: UE goes to RRC_IDLE and release the stored conditional handover configurations | Huawei, HiSilicon | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 36.523-2: Applicability for Protocol test cases
9 |  | 36.523-2 | 4 |  | Add test case applicability statements for the new test cases introduced in 36.523-1 | All companies. | RAN5#92 (Aug-21) | For WP Item #3: R5-211453 |  | 0.1 | 5% (+5%) | 5% (+5%) |  | 5% | 5%
E-UTRA RF/RRM
TS 36.521-2: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 36.531-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 36.521-3: RRM test cases
|  | 36.531-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TR 36.903: Test Tolerances analysis RRM test cases
|  | 36.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.