## Cover sheet
3GPP TSG-RAN WG5 Meeting #90-e | [10 empty] | R5-211287
Electronic Meeting, 22nd February - 5th March 2021
Agenda Item: | 7.4.2
Source: | Nokia
Title: | WP UE Conformance Test Aspects - Enhancing LTE CA Utilization
Work item code: | LTE_euCA-UEConTest
Release: | Rel-15
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#82 meeting in Sorrento, Italy, RAN5 work item UE Conformance Test Aspects – Enhancing LTE CA Utilization was approved [1]. The purpose of this present document is to provide a work plan for the RAN5 work item for this. The work plan is updated after each RAN5 meeting to give the status of this work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 56% (+21%) | 9 (+3) | 18 (+2)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 56% (+3.5%) | 9 (+3) | 18 (+2)
FDD |  | 66.1% (+13.6%) | 9 (+3) | 14 (+2)
TDD |  | 45.8% (-6.7%) | 6 | 12
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
Applicability RF, Demod/QSI and RRM test cases | 36.521-2 | 20% (+20%) |  |  | 40% (+40%) |  |  | 0%
RRM test cases | 36.521-3 | 18.8% (+18.8%) | 3 (+3) | 12 (+2) | 37.5% (+37.5%) | 3 (+3) | 8 (+2) | 0% | 0 | 6
Test Tolerances analysis RRM test cases | 36.903
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 100% | 6 | 6 | 100% | 6 | 6 | 100% | 6 | 6
Applicability Protocol test cases | 36.523-2 | 100% |  |  | 100% |  |  | 100%
Test suites (TTCN) | 36.523-3
5 References
[1] RP-182619 | New WI Proposal: New WID on UE Conformance Test Aspects- Enhancing LTE CA Utilization
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - Enhancing LTE CA Utilization | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_euCA-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item Enhancing LTE CA Utilization comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [12 empty] | vs Area
WP Resp: |  | Matti Kangas, Nokia |  |  | matti.kangas@nokia.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD | TDD | FDD + TDD
[14 empty] | 66.1% (+13.6%) | 45.8% (-6.7%)
[14 empty] | 16 (+2) | 16 (+2) | 0
[14 empty] | 14.2 (+2) | 14.2 (+2) | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.508 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.508 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
E-UTRA RF/RRM
TS 36.521-2: Applicability for RF, Demod/QSI reporting and RRM test cases
1 |  | 36.521-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.101-x and 38.533. |  | RAN5#90-e (Feb-21) |  |  | 0.1 | 20% (+20%) | 20% (+20%) |  | 40% | 0%
TS 36.521-3: RRM test cases
|  | 36.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 | Y | 36.521-3 | <Clause> | Hibernation and Activation of Known SCell in Non-DRX with generic duplex modes | Adding test case to verify that the SCell hibernation and activation delays are within the requirements for UE configured with a single downlink SCell, when the SCell is known by the UE at the time of hibernation and activation. TS 36.133, A.8.16.103 | Nokia | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0% | 0%
2 | Y | 36.521-3 | <Clause> | Hibernation and Activation of Unknown SCell in Non-DRX with generic duplex modes | Adding test case to verify that the SCell hibernation and activation delays are within the requirements for UE configured with a single downlink SCell, when the SCell is unknown by the UE at the time of hibernation and activation. TS 36.133, A.8.16.104 | Nokia | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0% | 0%
3 | Y | 36.521-3 | 9.1.1.1_3 | FDD Intra Frequency Absolute RSRP Accuracy for CA Idle Mode Measurements | Adding test case for verifying FDD intra-frequency RSRP absolute accuracy of the RRC_IDLE mode measurements. TS 36.133, 9.1.2B | Nokia | RAN5#90-e (Feb-21) |  |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
4 | Y | 36.521-3 | 9.1.2.1_3 | TDD Intra Frequency RSRP Accuracy CA Idle Mode Measurements | Adding test case for verifying TDD intra-frequency RSRP absolute accuracy of the RRC_IDLE mode measurements. TS 36.133, 9.1.2B | Nokia | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
5 | Y | 36.521-3 | 9.1.3.1_3 | FDD-FDD Inter Frequency Absolute RSRP Accuracy for CA Idle Mode Measurements for Overlapping Carrier | Adding test case for verifying FDD - FDD inter-frequency RSRP absolute accuracy of the RRC_IDLE mode measurements for overlapping carriers. TS 36.133, 9.1.3B | Nokia | RAN5#90-e (Feb-21) |  |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
6 | Y | 36.521-3 | 9.1.3.1_4 | FDD-FDD Inter Frequency Absolute RSRP Accuracy for CA Idle Mode Measurements for Non-Overlapping Carrier | Adding test case for verifying FDD - FDD inter-frequency RSRP absolute accuracy of the RRC_IDLE mode measurements for non-overlapping carriers. TS 36.133, 9.1.3B | Nokia | RAN5#90-e (Feb-21) |  |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
7 | Y | 36.521-3 | 9.1.4.1_3 | TDD-TDD Inter Frequency Absolute RSRP Accuracy for CA Idle Mode Measurements for Overlapping Carrier | Adding test case for verifying TDD - TDD inter-frequency RSRP absolute accuracy of the RRC_IDLE mode measurements for overlapping carriers. TS 36.133, 9.1.3B | Nokia | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  |  | 0%
8 |  | 36.521-3 | 9.1.4.1_4 | TDD-TDD Inter Frequency Absolute RSRP Accuracy for CA Idle Mode Measurements for Non-Overlapping Carrier | Adding test case for verifying TDD - TDD inter-frequency RSRP absolute accuracy of the RRC_IDLE mode measurements for non-overlapping carriers. TS 36.133, 9.1.3B | Nokia | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
9 | Y | 36.521-3 | 9.2.1.1_3 | FDD Intra Frequency Absolute RSRQ Accuracy for CA Idle Mode Measurements | Adding test case for verifying FDD intra-frequency RSRQ absolute accuracy of the RRC_IDLE mode measurements. TS 36.133, 9.1.5B | Nokia | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  | 0%
10 | Y | 36.521-3 | 9.2.2.1_3 | TDD Intra Frequency Absolute RSRQ Accuracy for CA Idle Mode Measurements | Adding test case for verifying TDD intra-frequency RSRQ absolute accuracy of the RRC_IDLE mode measurements. TS 36.133, 9.1.5B | Nokia | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
11 | Y | 36.521-3 | 9.2.3.1_3 | FDD-FDD Inter Frequency Absolute RSRQ Accuracy for CA Idle Mode Measurements for Overlapping Carrier | Adding test case for verifying FDD - FDD inter-frequency RSRQ absolute accuracy of the RRC_IDLE mode measurements for overlapping carriers. TS 36.133, 9.16B | Nokia | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  | 0%
12 | Y | 36.521-3 | 9.2.3.1_4 | FDD-FDD Inter Frequency Absolute RSRQ Accuracy for CA Idle Mode Measurements for Non-Overlapping Carrier | Adding test case for verifying FDD - FDD inter-frequency RSRQ absolute accuracy of the RRC_IDLE mode measurements for non-overlapping carriers. TS 36.133, 9.16B | Nokia | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  | 0%
13 |  | 36.521-3 | 9.2.4.1_3 | TDD-TDD Inter Frequency Absolute RSRQ Accuracy for CA Idle Mode Measurements for Overlapping Carrier | Adding test case for verifying FDD - FDD inter-frequency RSRQ absolute accuracy of the RRC_IDLE mode measurements for overlapping carriers. TS 36.133, 9.16B | Nokia | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
14 | Y | 36.521-3 | 9.2.4.1_4 | TDD-TDD Inter Frequency Absolute RSRQ Accuracy for CA Idle Mode Measurements for Non-Overlapping Carrier | Adding test case for verifying TDD - TDD inter-frequency RSRQ absolute accuracy of the RRC_IDLE mode measurements for overlapping carriers. TS 36.133, 9.1.6B | Nokia | RAN5#91-e (May-21) |  |  | 1 | 0% | 0% |  |  | 0%
TR 36.903: Test Tolerances analysis RRM test cases
|  | 36.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Layer 2
12 | Y | 36.523-1 | 7.1.13.1.1 | Modifying SCell in dormant state | 1. Modifying SCell in activated state to dormant state after receiving hibernation MAC CE having Ci = “1” with i being same as servingCellIndex of SCell. TS 36.321, 5.22, 6.1.3.15 2. Modifying SCell in activated state to dormant state after sCellHibernationTimer associated with SCell expires. TS 36.321, 5.13, 5.22, 6.1.3.15 3. Modifying SCell in dormant state to deactivated state after receiving both hibernation and activation/deactivation MAC CE having Ci = “0” with i being same as servingCellIndex of SCell. TS 36.321, 5.22, 6.1.3.15 4. Modifying SCell in dormant state to deactivated state after dormantSCellDeactivationTimer associated with SCell expires. TS 36.321, 5.22, 6.1.3.15 | Nokia | RAN5#84-e (Aug-19) | R5-197182 |  | 1 | 100% | 100% |  | 100% | 100%
RRC
13 | Y | 36.523-1 | 8.1.3.14 | Reporting of UE IDLE mode measurement results after receiving RRCConnectionRelease message including measIdleConfig with measIdleCarrierListEUTRA information and SIB2 idleModeMeasurements is true. | Add test case for reporting of UE RRC_IDLE mode cell measurement results, while RRCConnectionRelease message provides measurement information and SIB2 indicates that eNB is capable of processing measurement results. TS 36.331, 5.3.8.3, 5.6.20 | Nokia | RAN5#84-e (Aug-19) | R5-195205 |  | 1 | 100% | 100% |  | 100% | 100%
14 | Y | 36.523-1 | 8.1.3.15 | Reporting of UE IDLE mode measurement results after receiving RRCConnectionRelease message including measIdleConfig with measIdleCarrierListEUTRA information and SIB2 idleModeMeasurements is false. | Add test case for reporting of UE RRC_IDLE mode cell measurement results, while RRCConnectionRelease message provides measurement information and SIB2 indicates that eNB is NOT capable of processing measurement results. TS 36.331, 5.3.8.3, 5.6.20 | Nokia | RAN5#84-e (Aug-19) | R5-195206 |  | 1 | 100% | 100% |  | 100% | 100%
15 | Y | 36.523-1 | 8.1.3.13 | Reporting of UE IDLE mode measurement results after receiving RRCConnectionRelease message including measIdleConfig and SIB5 includes measIdleCarrierListEUTRA information and SIB2 idleModeMeasurements is true. | Add test case for reporting of UE RRC_IDLE mode cell measurement results, while RRCConnectionRelease message provides measurement information together with SIB5 and SIB2 indicates that eNB is capable of processing measurement results. TS 36.331, 5.3.8.3, 5.6.20 | Nokia | RAN5#84-e (Aug-19) | R5-195204 |  | 1 | 100% | 100% |  | 100% | 100%
16 | Y | 36.523-1 | 8.2.2.13.1 | Addition of SCell in dormant state | 1. Addition of SCell in dormant state after receiving RRCConnectionReconfiguration message including sCellToAddModList and sCellState indicates dormant. TS 36.331, 5.3.5.3, 5.3.10.3b 2. Maintaining SCell in dormant state after receiving RRCConnectionReconfiguration message including mobilityControlInfo and sCellState indicates dormant. TS 36.331, 5.3.5.4 3. Addition of SCell in dormant state after receiving RRCConnectionReconfiguration message including mobilityControlInfo and sCellToAddModList and sCellState indicates dormant. TS 36.331, 5.3.5.4, 5.3.10.3b | Nokia | RAN5#84-e (Aug-19) | R5-197181 |  | 1 | 100% | 100% |  | 100% | 100%
17 | Y | 36.523-1 | 8.2.2.14.1 | Addition of the SCell in activated state | 1. Addition of SCell in activated state after receiving RRCConnectionReconfiguration not including mobilityControlInfo and including sCellToAddModList together with sCellState indicating activated. TS 36.331, 5.3.5.3, 5.3.10.3b 2. Addition of the SCell in activated state after receiving RRCConnectionReconfiguration including mobilityControlInfo and sCellToAddModList together with sCellState indicating activated. TS 36.331, 5.3.5.3, 5.3.10.3b 3. Maintaining SCell in activated state after receiving RRCConnectionReconfiguration including mobilityControlInfo and sCellToAddModList together with sCellState indicating activated. TS 36.331, 5.3.5.3, 5.3.10.3b | Nokia | RAN5#84-e (Aug-19) |  |  | 1 | 100% | 100% |  | 100% | 100%
TS 36.523-2: Applicability for Protocol test cases
18 |  | 36.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#84-e (Aug-19) |  |  | 0.1 | 100% | 100% |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.