## Summary
Work plan summary:
IMS over 5G (TS 34.229-5)
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| IMS over 5G (TS 34.229-5) | SA Option 2 (SA NR) | 42.79% | 42.79% | 42.79%
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)
Test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of test cases applicable for FR1+FR2
|  |  | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed
| IMS over 5G (TS 34.229-5) | SA Option 2 (SA NR) | 121 | 38 | 121 | 38 | 121 | 38
NSA Option 3 (EN-DC)
SA Option 5
NSA Option 4 (NE-DC)
NSA Option 7 (NGEN-DC)

## Protocol IMS 5GS
WP Title: | IMS over 5G (TS 34.229-5) | [10 empty] | WP item applicability
RAN-CN interface options dependency
WP Scope: | This work plan section covers the IMS over 5G protocol test cases in TS 34.229-5 for SA option 2. | [10 empty] | 5GC/NR |  | 5GC/LTE | EPC/LTE | 5GC/NR master | 5GC / LTE master
WP Resp: | Hans Rohnert |  |  |  | hans.rohnert@rohde-schwarz.com
TS Resp: | Hans Rohnert |  |  |  | hans.rohnert@rohde-schwarz.com | [6 empty] | SA |  |  | NSA
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 | Opt. 3 | Opt. 4 | Opt. 7
[11 empty] | Overall | 42.79%
Phase 1
Phase 2
Phase 3
[11 empty] | Phase 4 | 100%
Phase 5
Phase 6
[11 empty] | Phase 7 | 100%
[11 empty] | Phase 8 | 100%
[11 empty] | Phase 9 | 100%
[11 empty] | Phase 10 | 100%
[11 empty] | Phase 11 | 6.826%
Phase 12
[7 empty] | Overall #WP items: Phase 1 #WP items: Phase 2 #WP items: Phase 3 #WP items: Phase 4 #WP items: Phase 5 #WP items: Phase 6#WP items: Phase 7#WP items: Phase 8#WP items: Phase 9#WP items: Phase 10#WP items: Phase 11#WP items: Phase 12#WP items: |  |  |  |  | 136 0 0 0 19 0 0 10 7 19 15 66 0 |  | 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [11 empty] | Phase number (1,2 etc) and completion (%) per option
Generic Procedures
1 |  | 34.229-1 | A.1.1 | REGISTER | Adapt REGISTER as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
2 |  | 34.229-1 | A.1.4 | SUBSCRIBE | Adapt SUBSCRIBE as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
3 |  | 34.229-1 | A.2.1 | MO INVITE | Adapt MO INVITE as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
4 |  | 34.229-1 | A.2.4 | PRACK | Adapt PRACK as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
5 |  | 34.229-1 | A.2.5 | UPDATE | Adapt UPDATE as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
6 |  | 34.229-1 | A.2.6 | 180 RINGING | Adapt 180 RINGING as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
7 |  | 34.229-1 | A.2.8 | BYE | Adapt BYE as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
8 |  | 34.229-1 | A.2.10 | MO REFER | Adapt MO REFER as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
9 |  | 34.229-1 | A.2.12 | MT REFER | Adapt MT REFER as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
10 |  | 34.229-1 | A.3.1 | 200 OK | Adapt 200 OK as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
11 |  | 34.229-1 | A.4.3 | PUBLISH | Adapt PUBLISH as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
12 |  | 34.229-1 | A.5.1 | SUBSCRIBE for conference event | Adapt SUBSCRIBE for conference event as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
13 |  | 34.229-1 | A.6.1 | SUBSCRIBE for message summary | Adapt SUBSCRIBE for message summary as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
14 |  | 34.229-1 | A.7.3 | MESSAGE for MO SMS | Adapt MESSAGE for MO SMS as needed for 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
15 |  | 34.229-1 | A.8.2 | MESSAGE UE providing information for CS to PS SRVCC | Adapt MESSAGE UE providing information for CS to PS SRVCC | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-193853 |  | 0.5 | 100% | 4 | 100%
16 |  | 34.229-5 | A.2 | IMS Registration / 5GS | IMS Registration in 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-195233, R5-203437, R5-205115, R5-205585 |  | 0.5 | 100% | 4 | 100%
17 |  | 34.229-5 | A.4 | MTSI MO Voice Call / 5GS | MO Voice Call over 5GS | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-195234, R5-195892, R5-202691, R5-205311, R5-210348 |  | 0.5 | 100% | 9 | 100%
18 |  | 34.229-5 | A.5 | MTSI MT Voice Call / 5GS | MT Voice Call over 5GS | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-202692, R5-203462, R5-205312, R5-210056 |  | 0.5 | 100% | 9 | 100%
19 |  | 34.229-5 | A.3 | IMS Emergency Registration / 5GS | IMS Emergency Registration in 5GS | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-195235, R5-204480 |  | 0.5 | 100% | 4 | 100%
20 |  | 34.229-5 | A.6 | IMS Emergency Voice Call / 5GS | Emergency call over 5GS | Rohde & Schwarz | Opt 2: RAN5#91 (May-21) | R5-195237, R5-205518 | SDP bodies to be checked | 0.5 | 60% | 11 | 60%
21 |  | 34.229-1 | C.32b | MO release of IMS call | When UE needs to release a voice call over NR | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-196034 |  | 0.5 | 100% | 4 | 100%
22 |  | 34.229-2 | A.4.10 | 5G capability | Adding 5G capability | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) | R5-195232, R5-195897 |  | 0.5 | 100% | 4 | 100%
37 |  | 34.229-5 | A.7 | MO release of IMS session | New generic procedure where UE releases the IMS session | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-197746, R5-205219 |  | 0.5 | 100% | 7 | 100%
36 |  | 34.229-5 | A.8 | MT release of IMS session | New generic procedure where SS releases the IMS session | Rohde & Schwarz | Opt 2: RAN5#88 (Aug-20) | R5-203439 |  | 0.5 | 100% | 8 | 100%
75 |  | 34.229-5 | A.9 | EPS Fallback for Voice Call | New generic procedure replacing preliminary procedure in TS 34.229-1 | Rohde & Schwarz | Opt 2: RAN5#88 (Aug-20) | R5-204484, R5-205113, R5-211437 |  | 0.5 | 100% | 8 | 100%
128 |  | 34.229-5 | A.10 | PUBLISH | New generic procedure for PUBLISH | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-205115 |  | 0.5 | 100% | 9 | 100%
129 |  | 34.229-5 | A.11 | Mobile Initiated De-Registration / 5GS | New generic procedure as 5G equivalent of Appendix C.30 of TS 34.229-1 | Rohde & Schwarz | Opt 2: RAN5#90 (Feb-21) | R5-206373, R5-210259 |  | 0.5 | 100% | 10 | 100%
130 |  | 34.229-5 | A.12 | IMS Re-Registration / 5GS | New generic procedure as 5G equivalent of Appendix C.46 of TS 34.229-1 | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-205185 |  | 0.5 | 100% | 9 | 100%
131 |  | 34.229-5 | A.13 | Mobile Originating SMS / 5GS | New generic procedure for Mobile Originating SMS over 5GS | Keysight | Opt 2: RAN5#89 (Nov-20) | R5-206374 |  | 0.5 | 100% | 9 | 100%
132 |  | 34.229-5 | A.14 | Mobile Terminating SMS / 5GS | New generic procedure for Mobile Terminating SMS over 5GS | Keysight | Opt 2: RAN5#89 (Nov-20) | R5-206374 |  | 0.5 | 100% | 9 | 100%
138 |  | 34.229-5 | A.15 | Mobile Originating Video Call / 5 | New generic procedure for Mobile Originating Video Call over 5GS | Qualcomm | Opt 2: RAN5#90 (Feb-21) | R5-211433 |  |  | 100% | 10 | 100%
133 |  | 34.229-1 | A.1.9 | 403 Forbidden for REGISTER | New generic procedure for 403 FORBIDDEN response for REGISTER | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-205210 |  |  | 100% | 9 | 100%
134 |  | 34.229-1 | A.2.25 | 420 Bad Extension for INVITE | New generic procedure for 420 Bad Extension response for INVITE | ZTE | Opt 2: RAN5#89 (Nov-20) | R5-206370 |  |  | 100% | 9 | 100%
Test cases Option 2 - NR access to 5GC
Registration
23 | Y | 34.229-5 | 6.1 | Initial Registration / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE has an ISIM or USIM inserted, is registered for 5GS, and has acquired P-CSCF address(es) WHEN: UE is made to register for IMS THEN: UE sends a correctly composed initial REGISTER request to the P-CSCF **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent an unprotected REGISTER request WHEN: UE receiving a valid 401 (Unauthorized) response for the initial REGISTER request sent THEN: UE correctly authenticates itself by sending another REGISTER request with a correctly composed Authorization header using the AKAv1-MD5 algorithm **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent unprotected and then protected REGISTER request WHEN: UE receiving a valid 200 OK response from S-CSCF for the REGISTER sent for authentication THEN: UE subscribes to the reg event package for the public user identiy registered, using the stored service route for routing the SUBSCRIBE request **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having subscribed to reg event WHEN: UE receives NOTIFY request for reg event THEN: UE responds with a valid 200 OK response | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-197049, R5-197934, R5-202686, R5-203442, R5-206383 |  | 1 | 100% | 7 | 100%
24 | Y | 34.229-5 | 6.2 | Initial Registration Failures / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent unprotected REGISTER request WHEN: UE receiving a 503 (Service Unavailable) response without Retry-After header for the unprotected REGISTER request sent THEN: UE waits at most 5 minutes and then sends another unprotected REGISTER request **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent an unprotected REGISTER request WHEN: UE receiving a 503 (Service Unavailable) response with Retry-After header for the initial REGISTER request sent THEN: UE waits until interval given is up and then sends another unprotected REGISTER request **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent unprotected REGISTER request WHEN: UE receiving a 423 (Interval Too Brief) response THEN: UE sends another unprotect REGISTER request with new expiration interval | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-198899, R5-198239, R5-202687, R5-203443 | outstanding CT1 response | 1 | 100% | 7 | 100%
25 | Y | 34.229-5 | 6.3 | Re-Registration Scenarios / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS with expiration interval at 120 seconds WHEN: 60 seconds passed THEN: UE re-registers **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE starting re-registration procedure by sending initial REGISTER WHEN: UE receives 500 Server Internal Error response THEN: UE starts initial registration **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS with expiration interval at 360 seconds WHEN: 180 seconds passed THEN: UE re-registers **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS with expiration interval at 1300 seconds WHEN: 700 seconds passed THEN: UE re-registers **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE attempting re-registration WHEN: UE receives 423 Interval Too Brief response THEN: UE sends REGISTER with given expiration interval **** TP6: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered WHEN: UE receives notification about shortened expiration interval for one of its registered public user identities THEN: UE re-registers after half of the shorted expiration interval elapses | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-198240, R5-202688, R5-204481, R5-210057 |  | 1 | 100% | 7 | 100%
26 | Y | 34.229-5 | 6.4 | De-Registration Scenarios / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: a REFRESH command happens THEN: UE waits for the network to deregister the UE from IMS **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE receiving a NOTIFY request containing deregistration information with contact elements being "deactivated" THEN: UE acknowledges deregistration **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being deregistered from IMS by the network with contact elements being "deactivated" WHEN: UE acknowledging deregistration THEN: UE performs initial registration to IMS **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE is made to deregister its contact address THEN: UE performs deregistration from IMS | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) | R5-198241, R5-202689, R5-203445, R50210095 |  | 1 | 100% | 7 | 100%
27 | Y | 34.229-5 | 6.5 | Refresh for ISIM parameters / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE receives indication that contents of USIM/ISIM has been updated THEN: UE does not deregister from IMS **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE waiting for network-initiated deregistration WHEN: UE receives NOTIFY request for reg event THEN: UE responds with a valid 200 OK response and initiates new IMS registration | HiSilicon | Opt 2: RAN5#87 (May-20) | R5-202678, R5-203447 | (LTE 8.15) 24.229 cl 5.1.1.7, C.4 | 1 | 100% | 7 | 100%
66 | Y | 34.229-5 | 6.6 | Re-Registration after capability update / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE is made to update its capabilities THEN: UE re-registers | HiSilicon | Opt 2: RAN5#87 (May-20) | R5-202679, R5-203448, R5-205217 | 24.229 cl 5.1.1.4.1 | 1 | 100% | 7 | 100%
28 | Y | 34.229-5 | 6.7 | Authentication / MAC Parameter Invalid / Only two consecutive invalid challenges / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE starting registration procedure WHEN: UE receiving invalid MAC parameter THEN: UE sends another REGISTER request without challenge response AUTS and populates a new Security-Client header **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having responded to invalid MAC parameter WHEN: UE receives another invalid MAC parameter THEN: UE sends another REGISTER request without challenge response AUTS and populates a new Security-Client header **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having responded to invalid MAC parameter twice WHEN: UE receives an invalid MAC parameter for a third time THEN: UE does not send another REGISTER request | HiSilicon | Opt 2: RAN5#87 (May-20) | R5-202680, R5-203452, R5-206386 | (LTE 9.1) + 24.229 cl 5.1.1.5.12 | 1 | 100% | 7 | 100%
29 | Y | 34.229-5 | 6.8 | Authentication / Security-Server missing / SQN out of range / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE starting registration procedure WHEN: UE receiving a challenge response without Security-Server header THEN: UE abandons the authentication procedure and sends a new REGISTER request with new Call-ID **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent a new initial REGISTER request WHEN: UE receiving a challenge response with SQN out of range THEN: UE sends another REGISTER request with challenge response AUTS and populates a new Security-Client header | HiSilicon | Opt 2: RAN5#87 (May-20) | R5-202681, R5-203453 | 24.229 cl 5.1.1.5.1 + (LTE 9.2) | 1 | 100% | 7 | 100%
30 | Y | 34.229-5 | 6.9 | Subscription / 503 Service Unavailable / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE subscribing to reg event WHEN: UE receives 503 Service unavailable containg a Retry-After header field THEN: UE does not reattempt the request for the indicated time period | HiSilicon | Opt 2: RAN5#87 (May-20) | R5-202682, R5-203454 | (LTE 10.1) | 1 | 100% | 7 | 100%
Call Control
32 | Y | 34.229-5 | 7.1 | MTSI MO Voice Call / 503 Service Unavailable / 5GS | Editor's note: Test case to work for both preconditions enabled and disabled **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] WITH: UE having sent an initial INVITE request for MO Voice call WHEN: UE receiving a 503 Service Unavailable response containing a Retry-After header indicating a period of 60 seconds THEN: UE does not reattempt the request until after the indicated period **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] WITH: UE waiting for period of 60 seconds to expire WHEN: Period expires THEN: UE sends initial INVITE request and completes setup of MO Voice call | Qualcomm | Opt 2: RAN5#89 (Nov-20) | R5-206385, R5-210882 | (LTE 12.2) | 1 | 100% | 9 | 100%
31 | Y | 34.229-5 | 7.2 | MTSI MO Voice Call / 504 Server Time-out / 5GS | Editor's note: Test case to work for both preconditions enabled and disabled **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent an INVITE request WHEN: UE receives 504 Server Time-out response THEN: UE performs initial registration to IMS | Qualcomm | Opt 2: RAN5#89 (Nov-20) | R5-206384, R5-211434 | (LTE 12.2a) | 1 | 100% | 9 | 100%
33 |  | 34.229-5 | 7.3 | Void | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE supporting preconditions and the precondition mechanism being enabled and UE having sent INVITE without preconditions WHEN: UE receives 421 Extension Required response with precondition option-tag in the Require header THEN: UE sends a new INVITE request using preconditions **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having received 200 OK for first PRACK request WHEN: Resources becoming available THEN: UE sends UPDATE request | HiSilicon |  | R5-206379, R5-210659 | Test Case voided by RAN5#90-e (was MTSI MO Voice Call / 421 Extension Required / 5GS) | 1
34 | Y | 34.229-5 | 7.4 | MTSI MO Voice Call with preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to use preconditions WHEN: UE is being made to initiate a voice call THEN: UE sends INVITE for voice call with preconditions **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE with preconditions WHEN: UE receives 100 Trying followed by 183 Session Progress THEN: UE sends PRACK for 183 Session Progress **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent PRACK WHEN: UE receives 200 OK for PRACK and resources are available THEN: UE sends UPDATE **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent UPDATE WHEN: UE receives 200 OK for UPDATE followed by 180 Ringing sent reliably THEN: UE sends PRACK for 180 Ringing **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent PRACK for 180 Ringing WHEN: UE receives 200 OK for PRACK followed by 200 OK for INVITE THEN: UE sends ACK **** TP6: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: FFS WHEN: FFS THEN: FFS | Rohde & Schwarz | Opt 2: RAN5#89 (Nov-20) | R5-202690, R5-206382, R5-211429, R5-210343 | (LTE 12.12/12.23), NG114 cl 2.2.4, 2.4.1 / could be changed to cover both possibilities at remote UE | 1 | 100% | 9 | 100%
38 | Y | 34.229-5 | 7.5 | MTSI MO Voice Call without preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to not use preconditions WHEN: UE is being made to initiate a voice call THEN: UE sends INVITE for voice call without preconditions **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE without precondtions WHEN: UE receives 183 Session Progress without preconditions THEN: UE sends PRACK for 183 Session Progress **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent PRACK WHEN: UE receives 200 OK for PRACK followed by 180 Ringing followed by 200 OK for INVITE THEN: UE sends ACK | HiSilicon | Opt 2: RAN5#89 (Nov-20) | R5-202683, R5-206382, R5-211429 | (LTE 12.12a/12.23), NG114 cl 2.2.4, 2.4.1 | 1 | 100% | 9 | 100%
35 | Y | 34.229-5 | 7.6 | MTSI MT Voice Call with preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE receives INVITE for voice call THEN: UE may respond with 100 Trying **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE receives INVITE for voice call THEN: UE responds with 183 Session Progress including SDP **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 183 Session Progress WHEN: UE receives PRACK for 183 Session Progress THEN: UE sends 200 OK for PRACK **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 200 OK for PRACK WHEN: UE receives UPDATE including SDP THEN: UE sends 200 OK for UPDATE including SDP and 180 Ringing **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 180 Ringing, possibly reliably WHEN: 180 was sent reliably and consequently UE receives PRACK for 180 Ringing THEN: UE sends 200 OK for PRACK **** TP6: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 180 Ringing WHEN: User accepts the incoming voice call request THEN: UE sends 200 OK for INVITE **** TP7: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 200 OK for INVITE WHEN: UE receives ACK followed by BYE THEN: UE sends 200 OK for BYE | HiSilicon | Opt 2: RAN5#89 (Nov-20) | R5-202684, R5-203441, R5-203461, R5-206382, R5-211429 | (LTE 12.13/12.24) NG114 cl 2.2.4, 2.4.1, 24.229 cl U.3.1.4 - investigate optionality | 1 | 100% | 9 | 100%
39 | Y | 34.229-5 | 7.7 | MTSI MT Voice Call without preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to not use preconditions WHEN: UE receives INVITE for voice call THEN: UE may respond with 100 Trying and then sends 183 Session Progress with SDP without preconditions **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 183 Session Progress WHEN: UE receives PRACK for 183 Session Progress THEN: UE sends 200 OK for PRACK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 200 OK for PRACK WHEN: UE is ready to start the call THEN: UE sends 180 Ringing followed by 200 OK for INVITE | HiSilicon | Opt 2: RAN5#89 (Nov-20) | R5-202685, R5-203441, R5-206382 | (LTE 12.13b/12.24) NG114 cl 2.2.4, 2.4.1, 24.229 cl U.3.1.4 | 1 | 100% | 9 | 100%
63 | Y | 34.229-5 | 7.8 | MTSI MT Voice Call without preconditions at originating UE and with preconditions at terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to use preconditions WHEN: UE receives INVITE for voice call without precondition option-tag in Require or Supported header THEN: UE completes setup of voice call without preconditions | ZTE | Opt 2: RAN5#89 (Nov-20) | R5-206375, R5-211429 | 24.229 cl 5.1.4.1, first bullet d). | 1 | 100% | 9 | 100%
64 | Y | 34.229-5 | 7.9 | MTSI MT Voice Call with preconditions at originating UE and without preconditions at terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to not use preconditions WHEN: UE receives INVITE for voice with preconditions THEN: UE completes setup of voice call without preconditions | ZTE | Opt 2: RAN5#89 (Nov-20) | R5-206376 | (LTE 12.13c) 24.229 cl 5.1.4.1, first bullet b) | 1 | 100% | 9 | 100%
45 | Y | 34.229-5 | 7.10 | MTSI MT Voice call without preconditions and without SDP offer in MT INVITE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to not use preconditions WHEN: UE receives INVITE for voice call not containing an SDP offer, but indicating support for reliable provisional responses THEN: UE sends 183 Session Progress reliably and containing an SDP offer **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 183 Session Progress WHEN: UE receives PRACK for 183 Session Progress THEN: UE sends 200 OK for PRACK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 200 OK for PRACK WHEN: UE is ready to start the call THEN: UE sends 180 Ringing followed by 200 OK for INVITE | HiSilicon | Opt 2: RAN5#89 (Nov-20) | R5-206381, R5-211436 | 24.229 cl U.3.1.4 | 1 | 100% | 9 | 100%
65 | Y | 34.229-5 | 7.11 | MTSI MT Voice call without preconditions at terminating UE and originating UE requiring them / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to not use preconditions WHEN: UE receives INVITE for voice call where remote UE requires usage of preconditions THEN: UE rejects INVITE with 420 Bad Extension response | ZTE | Opt 2: RAN5#89 (Nov-20) | R5-206377, R5-211435 | 24.229 cl 5.1.4.1, first bullet c) | 1 | 100% | 9 | 100%
127 | Y | 34.229-5 | 7.12 | MTSI MO Voice Call with preconditions at originating UE and without preconditions at terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to use preconditions WHEN: UE is being made to initate a voice call THEN: UE sends INVITE for voice call with preconditions **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE with precondtions WHEN: UE receives 183 Session Progress without preconditions THEN: UE sends PRACK for 183 Session Progress **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent PRACK WHEN: UE receives 200 OK for PRACK followed by 180 Ringing followed by 200 OK for INVITE THEN: UE sends ACK | HiSilicon | Opt 2: RAN5#89 (Nov-20) | R5-206380 | 24.229 cl 5.1.3, bullet b) | 1 | 100% | 9 | 100%
47 | Y | 34.229-5 | 7.13 | MTSI MT Voice Call with RTCP disabled / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE receives INVITE for voice call with both b=RS and b=RR attributes set to zero THEN: UE may respond with 100 Trying and then sends 183 Session Progress with SDP with both b=RS and b=RR set to zero | to be assigned | Opt 2: RAN5#91 (May-21) |  | NG114 cl 3.6.3 | 1 | 0% | 11 | 0%
40 | Y | 34.229-5 | 7.14 | MTSI MO Video call with preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to use preconditions WHEN: UE is being made to initiate a video call THEN: UE sends INVITE for video call with preconditions **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE with preconditions WHEN: UE receives 183 Session Progress THEN: UE sends PRACK for 183 Session Progress **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent PRACK WHEN: UE receives 200 OK for PRACK THEN: UE sends UPDATE **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent UPDATE WHEN: UE receives 200 OK for UPDATE followed by 180 Ringing sent reliably THEN: UE sends PRACK for 180 Ringing **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having send PRACK for 180 Ringing WHEN: UE receives 200 OK for PRACK followed by 200 OK for INVITE THEN: UE sends ACK | Qualcomm | Opt 2: RAN5#91 (May-21) | R5-211431 | (LTE 12.21), NG114 cl 2.2.4 | 1 | 60% | 11 | 60%
41 | Y | 34.229-5 | 7.15 | MTSI MO Video call without preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to not use preconditions WHEN: UE is being made to initiate a video call THEN: UE sends INVITE for video call without preconditions **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having send INVITE without preconditions WHEN: UE receives 183 Session Progress without preconditions THEN: UE sends PRACK for 183 Session Progress **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent PRACK WHEN: UE receives 200 OK for PRACK followed by 180 Ringing followed by 200 OK for INVITE THEN: UE sends ACK | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 12.21), NG114 cl 2.2.4 | 1 | 0% | 11 | 0%
42 | Y | 34.229-5 | 7.16 | MTSI MT Video call with preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE receives INVITE for video call THEN: UE may respond with 100 Trying **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE receives INVITE for video call THEN: UE responds with 183 Session Progress including SDP **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 183 Session Progress WHEN: UE receives PRACK for 183 Session Progress THEN: UE sends 200 OK for PRACK **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 200 OK for PRACK WHEN: UE receives UPDATE including SDP THEN: UE sends 200 OK for UPDATE including SDP and 180 Ringing **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 180 Ringing, possibly reliably WHEN: 180 Ringing was sent reliably and consequently UE receives PRACK for 180 Ringing THEN: UE sends 200 OK for PRACK **** TP6: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 180 Ringing WHEN: User accepts the incoming video call request THEN: UE sends 200 OK for INVITE **** TP7: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 200 OK for INVITE WHEN: UE receives ACK followed by BYE THEN: UE sends 200 OK for BYE | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 12.22) | 1 | 0% | 11 | 0%
43 | Y | 34.229-5 | 7.17 | MTSI MT Video call without preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to not use preconditions WHEN: UE receives INVITE for video call THEN: UE may respond with 100 Trying and then sends 183 Session Progress with SDP without preconditions **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 183 Session Progress WHEN: UE receives PRACK for 183 Session Progress THEN: UE sends 200 OK for PRACK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 200 OK for PRACK WHEN: UE is ready to start the call THEN: UE sends 180 Ringing followed by 200 OK for INVITE | Qualcomm | Opt 2: RAN5#91 (May-21) |  | (LTE 12.22) | 1 | 0% | 11 | 0%
48 | Y | 34.229-5 | 7.18 | MTSI MO Voice Call / EVS / AMR-WB / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to use preconditions WHEN: UE is being made to initiate a voice call THEN: UE sends INVITE for voice call with preconditions **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE with preconditions WHEN: UE receives 183 Session Progress indicating AMR-WB THEN: UE sends PRACK for 183 Session Progress agreeing to AMR-WB **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: FFS WHEN: FFS THEN: FFS | Mediatek | Opt 2: RAN5#91 (May-21) |  | (LTE 12.25) | 1 | 0% | 11 | 0%
49 | Y | 34.229-5 | 7.19 | MTSI MT Voice Call / EVS / AMR-WB IO mode / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having set up a voice call using EVS WHEN: UE receives INVITE indicating to switch to EVS AMR-WB IO mode THEN: UE responds by accepting this switch | Mediatek | Opt 2: RAN5#91 (May-21) |  | (LTE 12.26) | 1 | 0% | 11 | 0%
50 | Y | 34.229-5 | 7.20 | MTSI MO Voice Call / add video and remove video / with preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having set up a voice call with preconditions WHEN: UE is made to add video to the voice call THEN: UE sends re-INVITE with SDP media for both voice and video **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent re-INVITE WHEN: UE receives 100 Trying and 183 Session in Progress with SDP answer THEN: UE acks with PRACK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent PRACK WHEN: UE receives 200 OK for PRACK and indication that resources are reserved THEN: UE sends UPDATE with SDP offer indicating reserved resources **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent UPDATE WHEN: UE receives 200 OK for UPDATE followed by 200 OK for re-INVITE THEN: UE sends ACK **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having successfully added video WHEN: UE is made to remove video again THEN: UE sends re-INVITE with SDP indicating that video is being removed from the call **** TP6: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent re-INVITE WHEN: UE receives 100 Trying followed by 200 OK and indication that video resources have been removed THEN: UE sends ACK | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 17.1), NG114 cl 2.2.4 | 1 | 0% | 11 | 0%
51 | Y | 34.229-5 | 7.21 | MTSI MO Voice Call / add video and remove video / without preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having set up a voice call without preconditions WHEN: UE receives re-INVITE indicating addition of video to voice call THEN: UE may send 100 Trying and sends 183 Session Progress with SDP answer **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 183 Session Progress WHEN: UE receives PRACK for 183 Session Progress THEN: UE sends 200 OK for PRACK followed by 200 OK for re-INVITE **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE receiving ACK WHEN: UE is made to remove video again THEN: UE sends re-INVITE with SDP indicating that video is being removed from the call **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent re-INVITE WHEN: UE receives 100 Trying followed by 200 OK and indication that video resources have been removed THEN: UE sends ACK | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 17.1), NG114 cl 2.2.4, but send first re-INVITE from SS | 1 | 0% | 11 | 0%
54 | Y | 34.229-5 | 7.22 | MTSI MT Voice Call / add video and remove video / with preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE configured to use preconditions and having been invited to a voice call and voice call being set up successfully WHEN: UE is made to add video to the voice call THEN: UE sends re-INVITE with SDP media for both voice and video **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent re-INVITE WHEN: UE receives 100 Trying followed by 183 Session Progress THEN: UE sends PRACK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent PRACK WHEN: UE receives 200 OK for PRACK and resources being reserved THEN: UE sends UPDATE with SDP offer indicating reserved resources **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent UPDATE WHEN: UE receives 200 OK for UPDATE followed by 200 OK for re-INVITE THEN: UE sends ACK **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent ACK WHEN: UE receives re-INVITE indicating removal of video THEN: UE may send 100 Trying and sends 200 OK for re-INVITE **** TP6: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: FFS WHEN: FFS THEN: FFS | Qualcomm | Opt 2: RAN5#91 (May-21) |  | (LTE 17.2 but make UE send first re-INVITE) | 1 | 0% | 11 | 0%
55 | Y | 34.229-5 | 7.23 | MTSI MT Voice Call / add video and remove video / without preconditions at both originating UE and terminating UE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Ue configured to not use preconditions and having been invited to a voice call and voice call being set up successfully WHEN: UE is made to add video to the voice call THEN: UE sends re-INVITE with SDP media for both voice and video **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent re-INVITE WHEN: UE receives 100 Trying followed by 183 Session Progress THEN: UE sends PRACK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent PRACK WHEN: UE receives 200 OK for PRACK followed by 200 OK for INVITE and resources are reserved THEN: UE sends ACK **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent ACK WHEN: UE receives re-INVITE indicating that video is being removed from the call THEN: UE may send 100 Trying and sends 200 OK for re-INVITE | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 17.2 but make UE send first re-INVITE) | 1 | 0% | 11 | 0%
56 | Y | 34.229-5 | 7.24 | Forking / UE receives two responses and one CANCEL request / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to use preconditions WHEN: UE is being made to initiate a voice call THEN: UE sends INVITE for voice call with preconditions **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE WHEN: Ue receives two 100 Trying and two 183 Session Progress responses THEN: UE sends two PRACK requests for the two 183 Session Progress responses **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent two PRACK requests WHEN: UE receives CANCEL for the first forked early dialog and 200 OK for PRACK for the second early dialog THEN: UE completes setup of voice call on the second early dialog | to be assigned | Opt 2: RAN5#91 (May-21) |  | NG114 cl 2.3.7 | 1 | 0% | 11 | 0%
136 | Y | 34.229-5 | 7.25 | MTSI MT Voice call without SDP offer in INVITE / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE receives INVITE for voice call without SDP offer THEN: UE responds with 183 Session Progress including SDP offer and completes call initiation | Rohde & Schwarz | Opt 2: RAN5#90 (Feb-21) | R5-210072 | NG114 cl 2.2.4 | 1 | 100% | 10 | 100%
137 | Y | 34.229-5 | 7.26 | Mobile Originating CAT / Forking Model / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and having initiated an MO voice call with preconditions up to the last step before 180 Ringing WHEN: UE receives 183 Session Progress on a forked dialog indicating Customized Alerting Tones THEN: UE moves forked dialog forward until up to the last step before 180 Ringing **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having moved both dialogs forward up to the last step before 180 Ringing WHEN: UE receives 200 OK for INVITE for the first dialog THEN: UE acks reception of 200 OK for INVITE | Huawei/HiSilicon | Opt 2: RAN5#90 (Feb-21) | R5-211439 | (LTE 20.1) | 1 | 100% | 10 | 100%
44 | Y | 34.229-5 | 7.27 | Session Timer / MO Call / UE is able to refresh the session / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and being configured to use Session Timer and preconditions and to be the refresher WHEN: UE is being made to initiate a voice call THEN: UE sends INVITE for voice call **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having included Session-Expires in INVITE WHEN: UE receives 100 Trying followed by 422 Session Interval Too Small with Min-SE value of 1860 THEN: UE sends ACK and new INVITE with Min-SE value and Session-Expires value being 1860 **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having send 2nd INVITE WHEN: UE receives 100 Trying followed by 422 Session Interval Too Small with Min-SE value of 1920 THEN: UE sends ACK and new INVITE with Min-SE value and Session-Expires value being 1920 **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 3rd INVITE WHEN: UE receiving 100 Trying followed by 183 Session Progress THEN: UE concludes voice call set up procedure up until sending ACK, with Session-Expires having value 1920 and refresher being set to uac **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having been chosen as refresher for established voice call WHEN: voice call has been going on for 960 seconds THEN: UE sends UPDATE to refresh the session **** TP6: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having been chosen as refresher for established voice call WHEN: voice call has been going on for another 960 seconds THEN: UE sends UPDATE to refresh the session | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211421 | (LTE 22.1), NG114 cl 2.2.8 | 1 | 100% | 10 | 100%
57 | Y | 34.229-5 | 7.28 | Session Timer / MO Call / Remote end is refresher / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and being configured to use Session Timer and preconditions and to not be the refresher WHEN: UE is being made to initiate a voice call THEN: UE sends INVITE for voice call without refresher parameter **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE WHEN: UE continues setup of voice call and finally receives 200 OK for INVITE setting refresher to uas THEN: UE sends ACK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having completed call setup WHEN: UE receives refresh request via an UPDATE request THEN: UE sends 200 OK for UPDATE **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 200 OK for a refresh request WHEN: Session expires THEN: UE releases the call | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211422 | (LTE 22.2) | 1 | 100% | 10 | 100%
58 | Y | 34.229-5 | 7.29 | Session Timer / MO Call / Remote end does not support Session Timer / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and being configured to use Session Timer and preconditions and to be the refresher WHEN: UE is being made to initiate the voice call THEN: UE sends INVITE for voice call **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE and continuing wiht the call setup WHEN: UE receives 200 OK for INVITE without timer tag and Session-Expires THEN: UE sends ACK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent ACK WHEN: 900 seconds have passed THEN: UE sends UPDATE to refresh the session **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent received 200 OK for UPDATE WHEN: Another 900 seconds have passed THEN: UE sends UPDATE to refresh the session | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211423 | (LTE 22.3), NG114 cl 2.2.8 | 1 | 100% | 10 | 100%
59 | Y | 34.229-5 | 7.30 | Session Timer / MO Call / Remote end supports but does not use Session Timer / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and being configured to use Session Timer and preconditions and to be the refresher WHEN: UE is being made to initiate a voice call THEN: UE sends INVITE for voice call **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE for voice call and continuing the call setup WHEN: UE receives 200 OK for INVITE with timer tag and without Session-Expires THEN: UE sends ACK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent ACK WHEN: 1860 seconds passed without the UE refreshing the session THEN: UE receives BYE and sends 200 OK for BYE | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211424 | (LTE 22.4), NG114 cl 2.2.8 | 1 | 100% | 10 | 100%
60 | Y | 34.229-5 | 7.31 | Session Timer / MT Call / Remote end supports but does not send Session-Expires / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and being configured to use Session Timer and preconditions WHEN: UE receives INVITE for voice call THEN: UE continues setup of voice call and finally sends 200 OK for INVITE with Session-Expires being 1800 and setting refresher to uac **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Call having been set up WHEN: 900 seconds have passed and UE receives UPDATE to refresh the session THEN: UE sends 200 OK for UPDATE **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent 200 OK for UPDATE WHEN: 1800 seconds passed THEN: UE sends BYE | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211425 | (LTE 22.5), NG114 cl 2.2.8 | 1 | 100% | 10 | 100%
61 | Y | 34.229-5 | 7.32 | Session Timer / MT Call / Remote end sends Session-Expires but does not choose refresher / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] WITH: UE being registered to IMS and being configured to use Session Timer and preconditions WHEN: UE receives INVITE for voice call containing timer tag and Session-Expires value 1800 THEN: UE continues setup of voice call and finally sends 200 OK for INVITE with Session-Expires being 1800 and setting refresher to uac **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Call having been set up WHEN: 900 seconds have passed and UE receives UPDATE to refresh the session THEN: UE sends 200 OK for UPDATE | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211426 | (LTE 22.6), NG114 cl 2.2.8 | 1 | 100% | 10 | 100%
53 | Y | 34.229-5 | 7.33 | Session Timer / MT Call / Remote end chooses UE as refresher / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and being configured to use Session Timer and preconditions WHEN: UE receives INVITE for voice call with Session-Expires value 1800 and refresher set uas THEN: UE continues setup of voice call and finally sends 200 OK for INVITE with Session-Expires being 1800 and setting refresher to uas **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Voice call having been set up WHEN: 900 seconds have passed THEN: UE sends INVITE to refresh the session **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having refreshed the session WHEN: Another 900 seconds have passed THEN: UE sends another INVITE to refresh the session | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211427 | (LTE 22.7) | 1 | 100% | 10 | 100%
62 | Y | 34.229-5 | 7.34 | Session Timer / MT Call / Remote end does not support Session Timer / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and being configured to use Session Timer and preconditions WHEN: UE receives INVITE for voice call without support for Session Timer THEN: UE continues setup of voice call and finally sends 200 OK for INVITE with Session-Expires being 1800 and setting refresher to uas **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Call having been set up WHEN: 900 seconds have passed THEN: UE sends UPDATE to refresh the session | ZTE | Opt 2: RAN5#90 (Feb-21) | R5-211428 | (LTE 22.8) | 1 | 100% | 10 | 100%
Supplementary Services
72 | Y | 34.229-5 | 8.1 | Originating Identification Presentation / Configuration / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE is made to activate OIP THEN: UE authenticates itself using GBA **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having started authentication using GBA WHEN: UE receives 200 OK concluding the authentication THEN: UE sends HTTP request to activate OIP **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having concluded activation of OIP WHEN: UE is made to de-activate OIP THEN: UE sends HTTP request to de-activate OIP | Qualcomm | Opt 2: RAN5#91 (May-21) |  | (LTE 15.1), NG114 cl 2.3.12 Outstanding Editor's Notes | 1 | 50% | 11 | 50%
76 | Y | 34.229-5 | 8.2 | Originating Identification Restriction / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.2) | 1 | 0% | 11 | 0%
77 | Y | 34.229-5 | 8.3 | Originating Identification Restriction / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.2a), NG114 cl 2.3.6 | 1 | 0% | 11 | 0%
78 | Y | 34.229-5 | 8.4 | Terminating Identification Presentation / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.3) | 1 | 0% | 11 | 0%
79 | Y | 34.229-5 | 8.5 | Terminating Identification Restriction / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.4) | 1 | 0% | 11 | 0%
80 | Y | 34.229-5 | 8.6 | Terminating Identification Restriction / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.4a), NG114 cl 2.3.7 | 1 | 0% | 11 | 0%
81 | Y | 34.229-5 | 8.7 | Communication Forwarding Unconditional / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.5), NG114 cl 2.3.1 | 1 | 0% | 11 | 0%
82 | Y | 34.229-5 | 8.8 | Communication Forwarding Unconditional / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | 24.604 cl A.1.1 | 1 | 0% | 11 | 0%
83 | Y | 34.229-5 | 8.9 | Communication Forwarding on Not Logged-in / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.10), NG114 cl 2.3.1 | 1 | 0% | 11 | 0%
84 | Y | 34.229-5 | 8.10 | Communication Forwarding on Not Logged-in / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | NG114 cl 2.3.1 | 1 | 0% | 11 | 0%
85 | Y | 34.229-5 | 8.11 | Communication Forwarding on Busy / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.9), NG114 cl 2.3.1 | 1 | 0% | 11 | 0%
86 | Y | 34.229-5 | 8.12 | Communication Forwarding on Busy / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | NG114 cl 2.3.1 | 1 | 0% | 11 | 0%
87 | Y | 34.229-5 | 8.13 | Communication Forwarding on Subscriber Not Reachable / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.10a), NG114 cl 2.3.1 | 1 | 0% | 11 | 0%
88 | Y | 34.229-5 | 8.14 | Communication Forwarding on Subscriber Not Reachable / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | NG114 cl 2.3.1 | 1 | 0% | 11 | 0%
89 | Y | 34.229-5 | 8.15 | Communication Forwarding on No Reply / Configuration / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.7) | 1 | 0% | 11 | 0%
90 | Y | 34.229-5 | 8.16 | Communication Forwarding on No Reply / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.8), NG114 cl 2.3.1 | 1 | 0% | 11 | 0%
91 | Y | 34.229-5 | 8.17 | Barring of All Incoming Calls / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 11 | 0%
73 | Y | 34.229-5 | 8.18 | Barring of All Incoming Calls / except for a specific user / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE is made to activate incoming communication barring except for a specific user (ICBESU) THEN: UE authenticates itself using Digest **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having started authentication using Digest WHEN: UE receives 200 OK concluding the authentication THEN: UE sends HTTP request to activate ICBESU **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having concluded activation of ICBESU WHEN: UE is made to de-activate ICBESU THEN: UE sends HTTP request to de-activate ICBESU | Qualcomm | Opt 2: RAN5#91 (May-21) | R5-204485 | (LTE 15.13) same as 8.1 | 1 | 50% | 11 | 50%
92 | Y | 34.229-5 | 8.19 | Barring of All Incoming Calls from anonymous users / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.14) | 1 | 0% | 11 | 0%
93 | Y | 34.229-5 | 8.20 | Barring of All Incoming Calls / Signalling / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | TS 24.611 cl 4.5.2.13, NG114 cl 2.3.1 | 1 | 0% | 11 | 0%
94 | Y | 34.229-5 | 8.21 | Barring of all Outgoing Calls / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 11 | 0%
95 | Y | 34.229-5 | 8.22 | Barring of Outgoing International Calls / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 11 | 0%
96 | Y | 34.229-5 | 8.23 | Barring of Outgoing International Calls / ex Home Country / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 11 | 0%
97 | Y | 34.229-5 | 8.24 | Barring of Outgoing International Calls / When Roaming / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.14b) TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 11 | 0%
98 | Y | 34.229-5 | 8.25 | Barring of Incoming Calls / When Roaming / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.14a) TS 24.611 cl 4.9.1.4, NG114 cl 2.3.1, 2.3.9 | 1 | 0% | 11 | 0%
99 | Y | 34.229-5 | 8.26 | MO Call Hold without announcement / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and having set up a voice call WHEN: UE is being made to hold the call THEN: UE sends re-INVITE or UPDATE, and completes the call hold procedure **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having put the voice call on hold WHEN: UE is being made to resume the call THEN: UE sends re-INVITE or UPDATE, and completes the call resume procedure | Huawei / HiSilicon | Opt 2: RAN5#91 (May-21) | R5-211440 | (LTE 15.11 but MT release), NG114 cl 2.3.1, 2.3.10 Generic Procedure(s) to be produced | 1 | 60% | 11 | 60%
100 | Y | 34.229-5 | 8.27 | MO Video Call Hold without announcement / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.11a), NG114 cl 2.3.1, 2.3.10 | 1 | 0% | 11 | 0%
101 | Y | 34.229-5 | 8.28 | MT Call Hold without announcement / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and having set up an MO voice call WHEN: UE receives re-INVITE including call hold instructions THEN: UE may send 100 Trying and sends 200 OK for re-INVITE **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having responded to re-INVITE for call hold WHEN: UE receives ACK followed by re-INVITE including call resume instructions THEN: UE may send 100 Trying and sends 200 OK for re-INVITE **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having concluded the call resume procedure WHEN: UE is being made to release the call THEN: UE sends BYE | Huawei / HiSilicon | Opt 2: RAN5#91 (May-21) | R5-211441 | (LTE 15.12 but MO release), NG114 cl 2.3.1, 2.3.10 Generic Procedure(s) to be produced | 1 | 60% | 11 | 60%
102 | Y | 34.229-5 | 8.29 | MT Video Call Hold without announcement / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.12a), NG114 cl 2.3.1, 2.3.10 | 1 | 0% | 11 | 0%
103 | Y | 34.229-5 | 8.30 | Subscription to the MWI event package / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being configured to subscribe to MWI WHEN: UE registers to IMS THEN: UE subscribes to MWI and to reg event **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to MWI and reg event WHEN: UE receives initial NOTIFY for MWI THEN: UE sends 200 OK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to MWI and reg event WHEN: UE receives second NOTIFY for MWI indicating one voice message waiting THEN: UE sends 200 OK **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to MWI and reg event WHEN: UE receives NOTIFY for reg event THEN: UE sends 200 OK | Huawei / HiSilicon | Opt 2: RAN5#90 (Feb-21) | R5-211442 | (LTE 15.15), NG114 cl 2.3.1, cl 2.3.4 | 1 | 100% | 10 | 100%
104 | Y | 34.229-5 | 8.31 | Creating and leaving a conference / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE is made to start a conference call THEN: UE sends INVITE to the conference factory and completes the conference call initiation and subscribes to conference event **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Conference call going on WHEN: UE is made to leave the call THEN: UE sends BYE and processes notification for conf event if any | Huawei / HiSilicon | Opt 2: RAN5#91 (May-21) | R5-211443 | (LTE 15.17), NG114 cl 2.3.1, 2.3.3 Generic Procedure(s) to be produced | 1 | 60% | 11 | 60%
105 | Y | 34.229-5 | 8.32 | Inviting user to conference by sending a REFER request to the conference focus / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE is made to start a conference call THEN: UE sends INVITE to the conference factory and completes the conference call initiation and subscribes to conference event **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Conference call going on WHEN: UE is made to invite another user to the conference call THEN: UE sends REFER to the conference focus **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having invited another user to the conference call WHEN: UE receives 202 Accepted followed by notification messages for the REFER request, the confirmation on the other user and conditional conference event package THEN: UE sends 200 OK for each received NOTIFY request **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Conference call going on WHEN: UE is made to leave the call THEN: UE sends BYE and processes notification for conf event if any | Huawei / HiSilicon | Opt 2: RAN5#91 (May-21) | R5-211444 | (LTE 15.19), NG114 cl 2.3.1, 2.3.3 Generic Procedure(s) to be produced | 1 | 60% | 11 | 60%
106 | Y | 34.229-5 | 8.33 | Inviting user to conference by sending a REFER request to the conference focus / Video / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.19a), NG114 cl 2.3.1, 2.3.3 | 1 | 0% | 11 | 0%
107 | Y | 34.229-5 | 8.34 | Three way session creation / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and having set up an MO voice call with A WHEN: UE is made to start a three way voice call THEN: UE sends re-INVITE or UPDATE, and completes the call hold procedure with A **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being in the process of starting a three way voice call WHEN: UE having put A on hold THEN: UE initiates a voice call with B **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being in the process of starting a three way voice call WHEN: UE having initiated a voice call with B THEN: UE sends re-INVITE or UPDATE, and completes the call hold procedure with B **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being in the process of starting a three way voice call WHEN: UE having put both A and B on hold THEN: UE sends INVITE to the conference factory and completes the conference call initiation and subscribes to conference event **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being in the process of starting a three way voice call WHEN: UE having created a call at the conference factory THEN: UE sends REFER to the conference focus in order to invite A **** TP6: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having invited A to the conference call WHEN: UE receives 202 Accepted followed by notification messages for the REFER request, the confirmation on A and conditional conference event package THEN: UE sends 200 OK for each received NOTIFY request **** TP7: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being in the process of starting a three way voice call WHEN: UE having completed the invitation of A THEN: UE sends REFER to the conference focus in order to invite B **** TP8: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having invited B to the conference call WHEN: UE receives 202 Accepted followed by notification messages for the REFER request, the confirmation on B and conditional conference event package THEN: UE sends 200 OK for each received NOTIFY request | Huawei / HiSilicon | Opt 2: RAN5#91 (May-21) | R5-211445 | (LTE 15.21a), NG114 cl 2.3.1, 2.3.3 Generic Procedure(s) to be produced | 1 | 60% | 11 | 60%
108 | Y | 34.229-5 | 8.35 | Three way session creation / Video / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.21c), NG114 cl 2.3.1, 2.3.3 | 1 | 0% | 11 | 0%
109 | Y | 34.229-5 | 8.36 | MO Explicit Communication Transfer / Consultative Call Transfer / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and having established a voice call with A (the transferee) WHEN: UE is being made to attempt Consultative Call Transfer THEN: UE puts A on hold and sets up voice call with B (the transfer target) and puts B on hold and sends REFER to the transferee **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having initiated consultative call transfer WHEN: UE receives NOTIFY THEN: UE sends 200 OK response for NOTIFY **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having processed the NOTIFY exchange WHEN: UE receives instruction to be put on hold by A THEN: UE processes call hold instruction and responds to it **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having been put on hold by A WHEN: UE receives BYE from B THEN: UE sends 200 OK for BYE **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Call with B having ended WHEN: UE receives NOTIFY from A THEN: UE sends 200 OK for NOTIFY and may send BYE | Huawei / HiSilicon | Opt 2: RAN5#90 (Feb-21) | R5-211446 | (LTE 15.25), NG114 cl 2.3.1, 2.3.11 | 1 | 100% | 10 | 100%
110 | Y | 34.229-5 | 8.37 | Communication Waiting and answering the call / 5Gs | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and having initiated an MO voice call with preconditions WHEN: UE receives INVITE for MT voice call with preconditions THEN: UE continues voice call initiation until 180 Ringing (including conditional PRACK/200 OK) **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having continued initiation of incoming voice call until 180 Ringing WHEN: UE is being made to terminate the MO voice call THEN: UE sends BYE for the MO voice call **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having terminated the MO voice call WHEN: UE is being made to accept the incoming MT voice call THEN: UE sends 200 OK for INVITE | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.27), NG114 cl 2.3.1, 2.3.4 | 1 | 0% | 11 | 0%
111 | Y | 34.229-5 | 8.38 | Communication Waiting and cancelling the call / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and having initiated an MO voice call with preconditions WHEN: UE receives INVITE for MT voice call with preconditions THEN: UE continues voice call initiation until 180 Ringing (including conditional PRACK/200 OK) **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having continued initiation of incoming voice call until 180 Ringing WHEN: UE receives CANCEL for incoming voice call THEN: UE responds with 200 OK and 487 Request Terminated responses | Qualcomm | Opt 2: RAN5#90 (Feb-21) | R5-211447 | (LTE 15.28), NG114 cl 2.3.1, 2.3.4 | 1 | 100% | 10 | 100%
112 | Y | 34.229-5 | 8.39 | GBA authentication / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.29) | 1 | 0% | 11 | 0%
113 | Y | 34.229-5 | 8.40 | User initiated USSI / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] WITH: UE being registered to IMS WHEN: UE is being made to attempt user intiated USSI THEN: UE sends INVITE with SDP and ussd+xml bodies **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE WHEN: UE receiving 100 Trying followed by 200 OK THEN: UE completes session initiation by sending ACK **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Session initiation being completed WHEN: UE receives BYE containing ussd+xml body with ussd string and language element THEN: UE sends 200 OK response for BYE | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.30) | 1 | 0% | 11 | 0%
135 | Y | 34.229-5 | 8.41 | Communication Forwarding on No Reply: MO Call initiation with preconditions | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS and configured to use preconditions and being made to initiate a voice call WHEN: Voice call initiation progressed until 180 Ringing (including PRACK/200 OK) and UE receives 181 Call is being forwarded followed by 183 Session Progress THEN: UE completes call initiation with forwarded to UE by restarting from PRACK for 183 Session Progress | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 15.8), NG114 cl 2.4.8 |  | 0% | 11 | 0%
SMS
67 | Y | 34.229-5 | 9.1 | Mobile Originating SMS / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE is made to send an SMS over IP THEN: UE sends a SIP MESSAGE request containing a short message **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent a SIP MESSAGE request containing a short message WHEN: UE receives a 202 Accepted response, followed by a SIP MESSAGE request containing a submission report THEN: UE sends a 200 OK response **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent a 200 OK response for submission report WHEN: UE receives a SIP MESSAGE request containing a status report THEN: UE sends a 200 OK response, followed by a SIP MESSAGE request containing a delivery report for status report | ZTE | Opt 2: RAN5#88 (Aug-20) | R5-204482, R5-206287 | (LTE 18.1) | 1 | 100% | 8 | 100%
68 | Y | 34.229-5 | 9.2 | Mobile Terminating SMS / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE receives a SIP MESSAGE request containing a short message THEN: UE sends a 200 OK response, followed by a SIP MESSAGE request containing a delivery report | ZTE | Opt 2: RAN5#88 (Aug-20) | R5-204483, R5-206372 | (LTE 18.2) | 1 | 100% | 8 | 100%
69 | Y | 34.229-5 | 9.3 | Mobile Originating Concatenated SMS / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE is made to send a concatenated SMS over IP THEN: UE sends a SIP MESSAGE request containing the first segment of the concatenated SMS **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent a SIP MESSAGE request containing the first segment of the concatenated SMS WHEN: UE receives a 202 Accepted response, followed by a SIP MESSAGE request containing a submission report for the first segment THEN: UE sends a 200 OK response, followed by a SIP MESSAGE request containing the second segment of the concatenated SMS **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent a SIP MESSAGE request containing the second segment of the concatenated SMS WHEN: UE receives a 202 Accepted response, followed by a SIP MESSAGE request containing a submission report for the second segment THEN: UE sends a 200 OK response, followed by a SIP MESSAGE request containing the third segment of the concatenated SMS **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent a SIP MESSAGE request containing the third segment of the concatenated SMS WHEN: UE receives a 202 Accepted responsed, followed by a SIP MESSAGE request containing a submission report for the third segment THEN: UE sends a 200 OK response | Qualcomm | Opt 2: RAN5#88 (Aug-20) | R5-204486, R5-205157 | (LTE 18.1a) | 1 | 100% | 8 | 100%
70 | Y | 34.229-5 | 9.4 | Mobile Terminating Concatenated SMS / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE receives a SIP MESSAGE request containg a first segment of a concatenated SMS THEN: UE sends a 200 OK response, followed by a SIP MESSAGE request containing a delivery report for the first segment **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent a SIP MESSAGE request containing a delivery report for the first segment WHEN: UE receives a 202 Accepted response, followed by a SIP MESSAGE request containing a second segment of a concatenated SMS THEN: UE sends a 200 OK response, followed by a SIP MESSAGE request containing a delivery report for the second segment **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent a SIP MESSAGE request containing a delivery report for the second segment WHEN: UE receives a 202 Accepted response, followed by a SIP MESSAGE request containing a third segment of a concatenated SMS THEN: UE sends a 200 OK response, followed by a SIP MESSAGE request containing a delivery report for the third segment | Huawei, HiSilicon | Opt 2: RAN5#88 (Aug-20) | R5-204477, R5-205158 | (LTE 18.2a) | 1 | 100% | 8 | 100%
71 | Y | 34.229-5 | 9.5 | Mobile Originating SMS / RP-ERROR / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE is made to send an SMS over IP THEN: UE sends a SIP MESSAGE request containing a short message **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent a SIP MESSAGE request containing a short message WHEN: UE receives a 202 Accepted response, followed by a SIP MESSAGE request containing an RP-ERROR message THEN: UE sends a 200 OK response | Huawei, HiSilicon | Opt 2: RAN5#88 (Aug-20) | R5-204478, R5-205159, R5-210196 | (LTE 18.1b) | 1 | 100% | 8 | 100%
Emergency Calls
74 | Y | 34.229-5 | 10.1 | Emergency Call with emergency registration / Success / Location information available / 5GS | Editor's note: <Add test case note here if needed> **** TP1: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE being registered to IMS WHEN: UE is being made to initiate an emergency call THEN: UE sends a correctly composed initial REGISTER request for IMS emergency registration **** TP2: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent an unprotected REGISTER request WHEN: UE receiving a valid 401 (Unauthorized) response for the initial REGISTER request sent THEN: UE correctly authenticates itself by sending another REGISTER request with a correctly composed Authorization header using the AKAv1-MD5 algorithm **** TP3: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent unprotected and then protected REGISTER request WHEN: UE receiving a valid 200 OK response for the REGISTER sent for authentication THEN: UE sends a correctly composed INVITE request **** TP4: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: UE having sent INVITE WHEN: UE receving 100 Trying, followed by 180 Ringing, followed by 200 OK THEN: UE sends ACK **** TP5: [TS <TS#1>:FFS; TS <TS#2>:FFS; TS <TS#n>:FFS] Editor's note: <Add TP note here if needed> WITH: Emergency call being established WHEN: UE receives BYE THEN: UE sends a 200 OK response | Huawei, HiSilicon | Opt 2: RAN5#91 (May-21) | R5-204479, R5-211438 | (LTE 19.1.1). Dependency on A.6. | 1 | 80% | 11 | 80%
114 | Y | 34.229-5 | 10.2 | Emergency Call with emergency registration / Success / Location information not available / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 19.1.2) | 1 | 0% | 11 | 0%
115 | Y | 34.229-5 | 10.3 | Emergency call with emergency registration / Emergency SIP signalling and media in parallel with an other ongoing IM CN subsystem signalling and media / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 19.1.5) | 1 | 0% | 11 | 0%
116 | Y | 34.229-5 | 10.4 | Non-UE detectable emergency call / IM CN sends a 1xx response / UE geographical location information available or not / 5GS |  | Mediatek | Opt 2: RAN5#91 (May-21) |  | (LTE 19.3.1) | 1 | 0% | 11 | 0%
117 | Y | 34.229-5 | 10.6 | Non-UE detectable emergency call / IM CN sends 380 with an Alternative Service / Previous emergency IMS registration not expired / 5GS |  | Qualcomm | Opt 2: RAN5#91 (May-21) |  | (LTE 19.3.4) - note hole in that 10.5 is missing | 1 | 0% | 11 | 0%
118 | Y | 34.229-5 | 10.7 | Emergency call without emergency registration / UE does not contain an ISIM or USIM / 5GS |  | Mediatek | Opt 2: RAN5#91 (May-21) |  | (LTE 19.4.1) | 1 | 0% | 11 | 0%
119 | Y | 34.229-5 | 10.8 | Emergency call without emergency registration / UE contains an ISIM or USIM / UE is in state 5GMM-REGISTERED.LIMITED-SERVICE / 5GS |  | Mediatek | Opt 2: RAN5#91 (May-21) |  | (LTE 19.4.2) | 1 | 0% | 11 | 0%
120 | Y | 34.229-5 | 10.9 | Emergency call without emergency registration / UE credentials are not accepted / 5GS |  | Mediatek | Opt 2: RAN5#91 (May-21) |  | (LTE 19.4.5) | 1 | 0% | 11 | 0%
121 | Y | 34.229-5 | 10.10 | Emergency call without emergency registration / Failure of registration / Rejected by 403 (Forbidden) / 5GS |  | Mediatek | Opt 2: RAN5#91 (May-21) |  | (LTE 19.4.6) | 1 | 0% | 11 | 0%
122 | Y | 34.229-5 | 10.11 | New initial emergency registration after obtaining new IP address different than the IP address / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 19.5.1) | 1 | 0% | 11 | 0%
123 | Y | 34.229-5 | 10.12 | User-initiated emergency reregistration / UE has emergency related ongoing dialog / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 19.5.6) | 1 | 0% | 11 | 0%
124 | Y | 34.229-5 | 10.13 | User-initiated emergency reregistration / User initiates an emergency call / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 19.5.7) | 1 | 0% | 11 | 0%
125 | Y | 34.229-5 | 10.14 | In parallel emergency and non-emergency registrations / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 19.5.9) | 1 | 0% | 11 | 0%
126 | Y | 34.229-5 | 10.15 | Deregistration upon emergency registration expiration / 5GS |  | to be assigned | Opt 2: RAN5#91 (May-21) |  | (LTE 19.5.10) | 1 | 0% | 11 | 0%
Test cases Option 2 - non-3GPP access to 5GC
| Y | 34.229-5 | TBD | TBD | Placeholder for expected additionaltest cases that have not yet been included in the WP. | for later | Opt 2: RAN5#91 (May-21) |  | The number in the weight column represent the remaining number of test cases expected to be added. | 20 | 0% | 11 | 0%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Y = the WP Pitem is a test case.
Note on L6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.