## Summary
Work plan summary:
Multilayer and Services Protocol Test Cases (TS 38.523-1)
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| Multilayer and Services Protocol Test Cases (TS 38.523-1) | SA Option 2 (SA NR) | 97.45% | 98.91% | 95.99%
NSA Option 3 (EN-DC)
|  | SA Option 5 | 1.46% | 1.46%
|  | NSA Option 4 (NE-DC) | 1.46% | 1.46% | 1.46%
|  | NSA Option 7 (NGEN-DC) | 1.46% | 1.46% | 1.46%
Test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of test cases applicable for FR1+FR2
|  |  | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed
| Multilayer and Services Protocol Test Cases (TS 38.523-1) | SA Option 2 (SA NR) | 27 | 26 | 27 | 26 | 27 | 22 | 0 | 0
NSA Option 3 (EN-DC)
|  | SA Option 5 | 27 | 0 | 27 | 0
|  | NSA Option 4 (NE-DC) | 27 | 0 | 27 | 0
|  | NSA Option 7 (NGEN-DC) | 27 | 0 | 27 | 0

## Multilayer and Services
WP Title: | Multilayer and Services Protocol Test Cases (TS 38.523-1) | [10 empty] | WP item applicability
RAN-CN interface options dependency
WP Scope: | This work plan section covers the multilayer and services protocol test cases in TS 38.523-1 for all SA and NSA options. | [10 empty] | 5GC/NR |  |  |  | 5GC/LTE |  | EPC/LTE |  |  |  | 5GC/NR master |  |  |  | 5GC / LTE master
WP Resp: | Stoyan Baev, Samsung |  |  |  | stoyan.baev@partner.samsung.com
TS Resp: | Stoyan Baev, Samsung |  |  |  | stoyan.baev@partner.samsung.com | [6 empty] | SA | [5 empty] | NSA
[12 empty] | Opt.2 |  |  |  | Opt.5 |  | Opt.3 |  |  |  | Opt.4 |  |  |  | Opt.7
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | 1st Target | FR1 | FR2 | FR1+FR2 | Opt. 5 |  | 1st Target | FR1 | FR2 | FR1+FR2 | 1st Target | FR1 | FR2 | FR1+FR2 | 1st Target | FR1 | FR2 | FR1+FR2
[11 empty] | Overall |  | 97.45% |  |  | 1.46% | [6 empty] | 1.46% |  |  |  | 1.46%
[13 empty] | 98.91% | 95.99% | [8 empty] | 1.46% | 1.46% |  |  | 1.46% | 1.46%
[11 empty] | Phase 1 |  |  |  |  | 1.46% | [6 empty] | 1.46% | 1.46% |  |  | 1.46% | 1.46%
Phase 2
[11 empty] | Phase 3 |  | 100% | 100%
[11 empty] | Phase 4 |  | 100% | 100%
[11 empty] | Phase 5 |  | 100% | 100%
[11 empty] | Phase 6 |  | 100% | 100%
[11 empty] | Phase 7 |  | 100% | 100%
[11 empty] | Phase 8 |  | 100% | 100%
Phase 9
[11 empty] | Phase 10 |  | 100% | 100%
[11 empty] | Phase 11 |  | 94% | 78%
Phase 12
[7 empty] | Overall #WP items: Phase 1 #WP items: Phase 2 #WP items: Phase 3 #WP items: Phase 4 #WP items: Phase 5 #WP items: Phase 6 #WP items: Phase 7 #WP items: Phase 8 #WP items: Phase 9 #WP items: Phase 10 #WP items: Phase 11 #WP items: Phase 12 #WP items: | [5 empty] | 31 0 0 2 2 8 4 5 4 0 1 5 0 | 31 0 0 2 2 8 4 5 4 0 1 5 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 |  |  | 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 |  | 31 31 0 0 0 0 0 0 0 0 0 0 0 | 31 31 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 |  | 31 31 0 0 0 0 0 0 0 0 0 0 0 | 31 31 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [11 empty] | Phase number (1,2 etc) and completion (%) per option
|  | 38.523-1 | TBD | TBD | Placeholder for expected additionaltest cases that have not yet been identified. |  |  |  | The number in the weight column represent the remaining number of test cases expected to be added. | 0 |  | 10 |  |  |  | 1 |  | 3 |  |  |  | 1 |  |  |  | 1
5GS/EPS fallback
20 |  | 38.523-1 | 11 | Multi-layer and Services | New top-level clause |  | Opt 2: RAN5#83 (May-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS |  |  | 0.1 | 100% | 3 | 100% | 100% |  | 1 | 100% | 1 |  |  |  | 1 | 100% | 100% |  | 1 | 100% | 100%
19 |  | 38.523-1 | 11.1 | 5GS/EPS Fallback | New sub-clause |  | Opt 2: RAN5#83 (May-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS |  |  | 0.1 | 100% | 3 | 100% | 100% |  | 1 | 100% | 1 |  |  |  | 1 | 100% | 100% |  | 1 | 100% | 100%
1 | Y | 38.523-1 | 11.1.1 | MO MMTEL voice call setup from NR RRC_IDLE / EPS Fallback with redirection / Single registration mode with N26 interface / Success | **** TP1: [TS 24,501:4.5.4.1, 5.6.1.2; TS 38,331:5.3.3.2, 5.3.3.3; TS 24,229:U.2.2.1, U.3.1.2] Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE supporting both S1 mode and N1 mode and operating in single-registration mode, and, the Network has indicated "interworking without N26 interface not supported", and, the UE in NR RRC_IDLE state WHEN: User initiates a MMTEL call and the UE completes Access control and checking in 5GMM-IDLE mode THEN: UE requests the establishment of a MMTEL call by transmitting an RRCSetupRequest message with establishmentCause set to 'mo-VoiceCall', and, a SERVICE REQUEST message with Service type set to 'data' **** TP2: [TS 24,501:4.8.2.2, 5.1.4.2, 6.1.4.1; TS 38,331:5.3.8.3, 5.3.11; TS 24,229:U.2.2.1, U.3.1.2] Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE is NR RRC_CONNECTED state after having requested a MMTEL call establishment and the MO IMS voice session establishment has been initiated WHEN: UE receives a RRCRelease message which includes redirectedCarrierInfo indicating redirection to eutra THEN: UE selects the E-UTRA cell, performs a TAU procedure, and, successfully completes the MO MMTEL call setup in EPS | Qualcomm | Opt 2: RAN5#86 (Feb-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-197089, R5-197091, R5-201231, R5-204466, R5-206361, R5-211547, R5-210133 |  | 1 | 28.57% | 6 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
2 | Y | 38.523-1 | 11.1.2 | MO MMTEL voice call setup from NR RRC_IDLE / EPS Fallback with redirection / Single registration mode without N26 interface / Success | **** TP1: [TS 24,501:4.5.4.1, 5.6.1.2; TS 38,331:5.3.3.2, 5.3.3.3; TS 24,229:U.2.2.1, U.3.1.2] Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE supporting both S1 mode and N1 mode and operating in single-registration mode, and, the Network has indicated "interworking without N26 interface supported", and, the UE is in NR RRC_IDLE state WHEN: User initiates a MMTEL call and the UE completes Access control and checking in 5GMM-IDLE mode THEN: UE requests the establishment of a MMTEL call by transmitting an RRCSetupRequest message with establishmentCause set to 'mo-VoiceCall', and, a SERVICE REQUEST message with Service type set to 'data' **** TP2: [TS 24,501:4.8.2.3, 5.1.4.3, 6.1.4.2; TS 38,331:5.3.8.3, 5.3.11] Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE is NR RRC_CONNECTED state after having requested a MMTEL call establishment and the MO IMS voice session establishment has been initiated WHEN: UE receives a RRCRelease message which includes redirectedCarrierInfo indicating redirection to eutra THEN: UE selects the E-UTRA cell, performs an ATTACH or a TAU procedure, and, successfully completes the MO MMTEL call setup in EPS | ZTE | Opt 2: RAN5#86 (Feb-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-197093, R5-197091, R5-198978, R5-201103, R5-202667, R5-204465, R5-210133 |  | 1 | 28.57% | 6 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
3 | Y | 38.523-1 | 11.1.3 | MO MMTEL voice call setup from NR RRC_CONNECTED / EPS Fallback with handover / Single registration mode with N26 interface / Success | **** TP1: [TS 24,501:4.8.2.2, 5.1.4.2, 6.1.4.1; TS 38,331:5.4.3.3, 5.4.3.4; TS 24,229:U.2.2.1, U.3.1.2] Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE supporting both S1 mode and N1 mode and operating in single-registration mode, and, the Network has indicated "interworking without N26 interface not supported", and, the UE is in NR RRC_CONNECTED state after having established connection with establishmentCause set to 'mo-Data', and, the UE is receiving and transmitting PS data WHEN: User initiates a MMTEL call, the MO IMS voice session establishment has been initiated and the UE receives a MobilityFromNRCommand message which includes targetRAT-Type set to eutra THEN: UE performs a handover to the E-UTRA including a TAU procedure, and, while the UE continues receiving and transmitting PS data the UE successfully completes the MO MMTEL call in EPS | MediaTek | Opt 2: RAN5#86 (Feb-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-197090, R5-197091, R5-198982, R5-204336, R5-206362, R5-205292, R5-211406, R5-210133, R5-211407 | TC cannot use test mode for checking that data can be transmitted on the non IMS DRB handed over because this is an IMS and test mode requires IMS to be turned off. PING is used instead if supported (assumption made that if IMS supported PING will be supported). The usage of PING removed in R5-211407. | 1 | 28.57% | 6 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
4 | Y | 38.523-1 | 11.1.4 | MO MMTEL voice call setup from NR RRC_CONNECTED / EPS Fallback with redirection / Single registration mode with N26 interface / E-UTRAN cell reselection using cell status barred / Success | **** TP1: [TS 24,501:4.8.2.2, 5.1.4.2, 6.1.4.1; TS 38,331:5.3.3.2, 5.3.3.3, 5.3.8.3, 5.3.11; TS 36,304:5.2.4.4, 5.3.1; TS 24,229:U.2.2.1, U.3.1.2] Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE supporting both S1 mode and N1 mode and operating in single-registration mode, and, the Network has indicated "interworking without N26 interface not supported", and, the UE in NR RRC_CONNECTED state after having established connection with establishmentCause set to 'mo-Data', and, the UE receiving and transmitting PS data WHEN: User initiates a MMTEL call, the MO IMS voice session establishment has been initiated and the UE receives a RRCRelease message which includes redirectedCarrierInfo indicating redirection to eutra, and, a higher ranked E-UTRA cell is found with cell status "barred" and a lower ranked E-UTRA cell is found which is not "barred" THEN: UE selects the not "barred" E-UTRA cell, performs a TAU procedure, and, while the UE continues receiving and transmitting PS data the UE successfully completes the MO MMTEL call in EPS | MediaTek | Opt 2: RAN5#91 (May-21) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-197092, R5-197091, R5-198981, R5-206360, R5-205292, R5-210133, R5-211407 | TC cannot use test mode for checking that data can be transmitted on the non IMS DRB handed over because this is an IMS and test mode requires IMS to be turned off. PING is used instead if supported (assumption made that if IMS supported PING will be supported). The usage of PING removed in R5-211407. 2 E-UTRA cells with FR2 needed - not allowed according to 38.508-1, 6.2.2.2 | 1 | 25.71% | 11 | 100% | 80% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
5 | Y | 38.523-1 | 11.1.5 | MO MMTEL voice call setup from NR RRC_CONNECTED / EPS Fallback with redirection / Single registration mode without N26 interface / E-UTRAN cell reselection using cell status reservation / Success | **** TP1: [TS 24,501:4.8.2.3, 5.1.4.3, 6.1.4.2; TS 38,331:5.3.3.2, 5.3.3.3, 5.3.8.3, 5.3.11; TS 36,304:5.2.4.4, 5.3.1; TS 24,229:U.2.2.1, U.3.1.2] Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE supporting both S1 mode and N1 mode and operating in single-registration mode, and, the Network has indicated "interworking without N26 interface supported", and, the UE in NR RRC_CONNECTED state after having established connection with establishmentCause set to 'mo-Data', and, the UE receiving and transmitting PS data WHEN: User initiates a MMTEL call, the MO IMS voice session establishment has been initiated and the UE receives a RRCRelease message which includes redirectedCarrierInfo indicating redirection to eutra, and, a higher ranked E-UTRA cell is found with cell status "reserved for operator use" and a lower ranked E-UTRA cell is found which is not "reserved for operator use" both cells belonging to the UE's HPLMN THEN: UE selects the E-UTRA cell respecting the UE Access Class, performs an ATTACH or a TAU procedure, and, while the UE continues receiving and transmitting PS data the UE successfully completes the MO MMTEL call in EPS | ZTE | Opt 2: RAN5#91 (May-21) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-197094, R5-197091, R5-198979, R5-198362, R5-200872, R5-202665, R5-204465, R5-211407 | TC cannot use test mode for checking that data can be transmitted on the non IMS DRB handed over because this is an IMS and test mode requires IMS to be turned off. PING is used instead if supported (assumption made that if IMS supported PING will be supported). The usage of PING removed in R5-211407. 2 E-UTRA cells with FR2 needed - not allowed according to 38.508-1, 6.2.2.2 | 1 | 25.71% | 11 | 100% | 80% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
6 | Y | 38.523-1 | 11.1.6 | MT MMTEL voice call setup from NR RRC_IDLE / EPS Fallback with redirection / Single registration mode without N26 interface / Success | **** TP1: [TS 24,501:5.6.2.2.1, 5.6.1.2, 4.8.2.3, 5.1.4.3, 6.1.4.2; TS 38,331:5.3.2.3, 5.3.3.2, 5.3.3.3, 5.3.8.3, 5.3.11] Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE supporting both S1 mode and N1 mode and operating in single-registration mode, and, the Network has indicated "interworking without N26 interface supported", and, the UE is in NR RRC_IDLE state WHEN: Network initiates a paging procedure for the purposes of establishing a MT MMTEL call THEN: UE requests RRC connection establishment by transmitting an RRCSetupRequest message with establishmentCause set to 'mt-Access', and, a SERVICE REQUEST message with Service type set to 'mobile terminated services' **** TP2: [TS 24,501:5.6.2.2.1, 5.6.1.2, 4.8.2.3, 5.1.4.3, 6.1.4.2; TS 38,331:5.3.2.3, 5.3.3.2, 5.3.3.3, 5.3.8.3, 5.3.11] Editor's note: Complimentary references: TS 23.501, subclause 5.16.3.10, TS 23.502, subclauses 4.13.6.1, 4.11.1 WITH: UE is NR RRC_CONNECTED state after having sent a SERVICE REQUEST message with Service type set to 'mobile terminated services' and a MO IMS voice session establishment has been initiated by the NEtwork WHEN: UE receives a RRCRelease message which includes redirectedCarrierInfo indicating redirection to eutra THEN: UE selects the E-UTRA cell, performs an ATTACH or a TAU procedure, and, successfully completes the MT MMTEL call setup in EPS | ZTE | Opt 2: RAN5#87 (May-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-197095, R5-197091, R5-198980, R5-200877, R5-202666, R5-210133 |  | 1 | 28.57% | 7 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
7 | Y | 38.523-1 | 11.1.7 | Emergency call setup from NR RRC_IDLE / Emergency Services Fallback to EPS with redirection / Single registration mode with N26 interface / Success | **** TP1: [TS TS 24.501:5.6.1.1, 5.6.1.2, 5.6.1.4; TS TS 23.502:4.13.4.2; TS TS 24.301:4.4.2.3, 5.5.3.2.2] WITH: UE supporting both S1 mode and N1 mode and operating in single-registration mode, and, the Network has indicated "interworking without N26 interface not supported", and, the UE in NR RRC_IDLE state WHEN: User initiates an Emergency call and the UE completes Access control and checking in 5GMM-IDLE mode THEN: UE requests the establishment of an Emergency call by transmitting an RRCSetupRequest message with establishmentCause set to 'emergency', and, a SERVICE REQUEST message with Service type set to 'emergency services fallback' **** TP2: [TS TS 24.501:5.6.1.1, 5.6.1.2, 5.6.1.4; TS TS 23.502:4.13.4.2; TS TS 24.301:4.4.2.3, 5.5.3.2.2] WITH: UE is NR RRC_CONNECTED state after having requested a MMTEL call establishment and the MO IMS voice session establishment has been initiated WHEN: UE receives a RRCRelease message which includes redirectedCarrierInfo indicating redirection to epc THEN: UE selects the E-UTRA cell, performs a TAU procedure, and, successfully completes the Emergency call setup in EPS | Samsung | Opt 2: RAN5#86 (Feb-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-197091, R5-198975, R5-204467, R5-210133 |  | 1 | 28.57% | 6 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
8 |  | 38.523-1 | 11.1.x | FFS | FFS - No test purpose details specified yet. |  |  |  | Not pursued | 0 |  | 10 |  |  |  | 1 |  | 1 |  |  |  | 1 |  |  |  | 1
5GS/RAT fallback
|  | 38.523-1 | 11.x | 5GS/RAT Fallback | New sub-clause |  |  |  | Not pursued. Section given away to another WI. If need to be ever introduced, a new section needed | 0 |  | 10 |  |  |  | 1 |  | 1 |  |  |  | 1 |  |  |  | 1
Unified Access Control (UAC)
17 |  | 38.523-1 | 11.3 | Unified Access Control (UAC) | New sub-clause | Samsung | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS |  |  | 0.1 | 100% | 4 | 100% | 100% |  | 1 | 100% | 1 |  |  |  | 1 | 100% | 100% |  | 1 | 100% | 100%
40 | Y | 38.523-1 | 11.3.1 | UAC / Access Identity 0 / 0% access probability / MTSI MO speech call/SMSoIP/Uplink User data transfer | Editor's note: Conformance references: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.4.2 , 4.5.6, 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) having received a SIB1 message indicating UAC Info set to 0% accessibility for Access category 4 and in NR RRC_IDLE WHEN: User initiates MMTEL Voice call THEN: UE does not initiate connection over NR Cell **** TP2: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) , previously barred for MO MTSI MMTEL Voice in NR RRC_IDLE & current SIB1 indicates no access barred as part of UAC Info WHEN: user tries another MO MTSI MMTEL Voice session after T390 expires WHEN: user tries another MO MTSI MMTEL Voice session after T390 expires THEN: UE is able to successfully establish MMTEL Voice session **** TP3: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) with SIB1 indicating UAC info set to 0% accessibility for Access category 6 in NR RRC_CONNECTED state WHEN: user tries another MO MTSI MMTEL Voice session after T390 expires WHEN: user tries to send SMS over IP THEN: UE does not initiate SMS access attempt **** TP4: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) , with atleast one PDU Session in 5GSM PDU SESSION ACTIVE state (with user plane suspended) in NR RRC_INACTIVE state & SIB1 indicating 0% accessibility for Access Category 7 in NR RRC_INACTIVE state WHEN: User initiates uplink user data packet to be sent for a PDU session with suspended user-plane resources THEN: UE does not send the data packet | Huawei | Opt 2: RAN5#88 (Aug-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-202668, R5-206363, R5-210356 |  | 1 | 28.57% | 8 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
32 | Y | 38.523-1 | 11.3.2 | UAC / Access Identity 0 / 0% access probability / Paging for MT Access/Emergency Call | Editor's note: Conformance references: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.6, TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) having received a SIB1 message indicating 0% accessibility for all Access Categories in NR RRC_Idle state WHEN: UE is paged for MT access THEN: UE does not consider the access as barred and initiates RRC Connection **** TP2: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) having received a SIB1 message including UAC Info set to 0% accessibility for Access Category 2 in NR RRC_Idle state WHEN: UE attempts emergency call THEN: UE does not initiate emergency call **** TP3: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) with T302 running but T390 expired for Access Category 2 and with SIB1 including UAC Info indicating 100% accessibility for Acces Category 2 in NR RRC_IDLE state WHEN: UE attempts emergency call THEN: UE does not consider the access attempt as barred and initiates the emergency call | Qualcomm | Opt 2: RAN5#88 (Aug-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-204518, R5-205321 |  | 1 | 28.57% | 8 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
33 | Y | 38.523-1 | 11.3.3 | UAC / Access Identity 0 / AC8 / RRC_INACTIVE / RNAUpdate/RRC Resume | Editor's note: Conformance references: TS 24.501 4.5.2 , 4.5.4.2 , 4.5.6, TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) having received SIB1 indicating UAC info containing 0% accessiblity for Access category 8 in NR RRC_INACTIVE state WHEN: RRC connection is to be resumed due to an RNA update with no emergency services ongoing THEN: UE resume attempt is barred and UE does not attempt the connection **** TP2: [TS <TS#1>:FFS] WITH: SIB1 indicating UAC info containing 100% accessiblity for Access category 8 in NR RRC_INACTIVE state WHEN: Access Barring is alleviated for Access Category 8 & upper layers do not request resumption of an RRC connection & variable pendingRnaUpdate is set to true THEN: UE initiates RRC connection resume procedure with resumeCause value set to rna-Update | CATT | Opt 2: RAN5#85 (Nov-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-199037, R5-200357 |  | 1 | 28.57% | 5 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
34 | Y | 38.523-1 | 11.3.4 | UAC / Access Identity 0 / Registration procedure for mobility and periodic registration update / BarringPerPLMN/Implicit AC Barring List | Editor's note: Conformance references: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.6; TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE in NR RRC_IDLE not configured for special AIs (1,2,11-15) having received a SIB1 message including UAC set to 0% accessibility for Access Category 3 WHEN: UE finds a new cell (AC 3) with SIB1 containing UAC Barring Info Per PLMNwith Implicit AC Barring List THEN: UE does not move to the new cell until barring is alleviated | CATT | Opt 2: RAN5#85 (Nov-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-198985, R5-200358, R5-202671, R5-206364, R5-211408 |  | 1 | 28.57% | 5 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
35 | Y | 38.523-1 | 11.3.5 | UAC / Access Identity 1 / New cell not in the country of its HPLMN/EHPLMN 0% access probability/MPS indicator / HPLMN/0%/100% accessibility AC5/MMTEL-Video call | Editor's note: Conformance Requirements: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.6; TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE configured for Access Identity 1 WHEN: UE moves to a new cell which is not in the country of its HPLMN or in an EHPLMN (if the EHPLMN list is present) having received SIB1 message including UAC set to 0% accessibility for Access Identity 1 THEN: UE does not consider Access Identity 1 as valid and continues with the REGISTRATION procedure **** TP2: [TS <TS#1>:FFS] WITH: UE configured for Access Identity 1 WHEN: UE moves to a new cell which is not in the country of its HPLMN or in an EHPLMN (if the EHPLMN list is present) but receives the MPS indicator bit of the 5GS network feature support IE in the REGISTRATION ACCEPT message being set to "Access identity 1 valid" THEN: UE does consider Access Identity 1 as valid **** TP3: [TS <TS#1>:FFS] WITH: UE configured for Access Identity 1 having received SIB1 containing UAC Barring Info indicating 0% accessibility for Access Category 5 in NR RRC_IDLE state on HPLMN WHEN: User initiates MMTEL-Video call THEN: UE does not attempt to initiate connection on the NR Cell **** TP4: [TS <TS#1>:FFS] WITH: UE configured for Access Identity 1 having received SIB1 containig UAC Info indicating 100% accessibility for Access Cateogry 5 while camped on HPLMN in NR RRC_IDLE state WHEN: User initiates MMTEL-Video call and Access Barring check indicates Barring is alleviated THEN: UE initiates RRC Connection Setup procedure with establishmentCause set to mps-PriorityAccess | Huawei | Opt 2: RAN5#91 (May-21) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-201379 | IMS relevant parts still not completed FR2 Cell settings FFS USIM configuration FFS | 1 | 20% | 11 | 70% | 70% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
36 | Y | 38.523-1 | 11.3.6 | UAC / Access Identity 2 / New cell not in the country of its HPLMN/EHPLMN 0% access probability/MCS indicator / HPLMN/0%/100% accessibility AC7/RRC_INACTIVE | Editor's note: Conformance requirements: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.6; TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE configured for Acces Identity 2 WHEN: UE moves to a new cell which is not in the country of its HPLMN or in an EHPLMN (if the EHPLMN list is present) having received SIB1 message including UAC set to 0% accessibility for Access Identity 2 THEN: UE does not consider Access Identity 2 as valid and continues with the REGISTRATION procedure **** TP2: [TS <TS#1>:FFS] WITH: UE configured for Acces Identity 2 WHEN: UE moves to a new cell which is not in the country of its HPLMN or in an EHPLMN (if the EHPLMN list is present) but receives the MCS indicator bit of the 5GS network feature support IE in the REGISTRATION ACCEPT message being set to "Access identity 2 valid" THEN: UE does consider Access Identity 2 as valid **** TP3: [TS <TS#1>:FFS] WITH: UE configured for Acces Identity 2 having received SIB1 containing UAC Info indicating 0% accessibility for Access Category 7 camped in NR RRC_INACTIVE state on HPLMN WHEN: UE attempts to send uplink user data packet for a PDU session with suspended user-plane resources THEN: UE does not attempt to initiate connection on the NR Cell until barring is alleviated **** TP4: [TS <TS#1>:FFS] WITH: UE configured for Acces Identity 2 having received SIB1 containig UAC Info indicating 100% accessibility for Access Category 7 while camped on HPLMN in NR RRC_INACTIVE state WHEN: UE attempts to send uplink user data packet for a PDU session with suspended user-plane resources THEN: UE initiates RRC Resume procedure with establishmentCause set to mcs-PriorityAccess | Huawei | Opt 2: RAN5#91 (May-21) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-199036, R5-201227, R5-211409 | FR2 Cell settings FFS | 1 | 25.71% | 11 | 100% | 80% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
37 | Y | 38.523-1 | 11.3.7 | UAC / Access Identity 11..15 / High Priority Access / HPLMN/0% accessibility AC2/Emergency call | Editor's note: Conformance Requirements: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.6; TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE configured for Acces Identity 11..15 having received SIB1 containing UAC Info indicating 0% accessibility for Access Category 2 camped in NR RRC_IDLE state on HPLMN WHEN: User initiates MO emergency call THEN: UE does not initiate emergency call on NR Cell | Qualcomm | Opt 2: RAN5#87 (May-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-201633, R5-211410 |  | 1 | 28.57% | 7 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
38 | Y | 38.523-1 | 11.3.8 | UAC / Access Identity 0 / NR RRC_IDLE / Cell re-selection while T390 is running | Editor's note: Conformance Requirements: TS 24.501 4.5.2 , 4.5.4.1 , 4.5.6; TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) ,having access barred for MO MMTEL Voice and T390 running in NR RRC_IDLE state WHEN: UE performs Cell Reselection to a new NR Cell THEN: UE stops T390 for MO MMTEL Voice and informs upper layers about barring alleviation for this Access Category | Qualcomm | Opt 2: RAN5#87 (May-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-202670, R5-204019 |  | 1 | 28.57% | 7 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
12 | Y | 38.523-1 | 11.3.9 | UAC / Access Identity 0 / ODAC / PLMN/RPLMN/not EPLMN | Editor's note: Conformance Requirements: TS 24.501 4.5.3; TS 38.331 5.3.14 **** TP1: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) having received Operator Defined Access Category ""x"" in the range 32..63 with access category criteria type set to ""DNN"" valid in the selected PLMN or RPLMN as part of Registration Procedure WHEN: SIB1 message indicates no barring for Access category 7 but 0% accessibility for Access Category ""x" THEN: UE does not initiate PDU Session Establishment for the "DNN" **** TP2: [TS <TS#1>:FFS] WITH: UE not configured for special AIs (1,2,11-15) having received Operator Defined Access Category ""x"" in the range 32..63 with access category criteria type set to ""DNN"" valid in the selected PLMN or RPLMN as part of Registration Procedure , SIB1 message indicates no barring for Access category 7 but 0% accessibility for Access Category ""x" WHEN: UE moves to another cell belonging to a different PLMN not equivalent to the previous PLMN THEN: UE is able to initiate PDU Session Establishment for "DNN" in the new PLMN | Huawei | Opt 2: RAN5#91 (May-21) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-202669, R5-204468, R5-205388 | FR2 Cell settings FFS | 1 | 25.71% | 11 | 100% | 80% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
SDAP+5GSM interaction
|  | 38.523-1 | <Clause> | <Title> | FFS - No test purpose details specified yet. |  |  |  | Not Pursued | 0 |  | 4 |  |  |  | 1 |  | 4 |  |  |  | 1 |  |  |  | 1
Emergency
18 |  | 38.523-1 | 11.4 | Emergency Services | New sub-clause | Samsung | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS |  |  | 0.1 | 100% | 4 | 100% | 100% |  | 1 | 100% | 1 |  |  |  | 1 | 100% | 100% |  | 1 | 100% | 100%
14 | Y | 38.523-1 | 11.4.1 | 5GMM-REGISTERED.NORMAL-SERVICE / 5GMM-IDLE / Emergency call / Utilising emergency number stored on the USIM / New emergency PDU session / Network failing the authentication check (5G AKA) | **** TP1: [TS TS 36.331:5.3.3.3; TS TS 24.501:5.6.1.2, 6.4.1.2; TS TS 31.102:10.1.1] WITH: UE in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-IDLE mode WHEN: UE is requested to make an outgoing call using an emergency number storred on the USIM THEN: UE establishes an RRC connection with the RRC establishmentCause set to "emergency", and, sends a SERVICE REQUEST message with Service type IE set to "emergency services", and, establishes a New emergency PDU session by sending an UL NAS TRANSPORT message with Request type set to "initial emergency request" and a PDU SESSION ESTABLISHMENT REQUEST **** TP2: [TS TS 24.501:5.4.1.3.7] WITH: UE in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-CONNECTED mode having established an Emergency call WHEN: UE establishes that the network has failed the authentication check during a 5G AKA based primary authentication and key agreement procedure THEN: UE continues using the current security context, and, releases all non-emergency PDU sessions by initiating UE-requested PDU session release procedure and treats the active cell as barred for non-emergencvy services | Samsung | Opt 2: RAN5#85 (Nov-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-197219, R5-196997, R5-198986, R5-200227, R5-201032, R5-206365 | Incorporated the initially planed separate TC 11.4.x | 1 | 28.57% | 5 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
21 | Y | 38.523-1 | 11.4.2 | 5GMM-DEREGISTERED.LIMITED-SERVICE / Emergency call / Utilisation of emergency numbers stored on the ME / Initial registration for emergency services / Handling of forbidden PLMNs | **** TP1: [TS TS 36.331:5.3.3.3; TS TS 23.501:5.16.4.1; TS TS 23.122:2, 3.1, 3.5; TS TS 24.501:4.4.4.1, 5.1.3.2.1.3.3, 5.4.2.3, 5.5.1.2.2, 6.4.1.2; TS TS 31.102:10.1.1] WITH: UE in 5GMM-DEREGISTERED.LIMITED-SERVICE state WHEN: UE is requested to make an outgoing call using an emergency number storred on the ME THEN: UE establishes an RRC connection with the RRC establishmentCause set to "emergency", and, attempts a Initial registration for emergency services by sending a REGISTRATION REQUEST message with IE Service type set to "emergency services", and, accepts and applies security with NULL security and integrity algorithms, and, after successfull completion of the registration for emergency services establishes an emergency PDU session by sending an UL NAS TRANSPORT message with Request type set to "initial emergency request" and a PDU SESSION ESTABLISHMENT REQUEST **** TP2: [TS TS 24.501:5.5.1.2.4] WITH: UE in 5GMM-DEREGISTERED.LIMITED-SERVICE state WHEN: UE has performed an IMS Emergency call on a forbidden PLMN THEN: UE does not remove the PLMN code of the accessed PLMN from the list of forbidden PLMNs | Samsung | Opt 2: RAN5#85 (Nov-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-197220, R5-197246, R5-198987, R5-200229, R5-202550, R5-211411 |  | 1 | 28.57% | 5 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
22 | Y | 38.523-1 | 11.4.3 | 5GMM-DEREGISTERED.NO-SUPI / Emergency call / Utilisation of emergency numbers stored on the ME / Initial registration for emergency services | **** TP1: [TS TS 36.331:5.3.3.3; TS TS 23.501:5.16.4.1; TS TS 23.122:2, 3.1, 3.5; TS TS 24.501:4.4.4.1, 5.1.3.2.1.3.6, 5.4.2.3, 5.5.1.2.2, 6.4.1.2; TS TS 31.102:10.1.1] WITH: UE in 5GMM-DEREGISTERED.NO-SUPI state WHEN: UE is requested to make an outgoing call using an emergency number storred on the ME THEN: UE establishes an RRC connection with the RRC establishmentCause set to "emergency", and, attempts a Initial registration for emergency services by sending a REGISTRATION REQUEST message with IE Service type set to "emergency services", and, accepts and applies security with NULL security and integrity algorithms, and, after successfull completion of the registration for emergency services establishes an emergency PDU session by sending an UL NAS TRANSPORT message with Request type set to "initial emergency request" and a PDU SESSION ESTABLISHMENT REQUEST | Samsung | Opt 2: RAN5#85 (Nov-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-197221, R5-197246, R5-198988, R5-211411 |  | 1 | 28.57% | 5 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
31 | Y | 38.523-1 | 11.4.4 | 5GMM-REGISTERED.ATTEMPTING-REGISTRATION-UPDATE T3346 running / Emergency call establishment / 5GMM-REGISTERED.NORMAL-SERVICE / Emergency call establishment before T3396 expiry | **** TP1: [TS TS 24.501:5.5.1.3.5, 5.3.9, 5.5.1.3.2] WITH: UE in 5GMM-REGISTERED.ATTEMPTING-REGISTRATION-UPDATE state, timer T3346 is running and 5GMM-IDLE mode WHEN: UE is requested to make an Emergency call THEN: UE initiate the registration procedure for mobility and periodic registration update, and, establishes the Emergency call | Samsung | Opt 2: RAN5#85 (Nov-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-198989, R5-200230, R5-201033, R5-206366 | Incorporated the initially planed separate TC 11.4.y | 1 | 28.57% | 5 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
23 | Y | 38.523-1 | 11.4.5 | 5GMM-REGISTERED.LIMITED-SERVICE / 5GMM-IDLE / Emergency call establishment and release / Handling of 5GS forbidden tracking areas for roaming | **** TP1: [TS TS 24.501:5.5.1.3.5; TS TS 23.122:3.4.2] WITH: UE in 5GMM-REGISTERED.LIMITED-SERVICE state and 5GMM-IDLE mode WHEN: UE is requested to make an Emergency call THEN: UE establishes the Emergency call **** TP2: [TS TS 24.501:5.5.1.3.5; TS TS 23.122:3.4.2] WITH: UE in 5GMM-REGISTERED.LIMITED-SERVICE state and 5GMM-IDLE mode having established an Emergency call WHEN: UE is requested to release the Emergency call THEN: UE releases the Emergency call, and, the UE considers the current cell as belonging to 5GS forbidden tracking areas for roaming | Samsung | Opt 2: RAN5#85 (Nov-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-198990 |  | 1 | 28.57% | 5 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
24 | Y | 38.523-1 | 11.4.6 | 5GMM-REGISTERED.NON-ALLOWED-SERVICE / Emergency call establishment and release / Handling of non-allowed tracking areas | **** TP1: [TS TS 24.501:5.3.5; TS TS 22.101:10.1.1] WITH: UE in 5GMM-REGISTERED.NON-ALLOWED-SERVICE state and 5GMM-IDLE mode WHEN: UE is requested to make an Emergency call THEN: UE establishes the Emergency call **** TP2: [TS TS 24.501:5.3.5; TS TS 22.101:10.1.1] WITH: UE in 5GMM-REGISTERED.NON-ALLOWED-SERVICE state and 5GMM-CONNECTED mode having established an Emergency call WHEN: UE is requested to release the Emergency call THEN: UE releases the Emergency call, and, the UE considers the current cell as belonging to non-allowed tracking areas | Samsung | Opt 2: RAN5#85 (Nov-19) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-198991, R5-200232 |  | 1 | 28.57% | 5 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
25 |  | 38.523-1 | 11.4.x | 5GMM-REGISTERED.NORMAL-SERVICE / 5GMM-IDLE / Emergency call establishment and release / Network failing the authentication check (5G AKA) |  | Samsung |  |  | Scope of TC added into TC 11.4.1 | 0 |  | 6 |  |  |  | 1 |  | 1 |  |  |  | 1 |  |  |  | 1
26 |  | 38.523-1 | 11.4.y | 5GMM-REGISTERED.NORMAL-SERVICE / Emergency call establishment before T3396 expiry |  | Samsung |  |  | Scope of TC added into TC 11.4.4 | 0 |  | 6 |  |  |  | 1 |  | 1 |  |  |  | 1 |  |  |  | 1
27 | Y | 38.523-1 | 11.4.9 | 5GMM-DEREGISTERED.LIMITED-SERVICE No suitable cells in tracking area / Emergency call establishment and release | **** TP1: [TS TS 36.331:5.3.3.3; TS TS 23.501:5.16.4.1; TS TS 23.122:3.4.2; TS TS 24.501:5.5.1.2.5, 4.4.4.1, 5.1.3.2.1.3.3, 5.3.2, 5.4.2.3, 5.5.1.2.2, 6.4.1.2; TS TS 31.102:10.1.1] WITH: UE in 5GMM-DEREGISTERED.LIMITED-SERVICE state after receiving REGISTRATION REJECT message with 5GMM cause value #15 'No suitable cells in tracking area' WHEN: UE is requested to make an Emergency call THEN: UE establishes an RRC connection with the RRC establishmentCause set to "emergency", and, attempts an Initial registration for emergency services by sending a REGISTRATION REQUEST message with IE Service type set to "emergency services", and, accepts and applies security with NULL security and integrity algorithms, and, after successful completion of the registration for emergency services establishes an emergency PDU session by sending an UL NAS TRANSPORT message with Request type set to "initial emergency request" and a PDU SESSION ESTABLISHMENT REQUEST **** TP2: [TS TS 24.501:5.5.1.2.5] WITH: UE in 5GMM-DEREGISTERED.LIMITED-SERVICE state after receiving REGISTRATION REJECT message with 5GMM cause value #15 'No suitable cells in tracking area' and having established an Emergency call WHEN: UE is requested to release the Emergency call THEN: UE releases the Emergency call, and, the UE considers the current cell as belonging to 5GS forbidden tracking areas for roaming | Samsung | Opt 2: RAN5#88 (Aug-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-202551 |  | 1 | 28.57% | 8 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
28 | Y | 38.523-1 | 11.4.10 | 5GMM-REGISTERED.NORMAL-SERVICE / N26 interface not supported / N1 mode to S1 mode transfer of an existing emergency PDU session | **** TP1: [TS TS 24.501:6.1.4.2; TS TS 22.101:10.1.1] WITH: UE in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-IDLE mode with Interworking without N26 interface supported, and, the UE has an emergency PDU session established WHEN: UE performs a inter-system change from the N1 to S1 mode THEN: UE correctly transfers the existing emergency PDU session into an emergency PDN connection | Samsung | Opt 2: RAN5#88 (Aug-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-202672, R5-210163 |  | 1 | 28.57% | 8 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
29 | Y | 38.523-1 | 11.4.7 | Handling of Local and Extended emergency numbers / Mobility | Editor's note: TC contain 11 TPs. For simplicity only one added here with All conformance references **** TP1: [TS TS 38.331:5.3.3.3; TS TS 24.501:5.3.12; TS TS 24.301:5.3.7; TS TS 22.101:10.1.1] WITH: UE in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-IDLE mode, UE receives a Local emergency numbers list in the REGISTRATION ACCEPT message, provided in the Emergency number list IE WHEN: UE is requested to make an outgoing call using any of the emergency numbers received in the Local emergency numbers list THEN: UE establishes an IMS Emergency call | Samsung | Opt 2: RAN5#87 (May-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-200233 | Test case renumbered. Initial scope split in 2 tests (11.4.7 and 11.4.8). | 1 | 28.57% | 7 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
39 | Y | 38.523-1 | 11.4.8 | Handling of Local and extended emergency numbers / Switch-off and maximum local numbers storage | Editor's note: This test has 4 TPs. For simplicit only one is listed here together with all conformance requirements **** TP1: [TS TS 38.331:5.3.3.3; TS TS 24.501:5.3.12; TS TS 24.301:5.3.7; TS TS 22.101:10.1.1] WITH: UE in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-IDLE mode, having stored a Local emergency numbers list WHEN: UE is switched off or the USIM is removed THEN: UE deletes the stored Local emergency numbers list in the user equipment | Samsung | Opt 2: RAN5#87 (May-20) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-200234, R5-210571 | Test case renumbered. Initial scope split in 2 tests (11.4.7 and 11.4.8). | 1 | 28.57% | 7 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
30 | Y | 38.523-1 | 11.4.11 | 5GMM-REGISTERED.NORMAL-SERVICE / N26 interface not supported / S1 mode to N1 mode transfer of an existing PDN connection for emergency services | **** TP1: [TS TS 24.501:6.1.4.2; TS TS 22.101:10.1.1; TS <TS#n>:FFS] WITH: UE in EMM-REGISTERED and EMM-IDLE on an E-UTRA cell, and, the UE has an emergency PDN connection established WHEN: UE performs a inter-system change from the S1 to N1 mode, to an NR Cell belonging to a NWK supporting Interworking without N26 interface THEN: UE correctly transfers the existing emergency PDN connection into an emergency PDU session | Samsung | Opt 2: RAN5#90 (Feb-21) Opt 5: FFS Opt 4: FFS Opt 7: FFS | R5-210165, R5-211414 |  | 1 | 28.57% | 10 | 100% | 100% |  | 1 | 0% | 1 |  |  |  | 1 | 0% | 0% |  | 1 | 0% | 0%
<area#5>
|  | 38.523-1 | <Clause> | <Title> | FFS - No test purpose details specified yet. |  |  |  |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  |  |  | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A7: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B7: Y = the WP Pitem is a test case.
Note on K7: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.