## Cover sheet
3GPP TSG-RAN WG5 Meeting #91-e | [10 empty] | R5-213361
Electronic Meeting, 17th May - 28th May 2021
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | Work plan for UE Conformance Test Aspects for CLI handling for NR
Work item code: | NR_CLI-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#89-e meeting a Rel-16 RAN5 work item for UE Conformance Test Aspects for CLI (Cross Link Interference) handling for NR (NR_CLI-UEConTest) was approved [1]. The objective of this work item is to define the UE conformance requirements corresponding to WID on CLI handling support for NR. This work item will cover RRM conformance test specifications aspects for CLI including the Applicability, Test Environment, Intial Conditions, Test Procedure, Messaeg Exceptions, Test Setup, Connection Diagram, etc. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item. The present document is an update of the WP submitted at the end of RAN5#90-e [3].
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% | 0 | 16
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5.2% | 0 | 8
FR1 |  | 5.5% | 0 | 4
FR2 |  | 5% | 0 | 4
FR1 + FR2
NSA Option 3 (EN-DC) |  | 5% | 0 | 8
FR1 |  | 5% | 0 | 4
FR2 |  | 5% | 0 | 4
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 1.6% |  |  | 5% |  |  | 0% | [5 empty] | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0% | [5 empty] | 0% |  |  | 0%
NR RF/RRM
RRM test cases | 38.533 | 0% | 0 | 16 | 0% | 0 | 4 | 0% | 0 | 4 |  |  |  | 0% | 0 | 4 | 0% | 0 | 4
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0% |  |  | 0% | [5 empty] | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903
5 References
[1] RP-201940 | New WID on UE Conformance Test Aspects for CLI handling for NR – Qualcomm (Supporting companies: Anritsu, Apple, AT&T, Bureau Veritas, Lenovo, LG Electronics, Motorola Mobility, Rohde & Schwarz, ZTE)
[2] R5-206199 | WP UE Conformance Test Aspects - Rel -16 for CLI handling for NR
[3] R5-211366 | WP UE Conformance Test Aspects - Rel -16 for CLI handling for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for CLI handling for NR | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [5 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_CLI-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item CLI handling for NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate (RRM conformance test specifications aspects for CLI including the Applicability, Test Environment, Intial Conditions, Test Procedure, Messaeg Exceptions, Test Setup, Connection Diagram, etc.), with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [13 empty] | vs Area
WP Resp: |  | Vijay Balasubramanian, Qualcomm |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2
[15 empty] | 5.5% | 5% |  | 5% | 5%
[15 empty] | 9 | 9 | 0 | 9 | 9 | 0
[15 empty] | 5.1 | 5.1 | 0 | 5.1 | 5.1 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4 | Common test environments | Default NG-RAN RRC message and information elements contents for Rel-16 CLI Handling for NR ASN.1 update (RRC messages carrying CLI related IE’s). |  | RAN5#93 (Nov-21) |  |  | 0.5 | 1.2% | 2.5% | 0% |  | 5% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | A.4 | Common Implementation Conformance Statement (ICS) proforma | Introduction of common implementation conformance statements for Rel-16 CLI Handling. CAG PICS Resolve Applicability for CLI |  | RAN5#93 (Nov-21) |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0% |  | 0% | 0%
NR RF/RRM
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
3 |  | 38.522 | 4.2 | RRM conformance test cases | Introduction of test applicability for RRM test cases impacted by R16 CLI Handling. |  | RAN5#93 (Nov-21) |  |  | 0.1 | 0% | 0% | 0% |  | 0% | 0% |  | 0% | 0%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
4 |  | 38.533 | 4.6.5 | <Title> | New sub-section title |  |  |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
5 | Y | 38.533 | 4.6.5.1 | EN-DC FR1 SRS-RSRP measurement in non-DRX | • To verify that the UE makes correct reporting of SRS-RSRP measurement. • This test will verify the SRS-RSRP measurement requirements in clause 9.7.2.5, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
6 | Y | 38.533 | 4.6.5.2 | EN-DC FR1 CLI-RSSI measurement in non-DRX | • To verify that the UE makes correct reporting of CLI-RSSI measurement. • This test will verify the CLI-RSSI measurement requirements in clause 9.7.3.5, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
7 |  | 38.533 | 4.7.6 | <Title> | New sub-section title |  |  |  |  | 0 | 0% |  | 0% |  |  |  |  | 0%
8 | Y | 38.533 | 4.7.6.1 | EN-DC FR1 SRS-RSRP measurement accuracy | • To verify that the SRS-RSRP measurement accuracy is within the specified limits. • This test will verify the requirements in Clauses 10.1.22.1.1, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
9 | Y | 38.533 | 4.7.6.2 | EN-DC FR1 CLI-RSSI measurement accuracy | • To verify that the CLI-RSSI measurement accuracy is within the specified limits. • This test will verify the requirements in Clauses 10.1.22.2.1, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
10 |  | 38.533 | 5.6.4 | <Title> | New sub-section title |  |  |  |  | 0 | 0% |  | 0% | [5 empty] | 0%
11 | Y | 38.533 | 5.6.4.1 | EN-DC FR2 SRS-RSRP measurement in non-DRX | • To verify that the UE makes correct reporting of SRS-RSRP measurement. • This test will verify the SRS-RSRP measurement requirements in clause 9.7.2.5, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
12 | Y | 38.533 | 5.6.4.2 | EN-DC FR2 CLI-RSSI measurement in non-DRX | • To verify that the UE makes correct reporting of CLI-RSSI measurement. • This test will verify the CLI-RSSI measurement requirements in clause 9.7.3.5, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
13 |  | 38.533 | 5.7.5 | <Title> | New sub-section title |  |  |  |  | 0 | 0% |  | 0% | [5 empty] | 0%
14 | Y | 38.533 | 5.7.5.1 | EN-DC FR2 SRS-RSRP measurement accuracy | • To verify that the SRS-RSRP measurement accuracy is within the specified limits. • This test will verify the requirements in Clauses 10.1.22.1.1, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
15 | Y | 38.533 | 5.7.5.2 | EN-DC FR2 CLI-RSSI measurement accuracy | • To verify that the CLI-RSSI measurement accuracy is within the specified limits. • This test will verify the requirements in Clauses 10.1.22.2.1, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
16 |  | 38.533 | 6.6.6 | <Title> | New sub-section title |  |  |  |  | 0 | 0% | 0% |  |  | 0%
17 | Y | 38.533 | 6.6.6.1 | NR SA FR1 SRS-RSRP measurement in non-DRX | • To verify that the UE makes correct reporting of SRS-RSRP measurement. • This test will verify the SRS-RSRP measurement requirements in clause 9.7.2.5, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  | 0%
18 | Y | 38.533 | 6.6.6.2 | NR SA FR1 CLI-RSSI measurement in non-DRX | • To verify that the UE makes correct reporting of CLI-RSSI measurement. • This test will verify the CLI-RSSI measurement requirements in clause 9.7.3.5, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  | 0%
19 |  | 38.533 | 6.7.8 | <Title> | New sub-section title |  |  |  |  | 0 | 0% | 0% |  |  | 0%
20 | Y | 38.533 | 6.7.8.1 | NR SA FR1 SRS-RSRP measurement accuracy | • To verify that the SRS-RSRP measurement accuracy is within the specified limits. • This test will verify the requirements in Clauses 10.1.22.1.1, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  | 0%
21 | Y | 38.533 | 6.7.8.2 | NR SA FR1 CLI-RSSI measurement accuracy | • To verify that the CLI-RSSI measurement accuracy is within the specified limits. • This test will verify the requirements in Clauses 10.1.22.2.1, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  | 0%
22 |  | 38.533 | 7.6.4 | <Title> | New sub-section title |  |  |  |  | 0 | 0% | 0% |  |  |  | 0%
23 | Y | 38.533 | 7.6.4.1 | NR SA FR2 SRS-RSRP measurement in non-DRX | • To verify that the UE makes correct reporting of SRS-RSRP measurement. • This test will verify the SRS-RSRP measurement requirements in clause 9.7.2.5, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
24 | Y | 38.533 | 7.6.4.2 | NR SA FR2 CLI-RSSI measurement in non-DRX | • To verify that the UE makes correct reporting of CLI-RSSI measurement. • This test will verify the CLI-RSSI measurement requirements in clause 9.7.3.5, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
25 |  | 38.533 | 7.7.5 | <Title> | New sub-section title |  |  |  |  | 0 | 0% | 0% |  |  |  | 0%
26 | Y | 38.533 | 7.7.5.1 | NR SA FR2 SRS-RSRP measurement accuracy | • To verify that the SRS-RSRP measurement accuracy is within the specified limits. • This test will verify the requirements in Clauses 10.1.22.1.1, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
27 | Y | 38.533 | 7.7.5.2 | NR SA FR2 CLI-RSSI measurement accuracy | • To verify that the CLI-RSSI measurement accuracy is within the specified limits. • This test will verify the requirements in Clauses 10.1.22.2.1, from 38.133. |  | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  |  |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  |  |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.