## Cover sheet
3GPP TSG-RAN WG5 Meeting #93-e | [10 empty] | R5-216557
Electronic Meeting, 8th -19th Nov 2021
Agenda Item: | 7.4.2
Source: | ZTE, China Telecom
Title: | WP UE Conformance Test Aspects for 2-step RACH for NR
Work item code: | NR_2step_RACH-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The Rel-16 WI NR_2step_RACH-Core and NR_2step_RACH-Perf has been 100% completed at RAN#90-e meeting. According to the requirements of NR network deployment and performance optimization, it is justified now to start the work on the corresponding UE conformance test specifications for 2-step RACH features in 3GPP RAN WG5 to meet the market requirements. At the RAN#91e meeting in March 2021 the Rel-16 RAN5 work item for UE Conformance Test Aspects for NR 2-step RACH was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 72% (+18%) | 2 (+2) | 12
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 68.8% (+17.8%) | 2 (+2) | 8
FR1 |  | 74.8% (+17.8%) | 2 (+2) | 6
FR2 |  | 62.9% (+17.8%) | 2 (+2) | 6
FR1 + FR2
NSA Option 3 (EN-DC) |  | 74.8% (+17.8%) | 2 (+2) | 8
FR1 |  | 74.8% (+17.8%) | 2 (+2) | 6
FR2 |  | 74.8% (+17.8%) | 2 (+2) | 6
FR1 + FR2
LTE
FDD
TDD
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%) | [5 empty] | 100% (+100%) |  |  | 100% (+100%)
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  | 100% | [5 empty] | 100% |  |  | 100%
NR RF/RRM
RRM test cases | 38.533 | 63.3% | 0 | 8 | 75% | 0 | 2 | 25% | 0 | 2 |  |  |  | 75% | 0 | 2 | 75% | 0 | 2
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 75% |  |  | 75% |  |  | 75% | [5 empty] | 75% |  |  | 75%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0% |  |  | 0% | [5 empty] | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 75% (+25%) | 2 (+2) | 4 | 75% (+25%) | 2 (+2) | 4 | 75% (+25%) | 2 (+2) | 4 |  |  |  | 75% (+25%) | 2 (+2) | 4 | 75% (+25%) | 2 (+2) | 4
Applicability Protocol test cases | 38.523-2 | 100% |  |  | 100% |  |  | 100% | [5 empty] | 100% |  |  | 100%
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0% | [5 empty] | 0% |  |  | 0%
5 References
[1] RP-210612 | New WID on UE Conformance Test Aspects for 2-step RACH for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for 2-step RACH for NR | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_2step_RACH-UEConTest
WP Scope: |  | Conformance test specifications for the core requirements of Rel-16 WI NR_2step_RACH-Core and NR_2step_RACH-Perf. The RAN5 areas of RRM and Protocol conformance test specifications with NR_2step_RACH operation are to be covered. | [14 empty] | vs Area
WP Resp: |  | Wei Ma |  |  | ma.wei4@zte.com.cn | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | LTE |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FDD | TDD | FDD + TDD
[14 empty] | Overall |  | 74.8% (+17.8%) | 62.9% (+17.8%) |  | 74.8% (+17.8%) | 74.8% (+17.8%)
[14 empty] | Number of WP items |  | 14 | 14 | 0 | 14 | 14 | 0 | 0 | 0 | 0
[14 empty] | Sum weight of WP items |  | 16 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0
[14 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4.6.3, 4.6.5 | RRC default messages | Add 2-step RACH changes to default messages if needed | ZTE | RAN5#94 (Feb-22) | R5-217943 |  | 2 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  |  | 100% | 100% |  | 100% | 100%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4.4 | Additional information | Define UE capabilities for MDT/SON features if needed | Lenovo, Motorola Mobility | RAN5#94 (Feb-22) | R5-213374 |  | 2 | 100% | 100% | 100% |  |  | 100% | 100% |  | 100% | 100%
NR RF/RRM
3 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. | R&S, NOKIA, China telecom | RAN5#94 (Feb-22) | R5-215399 |  | 1 | 75% | 75% | 75% |  |  | 75% | 75% |  | 75% | 75%
TS 38.533: RRM test cases
4 | Y | 38.533 | 4.3.2.2.3 | EN-DC FR1 2-step contention based random access | Add new test case for EN-DC FR1 2-step contention based random access | R&S | RAN5#94 (Feb-22) | R5-215392 |  | 1 | 50% |  | 50% | [5 empty] | 50%
5 | Y | 38.533 | 4.3.2.2.4 | EN-DC FR1 2-step non-contention based random access | Add new test case for EN-DC FR1 2-step non-contention based random access | R&S | RAN5#94 (Feb-22) | R5-215393 |  | 1 | 50% |  | 50% | [5 empty] | 50%
6 | Y | 38.533 | 5.3.2.2.3 | EN-DC FR2 2-step contention based random access | Add new test case for EN-DC FR2 2-step contention based random access | R&S | RAN5#94 (Feb-22) | R5-215394 |  | 1 | 50% |  | 50% | [6 empty] | 50%
7 | Y | 38.533 | 5.3.2.2.4 | EN-DC FR2 2-step non-contention based random access | Add new test case for EN-DC FR2 2-step non-contention based random access | R&S | RAN5#94 (Feb-22) | R5-215395 |  | 1 | 50% |  | 50% | [6 empty] | 50%
8 | Y | 38.533 | 6.3.2.2.3 | NR SA FR1 2-step contention based random access | Add new test case for NR SA FR1 2-step contention based random access | NOKIA,R&S | RAN5#94 (Feb-22) | R5-215396 |  | 1 | 50% | 50% |  |  |  | 50%
9 | Y | 38.533 | 6.3.2.2.4 | NR SA FR1 2-step non-contention based random access | Add new test case for NR SA FR1 2-step non-contention based random access | R&S | RAN5#94 (Feb-22) | R5-215397 |  | 1 | 50% | 50% |  |  |  | 50%
10 | Y | 38.533 | 7.3.2.2.3 | NR SA FR2 2-step contention based random access | Add new test case for NR SA FR2 2-step contention based random access | NOKIA | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
11 | Y | 38.533 | 7.3.2.2.4 | NR SA FR2 2-step non-contention based random access | Add new test case for NR SA FR2 2-step non-contention based random access | China telecom | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
12 |  | 38.533 | A.7A | Reference MsgA configurations | Add reference MsgA configurations | R&S | RAN5#94 (Feb-22) | R5-215436 |  | 1 | 100% | 100% | 100% |  |  | 100% | 100% |  | 100% | 100%
13 |  | 38.533 | E | Cell configuration mapping | Add Cell configuration mapping for new NR 2-step RACH test cases | R&S, Nokia, China telecom, | RAN5#94 (Feb-22) | R5-215398 |  | 1 | 75% | 50% | 100% |  |  | 100% | 0% |  | 100% | 100%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
14 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | Adding analysis of measurement uncertainties and tolerance for RRM testing. | R&S | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% | 0% |  |  | 0% | 0% |  | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Layer 2
15 | Y | 38.523-1 | 7.1.1.1.7 | Random access procedure / 2-step RACH / RA_TYPE selection | ***** TP1: [TS 38.321:5.1.1, 5.1.2a] WITH: UE in RRC_Connected NR PSCell TimeAlignmentTimer expired, and has UL Data to send WHEN:the BWP selected for Random Access procedure is configured with both 2-step and 4-step RA type Random Access Resources and the RSRP of the downlink pathloss reference is above msgA-RSRP-Threshold THEN:UE SET RA_TYPE to 2-step AND sends a MSGA on the NR PSCell ***** TP2: [TS 38.321:5.1.1, 5.1.2a] WITH: UE in RRC_Connected NR PSCell TimeAlignmentTimer expired, and has UL Data to send WHEN:BWP selected for Random Access procedure is only configured with 2-step RA type Random Access resources THEN:UE SET RA_TYPE to 2-step AND sends a MSGA on the NR PSCell ***** TP3: [TS 38.321:5.1.1, 5.1.2a] WITH: UE in RRC_Connected NR PSCell WHEN: SS sends an RRCReconfiguration message including RACH-ConfigDedicated information element and the contention-free Random Access Resources for 2-step RA type have been explicitly provided in rach-ConfigDedicated THEN:UE SET RA_TYPE to 2-step AND sends a MSGA on the NR PSCell | Motorola Mobility | RAN5#94 (Feb-22) | R5-213185 R5-215578 |  | 1 | 50% | 50% | 50% |  |  | 50% | 50% |  | 50% | 50%
16 | Y | 38.523-1 | 7.1.1.1.8 | Correct selection of RACH parameters / 2-step RACH/MSGA and PRACH resource explicitly signalled to the UE by RRC / contention free random access procedure | **** TP1: [TS 38.321:5.1.2a, 5.1.4a] WITH: UE in RRC_CONNECTED state WHEN: SS sends an RRCReconfiguration message including RACH-ConfigDedicated information element THEN: UE sends a MSGA given in the RACH-ConfigDedicated on the target cell **** TP2: [TS 38.321:5.1.2a, 5.1.4a] WITH: UE in RRC_Connected state after transmission of a MSGA on NR SpCell received in RACH-ConfigDedicated on the target cell WHEN: UE does not receive a matching MSGB in msgB-ResponseWindow and PREAMBLE_TRANSMISSION_COUNTER is less than msgA-TransMax THEN: UE retransmits a MSGA in RACH-ConfigDedicated on the target cell | Motorola Mobility | RAN5#94 (Feb-22) | R5-213186 R5-215579 |  | 1 | 50% | 50% | 50% |  |  | 50% | 50% |  | 50% | 50%
17 | Y | 38.523-1 | 7.1.1.1.9 | Random access procedure / Successful / 2-step RACH/C-RNTI Based / Preamble selected by MAC itself | **** TP1: [TS 38.321:5.1.2a, 5.1.3a, 5.1.4a, 5.1.5, 5.2] WITH: UE in RRC_Connected NR SpCell TimeAlignmentTimer expired, and has UL Data to send WHEN: the UL MAC PDU Size is less than ra-MsgA-SizeGroupA THEN: UE transmits a MSGA using a preamble in group A of random access preambles **** TP2: [TS 38.321:5.1.2a, 5.1.3a, 5.1.4a, 5.1.5, 5.2] WITH: UE in RRC_Connected state after transmission of a MSGA on NR PSCell WHEN: SS does not answer with a matching MSGB within msgB-ResponseWindow THEN: UE retransmits a MSGA using a preamble from same group **** TP3: [TS 38.321:5.1.2a, 5.1.3a, 5.1.4a, 5.1.5, 5.2] WITH: UE in RRC_Connected state after transmission of a MSGA on NR PSCell WHEN: SS sends a MSGB including a Backoff Indicator and the Random Access Preamble identifier is different from the value received from the UE THEN: UE performS the Random Access Resource selection procedure for 2-step RA type Random Access after a random time between 0 and the indicated Backoff parameter from same group **** TP4: [TS 38.321:5.1.2a, 5.1.3a, 5.1.4a, 5.1.5, 5.2] WITH: UE in RRC_Connected NR PSCell TimeAlignmentTimer expired, and has UL Data to send WHEN: the UL MAC PDU Size is greater than messageSizeGroupA THEN: UE transmits a MSGA using a preamble in group B of random access preambles **** TP5: [TS 38.321:5.1.2a, 5.1.3a, 5.1.4a, 5.1.5, 5.2] WITH: UE in RRC_Connected state and having initiated a 2-step RA type Random Access procedure in NR PSCell WHEN: The SS transmits a Timing Advance Command in a MSGB message THEN: the UE applies the received Timing Advance value in the next transmitted MAC PDU | MediaTek | RAN5#94 (Feb-22) | R5-214946 R5-217254 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  |  | 100% | 100% |  | 100% | 100%
18 | Y | 38.523-1 | 7.1.1.1.10 | Random access procedure / 2-step RACH/not complete/ RA_TYPE to 4-stepRA | ***** TP1: [TS 38.321:5.1.1, 5.1.2a] WITH: UE in RRC_Connected state after transmission of a MSGA on NR SpCell WHEN: UE does not receive a matching MSGB in msgB-ResponseWindow and PREAMBLE_TRANSMISSION_COUNTER is equal to msgA-TransMax THEN: UE triggers 4-step RACH procedue on NR SpCell | ZTE | RAN5#94 (Feb-22) | R5-214872 R5-217069 |  | 1 | 100% (+50%) | 100% (+50%) | 100% (+50%) |  |  | 100% | 100% |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
19 |  | 38.523-2 | 4.1 | Introduction the applicability statement for new test cases for 2-step RACH | Add test case applicability for new 2-step RACH test cases | ZTE, Mediatek, Motorola Mobility | RAN5#94 (Feb-22) | R5-213375 R5-214873 |  | 1 | 100% | 100% | 100% |  |  | 100% | 100% |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
20 |  | 38.523-3 | FFS | TTCN test model updates | Placeholder: FFS if needed |  | TBD |  |  | 1 | 0% | 0% | 0% |  |  | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.