## Cover sheet
3GPP TSG RAN WG5#93-e | [10 empty] | R5-216632
Electronic meeting, 8 - 19 November 2021
Agenda Item: | 7.4.2
Source: | Ericsson
Title: | Work plan - Power Class 2 for EN-DC with xLTE band + yNR DL with 1LTE+1(TDD) NR UL band (x= 2, 3, 4, y=1; x=1, 2, y=2)
Work item code: | ENDC_PC2_R17_xLTE_yNR-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-7
1. Introduction
This work plan introduces new Rel-17 High Power UE (HPUE) Power Class 2 (PC2) for EN-DC configurations with xLTE band + yNR DL with 1LTE+1(TDD) NR UL band (x= 2, 3, 4, y=1; x=1, 2, y=2) .
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed configurations (Note 1) | Number of new configurations | Comments
Overall completion |  | 5% | 0 | 221
Completion Compensation |  | -
| Note 1: | Only configurations completed for all applicable WP areas and sub-areas are counted. For completed configurations per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of completed PC2 configurations | Number of PC2 configurations | Comments
NSA Option 3 (EN-DC) |  | 5% | 0 | 221
FR1 |  | 5% | 0 | 208
FR1 + FR2 |  | 5% | 0 | 13
Estimation of completion per configuration area:
|  | TS/TR overall completion |  |  | NSA Option 3 (EN-DC)
Configuration Scope | TS/Area | Completion | Number of completed configurations | Number of configurations | FR1 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed configurations | Number of new configurations | Completion | Number of new completed configurations | Number of new configurations
EN-DC HPUE (PC2) FR1 configurations
EN-DC PC2 FR1 configurations
EN-DC PC2 FR1 Inter-band (two bands) | PC2 FR1 EN-DC (2 bands) | 0% | 0 | 5 | 0% | 0 | 5
EN-DC PC2 FR1 Inter-band (three bands) | PC2 FR1 EN-DC (3 bands) | 0% | 0 | 118 | 0% | 0 | 118
EN-DC PC2 FR1 Inter-band (four bands) | PC2 FR1 EN-DC (4 bands) | 0% | 0 | 73 | 0% | 0 | 73
EN-DC PC2 FR1 Inter-band (five bands) | PC2 FR1 EN-DC (5 bands) | 0% | 0 | 12 | 0% | 0 | 12
EN-DC HPUE (PC2) FR1+FR2 configurations
EN-DC FR1+FR2 PC2 (2 bands)
EN-DC PC2 FR1 +FR2 Inter-band (2 bands) | PC2 FR1+FR2 EN-DC (2 bands) | 0% | 0 | 13 |  |  |  | 0% | 0 | 13
5 References
[1] RP-211870 | WID on UE Conformance - PC2 EN-DC with x LTE band + y NR band (x= 2, 3, 4, y=1; x=1, 2, y=2)；Source: Ericsson
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Work plan UE Conformance - Power Class 2 for EN-DC with xLTE band + yNR DL with 1LTE+1(TDD) NR UL band (x= 2, 3, 4, y=1; x=1, 2, y=2) | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [7 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | ENDC_PC2_R17_xLTE_yNR-UEConTest | [15 empty] | 1 | 1 | 1 | 1 | 3 | 3
WP Scope: |  | This work plan covers the tasks needed to include Rel-17 Power Class 2 for EN-DC with xLTE band + yNR DL with 1LTE+1(TDD) NR UL band (x= 2, 3, 4, y=1; x=1, 2, y=2). | [14 empty] | vs Area | Confirm that PC3 requirement for the EN-DC configuration are completed in TS 38.101-3 | Confirm that EN-DC configuration for PC3 is completed in applicable RAN5 basket WI | 38.508-2: UE capabilities | 38.522: Updated applicability for PC2 the EN-DC configuration | 38.521-x: Tx test cases updated for PC2 (MOP, MPR, A-MPR, SEM, ACLR, A-SEM, A-SE) | 38.521-x: Rx Reference Sens test case updated for PC2
WP Resp: |  | Leif Mattisson (Ericsson) |  |  | leif.mattisson@ericsson.com | [7 empty] | WP item completion |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new configuration or test case? | TS/Area | Configuration / Test case clause | UL configuration(s) / Test case title | Type of change | Interested Operator | Company | Status | Target | TDOC(s) | Comments | Weight | Overall | NSA Option 3 (EN-DC) |  | FR1 | FR1 + FR2
[7 empty] | NOTE! No PC2 CRs shall be submitted to TS 38.521-3, 38.508-2 and TS 38.522 for an EN-DC configuration until after it has been confirmed that the PC2 requirements have been completed in RAN4 TS 38.101-3 and the EN-DC configuration has been completed for PC3 in RAN5. (Reference: RAN5#92-e, R5-215709) | [8 empty] | 5% | 5%
[16 empty] | 209 | 1
[16 empty] | 208 | 13
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [15 empty] | CALCULATED CELLS
38.101-3: HPUE (PC2) FR1 EN-DC Inter-band (two bands)
1 | Y | PC2 FR1 EN-DC (2 bands) | DC_2A_n77C | DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
2 | Y | PC2 FR1 EN-DC (2 bands) | DC_5A_n77C | DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
3 | Y | PC2 FR1 EN-DC (2 bands) | DC_13A_n77C | DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
4 | Y | PC2 FR1 EN-DC (2 bands) | DC_66A_n77C | DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
5 | Y | PC2 FR1 EN-DC (2 bands) | DC_66A-66A-66A_n77C | DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
38.101-3: HPUE (PC2) FR1+FR2 EN-DC Inter-band (two bands)
6 | Y | PC2 FR1+FR2 EN-DC (2 bands) | DC_n78A-n258A/B/C/D/E/F/G/H/I/J/K/L/M | DC_n78A-n258A/G/H/I | New PC2 Config | Telstra 1 |  | Pending | TBD |  |  | 13 | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
38.101-3: HPUE (PC2) FR1 EN-DC Inter-band (three bands)
7 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-5A_n77A | DC_2A_n77A, DC_5A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
8 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-13A_n77A | DC_2A_n77A, DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
9 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-66A_n77A | DC_2A_n77A, DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
10 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-66A_n77A | DC_5A_n77A, DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
11 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A-66A_n77A | DC_13A_n77A, DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
12 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A_n2A-n77A | DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
13 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A_n66A-n77A | DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
14 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A_n5A-n77A | DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
15 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A_n2A-n77A | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
16 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A_n5A-n77A | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
17 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A-66A_n5A-n77A | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
18 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-66A_n41A | DC_2A_n41A DC_66A_n41A | New PC2 Config | T-Mobile USA |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
19 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A-5A_n77A | DC_2A_n77A, DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
20 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A-13A_n77A | DC_2A_n77A, DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
21 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A-66A_n77A | DC_2A_n77A, DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
22 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-66A-66A_n77A | DC_2A_n77A, DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
23 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A-66A-66A_n77A | DC_13A_n77A, DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
24 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A-66A-66A_n77A | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
25 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-48C_n77A | DC_2A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
26 | Y | PC2 FR1 EN-DC (3 bands) | DC_48C-66A_n77A | DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
27 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-48D_n77A | DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
28 | Y | PC2 FR1 EN-DC (3 bands) | DC_48D-66A_n77A | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
29 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A_n66A-n77A | DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
30 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A_n66A-n77A | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
31 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A_n2A-n77A | DC_2A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
32 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A_n2A-n77A | DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
33 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A_n5A-n77A | DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
34 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A_n66A-n77A | DC_2A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
35 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A-66A_n5A-n77A | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
36 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A_n66A-n77A | DC_2A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
37 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-5A_n2A-n77A | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
38 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A-66A_n2A-n77A | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
39 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A_n5A-n77A | DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
40 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A_n5A-n77A | DC_2A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
41 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A_n66A-n77A | DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
42 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-13A_n77A | DC_5A_n77A DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
43 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-48A_n77A | DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
44 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-48C_n77A | DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
45 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A-48C_n77A | DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
46 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-48D_n77A | DC_5A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
47 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A-48D_n77A | DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
48 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A-66A_n77C | DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
49 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-66A_n77C | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
50 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-13A_n77C | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
51 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A-66A_n77C | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
52 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-66A_n77C | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
53 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-5A_n77C | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
54 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-48A_n77C | DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
55 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-48A_n77C | DC_5A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
56 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A-48A_n77C | DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
57 | Y | PC2 FR1 EN-DC (3 bands) | DC_48A-66A_n77C | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
58 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A_n77C | DC_2A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
59 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A-66A-66A_n77C | DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
60 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-66A-66A_n77C | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
61 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-66A-66A_n77C | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
62 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A-13A_n77C | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
63 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A-66A_n77C | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
64 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A-5A_n77C | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
65 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-48C_n77C | DC_2A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
66 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-48C_n77C | DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
67 | Y | PC2 FR1 EN-DC (3 bands) | DC_48C-66A_n77C | DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
68 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A-48C_n77C | DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
69 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A-66A-66A_n77C | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
70 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-48D_n77C | DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
71 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A-48D_n77C | DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
72 | Y | PC2 FR1 EN-DC (3 bands) | DC_48D-66A_n77C | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
73 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-5A-48C_n77C | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
74 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-13A-48C_n77C | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
75 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-48C-66A_n77C | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
76 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A-48C-66A_n77C | DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
77 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-48C-66A_n77C | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
78 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A_n2A-n77C | DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
79 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A_n66A-n77C | DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
80 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A_n2A-n77C | DC_2A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
81 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A_n2A-n77C | DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
82 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A_n2A-n77C | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
83 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A_n5A-n77C | DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
84 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A_n5A-n77C | DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
85 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A_n5A-n77C | DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
86 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A_n5A-n77C | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
87 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A_n66A-n77C | DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
88 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A_n66A-n77C | DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
89 | Y | PC2 FR1 EN-DC (3 bands) | DC_13A_n66A-n77C | DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
90 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A_n66A-n77C | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
91 | Y | PC2 FR1 EN-DC (3 bands) | DC_66A-66A_n5A-n77C | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
92 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A_n5A-n77C | DC_2A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
93 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-2A_n66A-n77C | DC_2A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
94 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-66A_n66A-n77C | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
95 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-48D_n77C | DC_5A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
96 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-13A_n77C | DC_5A_n77A DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
97 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-12A_n77A | DC_2A_n77A, DC_12A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
98 | Y | PC2 FR1 EN-DC (3 bands) | DC_12A-66A_n77A | DC_12A_n77A, DC_66A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
99 | Y | PC2 FR1 EN-DC (3 bands) | DC_12A-30A_n77A | DC_12A_n77A, DC_30A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
100 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-14A_n77A | DC_2A_n77A, DC_14A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
101 | Y | PC2 FR1 EN-DC (3 bands) | DC_14A-66A_n77A | DC_14A_n77A, DC_66A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
102 | Y | PC2 FR1 EN-DC (3 bands) | DC_14A-30A_n77A | DC_14A_n77A , DC_30A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
103 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-29A_n77A | DC_2A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
104 | Y | PC2 FR1 EN-DC (3 bands) | DC_2A-30A_n77A | DC_2A_n77A DC_30A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
105 | Y | PC2 FR1 EN-DC (3 bands) | DC_5A-30A_n77A | DC_5A_n77A DC_30A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
106 | Y | PC2 FR1 EN-DC (3 bands) | DC_29A-30A_n77A | DC_30A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
107 | Y | PC2 FR1 EN-DC (3 bands) | DC_29A-66A_n77A | DC_66A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
108 | Y | PC2 FR1 EN-DC (3 bands) | DC_30A-66A_n77A | DC_30A_n77A DC_66A_n77A | New PC2 Config |  |  | Pending | TBD |  | [RAN4: AT&T] | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
109 | Y | PC2 FR1 EN-DC (3 bands) | DC_3A-7A_n78A | DC_3A_n78A DC_7A_n78A | New PC2 Config | Telstra 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
110 | Y | PC2 FR1 EN-DC (3 bands) | DC_3A-7C_n78A | DC_3A_n78A DC_7A_n78A DC_7C_n78A | New PC2 Config | Telstra 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
111 | Y | PC2 FR1 EN-DC (3 bands) | DC_3C-7A_n78A | DC_3A_n78A DC_3C_n78A DC_7A_n78A | New PC2 Config | Telstra 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
112 | Y | PC2 FR1 EN-DC (3 bands) | DC_3C-7C_n78A | DC_3A_n78A DC_3C_n78A DC_7A_n78A DC_7C_n78A | New PC2 Config | Telstra 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
113 | Y | PC2 FR1 EN-DC (3 bands) | DC_3A-28A_n78A | DC_3A_n78A DC_28A_n78A | New PC2 Config | Telstra 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
114 | Y | PC2 FR1 EN-DC (3 bands) | DC_3C-28A_n78A | DC_3A_n78A DC_3C_n78A DC_28A_n78A | New PC2 Config | Telstra 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
115 | Y | PC2 FR1 EN-DC (3 bands) | DC_7A-28A_n78A | DC_7A_n78A DC_28A_n78A | New PC2 Config | Telstra 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
116 | Y | PC2 FR1 EN-DC (3 bands) | DC_7C-28A_n78A | DC_7A_n78A DC_7C_n78A DC_28A_n78A | New PC2 Config | Telstra 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
117 | Y | PC2 FR1 EN-DC (3 bands) | DC_3A_n5A-n78A | DC_3A_n78A | New PC2 Config | Telstra 3 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
118 | Y | PC2 FR1 EN-DC (3 bands) | DC_3C_n5A-n78A | DC_3A_n78A DC_3C_n78A | New PC2 Config | Telstra 3 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
119 | Y | PC2 FR1 EN-DC (3 bands) | DC_7A_n5A-n78A | DC_7A_n78A | New PC2 Config | Telstra 3 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
120 | Y | PC2 FR1 EN-DC (3 bands) | DC_7C_n5A-n78A | DC_7A_n78A DC_7C_n78A | New PC2 Config | Telstra 3 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
121 | Y | PC2 FR1 EN-DC (3 bands) | DC_3A_n28A-n78A | DC_3A_n78A | New PC2 Config | Telstra 5 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
122 | Y | PC2 FR1 EN-DC (3 bands) | DC_3C_n28A-n78A | DC_3A_n78A DC_3C_n78A | New PC2 Config | Telstra 5 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
123 | Y | PC2 FR1 EN-DC (3 bands) | DC_7A_n28A-n78A | DC_7A_n78A | New PC2 Config | Telstra 5 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
124 | Y | PC2 FR1 EN-DC (3 bands) | DC_7C_n28A-n78A | DC_7A_n78A DC_7C_n78A | New PC2 Config | Telstra 5 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
38.101-3: HPUE (PC2) FR1 EN-DC Inter-band (four bands)
125 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A-66A_n77A | DC_2A_n77A, DC_13A_n77A, DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
126 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A-66A_n77A | DC_2A_n77A, DC_5A_n77A, DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
127 | Y | PC2 FR1 EN-DC (4 bands) | DC_13A-66A_n2A-n77A | DC_13A_n77A, DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
128 | Y | PC2 FR1 EN-DC (4 bands) | DC_13A-66A_n66A-n77A | DC_66A_n77A DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
129 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A_n66A-n77A | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
130 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-66A_n5A-n77A | DC_66A_n77A, DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
131 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A-66A_n77A | DC_2A_n77A, DC_5A_n77A, DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
132 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A-66A_n77A | DC_2A_n77A, DC_13A_n77A, DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
133 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-48C-66A_n77A | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
134 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A_n2A-n77A | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
135 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-66A_n2A-n77A | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
136 | Y | PC2 FR1 EN-DC (4 bands) | DC_5A-66A_n2A-n77A | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
137 | Y | PC2 FR1 EN-DC (4 bands) | DC_13A-66A_n5A-n77A | DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
138 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A_n5A-n77A | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
139 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-66A_n5A-n77A | DC_66A_n77A DC_5A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
140 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A_n5A-n77A | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
141 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A_n66A-n77A | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
142 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-66A_n66A-n77A | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
143 | Y | PC2 FR1 EN-DC (4 bands) | DC_5A-66A_n66A-n77A | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
144 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A_n66A-n77A | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
145 | Y | PC2 FR1 EN-DC (4 bands) | DC_5A-66A_n5A-n77A | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
146 | Y | PC2 FR1 EN-DC (4 bands) | DC_13A-66A-66A_n2A-n77A | DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
147 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-66A-66A_n2A-n77A | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
148 | Y | PC2 FR1 EN-DC (4 bands) | DC_5A-66A-66A_n2A-n77A | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
149 | Y | PC2 FR1 EN-DC (4 bands) | DC_13A-66A-66A_n5A-n77A | DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
150 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-66A-66A_n5A-n77A | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
151 | Y | PC2 FR1 EN-DC (4 bands) | DC_5A-66A-66A_n5A-n77A | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
152 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-2A-66A_n5A-n77A | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
153 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-2A-13A_n5A-n77A | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
154 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-2A-66A_n66A-n77A | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
155 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-2A-13A_n66A-n77A | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
156 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A-48C_n77A | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
157 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A-48A_n77A | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
158 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A-48C_n77A | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
159 | Y | PC2 FR1 EN-DC (4 bands) | DC_5A-48C-66A_n77A | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
160 | Y | PC2 FR1 EN-DC (4 bands) | DC_5A-48A-66A_n77A | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
161 | Y | PC2 FR1 EN-DC (4 bands) | DC_13A-48C-66A_n77A | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
162 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
163 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
164 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A-48A_n77C | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
165 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-48A-66A_n77C | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
166 | Y | PC2 FR1 EN-DC (4 bands) | DC_13A-48A-66A_n77C | DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
167 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A-66A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
168 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A-66A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
169 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-2A-13A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
170 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-2A-5A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
171 | Y | PC2 FR1 EN-DC (4 bands) | DC_13A-66A_n2A-n77C | DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
172 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A_n2A-n77C | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
173 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-66A_n2A-n77C | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
174 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A_n2A-n77C | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
175 | Y | PC2 FR1 EN-DC (4 bands) | DC_5A-66A_n2A-n77C | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
176 | Y | PC2 FR1 EN-DC (4 bands) | DC_66A-66A_n2A-n77C | DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
177 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-66A_n5A-n77C | DC_66A_n77A DC_2A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
178 | Y | PC2 FR1 EN-DC (4 bands) | DC_5A-66A_n5A-n77C | DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
179 | Y | PC2 FR1 EN-DC (4 bands) | DC_13A-66A_n5A-n77C | DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
180 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A_n5A-n77C | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
181 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A_n5A-n77C | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
182 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-13A_n66A-n77C | DC_2A_n77A DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
183 | Y | PC2 FR1 EN-DC (4 bands) | DC_13A-66A_n66A-n77C | DC_66A_n77A DC_13A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
184 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-66A_n66A-n77C | DC_2A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
185 | Y | PC2 FR1 EN-DC (4 bands) | DC_2A-5A_n66A-n77C | DC_2A_n77A DC_5A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
186 | Y | PC2 FR1 EN-DC (4 bands) | DC_3A-7A-28A_n78A | DC_3A_n78A DC_7A_n78A DC_28A_n78A | New PC2 Config | Telstra 4 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
187 | Y | PC2 FR1 EN-DC (4 bands) | DC_3C-7A-28A_n78A | DC_3A_n78A DC_3C_n78A DC_7A_n78A DC_28A_n78A | New PC2 Config | Telstra 4 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
188 | Y | PC2 FR1 EN-DC (4 bands) | DC_3A-7C-28A_n78A | DC_3A_n78A DC_7A_n78A DC_7C_n78A DC_28A_n78A | New PC2 Config | Telstra 4 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
189 | Y | PC2 FR1 EN-DC (4 bands) | DC_3C-7C-28A_n78A | DC_3A_n78A DC_3C_n78A DC_7A_n78A DC_7C_n78A DC_28A_n78A | New PC2 Config | Telstra 4 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
190 | Y | PC2 FR1 EN-DC (4 bands) | DC_3A-7A_n5A-n78A | DC_3A_n78A DC_7A_n78A | New PC2 Config | Telstra 3 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
191 | Y | PC2 FR1 EN-DC (4 bands) | DC_3A-7C_n5A-n78A | DC_3A_n78A DC_7A_n78A DC_7C_n78A | New PC2 Config | Telstra 3 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
192 | Y | PC2 FR1 EN-DC (4 bands) | DC_3C-7A_n5A-n78A | DC_3A_n78A DC_3C_n78A DC_7A_n78A | New PC2 Config | Telstra 3 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
193 | Y | PC2 FR1 EN-DC (4 bands) | DC_3C-7C_n5A-n78A | DC_3A_n78A DC_3C_n78A DC_7A_n78A DC_7C_n78A | New PC2 Config | Telstra 3 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
194 | Y | PC2 FR1 EN-DC (4 bands) | DC_3A-7A_n28A-n78A | DC_3A_n78A DC_7A_n78A | New PC2 Config | Telstra 5 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
195 | Y | PC2 FR1 EN-DC (4 bands) | DC_3A-7C_n28A-n78A | DC_3A_n78A DC_7A_n78A DC_7C_n78A | New PC2 Config | Telstra 5 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
196 | Y | PC2 FR1 EN-DC (4 bands) | DC_3C-7A_n28A-n78A | DC_3A_n78A DC_3C_n78A DC_7A_n78A | New PC2 Config | Telstra 5 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
197 | Y | PC2 FR1 EN-DC (4 bands) | DC_3C-7C_n28A-n78A | DC_3A_n78A DC_3C_n78A DC_7A_n78A DC_7C_n78A | New PC2 Config | Telstra 5 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
38.101-3: HPUE (PC2) FR1 EN-DC Inter-band (five bands)
198 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-13A-66A_n2A-n77A | DC_2A_n77A DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
199 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-5A-66A_n2A-n77A | DC_2A_n77A DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
200 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-13A-66A_n5A-n77A | DC_2A_n77A DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
201 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-5A-66A_n5A-n77A | DC_2A_n77A DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
202 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-13A-66A_n66A-n77A | DC_2A_n77A DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
203 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-5A-66A_n66A-n77A | DC_2A_n77A DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
204 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-13A-66A-66A_n2A-n77A | DC_2A_n77A DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
205 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-5A-66A-66A_n2A-n77A | DC_2A_n77A DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
206 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-13A-66A-66A_n5A-n77A | DC_2A_n77A DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
207 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-5A-66A-66A_n5A-n77A | DC_2A_n77A DC_5A_n77A DC_66A_n77A | New PC2 Config | Verizon 1 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
208 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-2A-13A-66A_n5A-n77A | DC_2A_n77A DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
209 | Y | PC2 FR1 EN-DC (5 bands) | DC_2A-2A-13A-66A_n66A-n77A | DC_2A_n77A DC_13A_n77A DC_66A_n77A | New PC2 Config | Verizon 2 |  | Pending | TBD |  |  | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on T3: No CR shall be introduced in RAN5 until PC2 for the configuration have been completed in RAN4.
Note on U3: As agreed in R5-215709 at RAN5#92-e Proposal 2: HP requirements can’t be introduced earlier than generic and PC3 requirements are completed.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new configuration or a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on Q12: Rapporteur guideline to assign applicable sub-areas for a WP item (columns S to X) To Set applicable sub-area(s) for a WP item do: - Copy the formula/cell content from one of the other non-empty cells under the "WP item status vs Area" section (columns S to X). To Clear applicable sub-area(s) for a WP item do: - Select the cell for teh WP item for the sub-area and press <Delete>-botton (clear content of the cell).