## Cover sheet
3GPP TSG-RAN WG5 Meeting #93-e | [10 empty] | R5-217197
Electronic Meeting, 08th Nov– 19th Nov 2021
Agenda Item: | 7.4.2
Source: | China Unicom
Title: | WP UE Conformance Test Aspects - Single Radio Voice Call Continuity from 5G to 3G
Work item code: | SRVCC_NR_to_UMTS
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to provide conformance tests for the protocol aspects of the SRVCC from 5G to 3G core requirement: 1. Inter-RAT measurement test cases to support voice service continuity from 5GS to UTRAN-FDD 2. Indirect Inter-RAT handover test cases to support voice service continuity from 5GS to UTRAN-FDD 3. UE capability reporting for supporting SRVCC 4. RRM test cases to support the SRVCC from 5G to UTRAN-FDD At the RAN#89-emeeting in Sep 2020,Rel-16 RAN5 work item for UE Conformance Test Aspects- SRVCC_NR_to_UMTS [1] was approved. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+12%) | 6 (+5) | 6
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+12.2%) | 6 (+5) | 6
FR1 |  | 100% (+9.2%) | 6 (+2) | 6
FR2 |  | 100% (+16.4%) | 4 (+3) | 4
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+10%) |  |  | 100% (+10%) |  |  | 100% (+10%)
Common ICS | 38.508-2 | 100% (+10%) |  |  | 100% (+10%) |  |  | 100% (+10%)
NR RF/RRM
RRM test cases | 38.533 | 100% (+10%) | 2 (+2) | 2 | 100% (+10%) | 2 (+2) | 2
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100% (+4.4%) | 4 (+3) | 4 | 100% | 4 | 4 | 100% (+10%) | 4 (+3) | 4
Applicability Protocol test cases | 38.523-2 | 100% (+20.8%) |  |  | 100% (+17.5%) |  |  | 100% (+25%)
Test suites (TTCN) | 38.523-3 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5 References
[1] RP-201794 | New WID on UE Conformance Test Aspects – Single Radio Voice Call Continuity from 5G to 3G；China Unicom
[2] RP-210400 | Revised WID on UE Conformance Test Aspects – Single Radio Voice Call Continuity from 5G to 3G; China Unicom
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance Test Aspects - Single Radio Voice Call Continuity from 5G to 3G | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | SRVCC_NR_to_UMTS
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item Single Radio Voice Call Continuity from 5G to 3G comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core requirement (relevant core spec WIs indicated in the WID). | [12 empty] | vs Area
WP Resp: |  | Ziyuan Zhu, China Unicom |  |  | zhuzy50@chinaunicom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2 | FR1 + FR2
[14 empty] | 100% (+9.2%) | 100% (+16.4%)
[14 empty] | 14 (-1) | 12 | 0
[14 empty] | 10.3 (+2.9) | 8.3 (+2.9) | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.4,4.6 | Common test environment | Addition of Cell configurations for 5G-SRVCC from NG-RAN to UTRAN | CATT, TDIA, Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-211491 R5-216895 R5-216896 R5-216898 R5-216899 R5-217243 R5-218335 |  | 0.5 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
17 |  | 38.508-1 | 6 | Test environment for Signalling Test | Updates to UTRA signal levels in FR1 and OTA environment | ANRITSU LTD | RAN5#93 (Nov-21) | R5-217933 |  | 0.5
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | A.4.3.8 | General Capabilities | Introduciton of general capability for NR to UTRA-FDD CELL_DCH CS handover | CATT, TDIA | RAN5#90-e (Feb-21) | R5-211492 |  | 0.3 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
NR RF/RRM
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0
3 |  | 38.522 | 4 | Applicability for 5G-SRVCC | Add test case applicability statements for the new test cases introduced for 38.522. | Huawei, Hisilicon | RAN5#92 (Aug-21) | R5-214834 |  | 0.3 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
4 | Y | 38.533 | 6.3.1.0.3 6.3.1.6 F.1.1.2 F.1.3.2 | NR SA FR1 - UTRAN FDD handover with known target cell | To verify that the UE can make correct inter-RAT UTRAN FDD handover when operating in SA with PCell in FR1 TS 38.133 A.6.3.1.6 | Huawei, HiSilicon | RAN5#91-e (May-21) | R5-214009 R5-214832 R5-216900 R5-216902 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100%
5 |  | 38.533 | 6.6.5 | UTRAN Inter-RAT measurement |  |  | RAN5#93 (Nov-21) |  |  | 0
6 | Y | 38.533 | 6.6.5.1 F.1.1.2 F.1.3.2 | NR SA FR1 – UTRAN FDD event triggered reporting in non-DRX | To verify that the UE can make correct inter-RAT UTRAN FDD handover when operating in SA with PCell in FR1 TS 38.133 A.6.6.5.1 | Huawei, HiSilicon | RAN5#93 (Nov-21) | R5-214010 R5-214833 R5-218336 R5-216902 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100%
TR 38.903: MU and TT analysis for RRM test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
16 |  | 38.903 | 8 | MU and TT analysis | TT analysis for SRVCC RRM TC 6.3.1.6 and TC 6.6.5.1 | Huawei, Hisilicon | RAN5#93 (Nov-21) | R5-218337 R5-218338 |  | 2 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
RRC
7 | Y | 38.523-1 | 8.1.3.2.6 | Measurement configuration control and reporting / Inter-RAT measurements / Event B1 / NR to UTRA | TP1: [TS 38.331, clause 5.5.4.1, 5.5.4.8 and 5.5.5.1.] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B1 to measure neighbour UTRA cell is configured WHEN: Entering condition for the event B1 is not met THEN: UE does not transmit any MeasurementReport TP2: [TS 38.331, clause 5.5.4.1, 5.5.4.8 and 5.5.5.1.] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B1 to measure neighbour UTRA cell is configured WHEN: Entering condition for the event B1 is met THEN: UE transmits a MeasurementReport | Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211494 R5-213422 R5-217934 |  | 1 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
8 | Y | 38.523-1 | 8.1.3.2.7 | Measurement configuration control and reporting / Inter-RAT measurements / Event B2 / NR to UTRA | TP1: [TS 38.331, clauses 5.3.5.3, 5.5.2.1, 5.5.4.1, 5.5.4.9 and 5.5.5.1] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B2 to measure neighbour UTRA cell is configured WHEN: Entering condition 1 for event B2 is not met but Entering condition 2 is met THEN: UE does not transmit any MeasurementReport TP2: [TS 38.331, clauses 5.3.5.3, 5.5.2.1, 5.5.4.1, 5.5.4.9 and 5.5.5.1] WITH: UE is NR RRC_CONNECTED state and inter-RAT measurement event B2 to measure neighbour UTRA cell is configured WHEN: Entering condition 1 and 2 for event B2 is met THEN: UE transmits a MeasurementReport | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211495 R5-217934 |  | 1 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
15 | Y | 38.523-1 | 8.1.3.2.8 | Measurement configuration control and reporting / Inter-RAT measurements / Periodic reporting / NR to UTRA | TP1: [TS 38.331 5.3.5.3, 5.5.2.1, 5.5.4.1 and 5.5.5.1] WITH: UE is NR RRC_CONNECTED state and periodic inter-RAT measurement reporting of neighbour UTRA cells is configured WHEN: The UE receives reference signal power of UTRA cell where measurements are configured THEN: UE sends MeasurementReport message at regular intervals TP2: [TS 38.331 5.3.5.3, 5.5.2.1, 5.5.4.1 and 5.5.5.1] WITH: UE is NR RRC_CONNECTED state with periodic measurement reporting of UTRA cells ongoing WHEN: The UE receives a RRCConnectionReconfiguration message removing the measId of periodic reporting of NR cells THEN: UE stops sending MeasurementReport message for UTRA cellsl. | CATT, TDIA | RAN5#91-e (May-21) | R5-212130 R5-217934 |  | 1 | 100% | 100% |  | 100% | 100%
Multi-layer and Services
11 |  | 38.523-1 | 11.2 | 5G-SRVCC | New Sub-title |  | TBD |  |  | 0 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
12 | Y | 38.523-1 | 11.2.1 | 5G-SRVCC from NG-RAN to 3GPP UTRAN | TP1: [TS 23.216, clause 6.5.4,TS 38.331, clause 5.4.3.3] WITH: the UE is in NR RRC_CONNECTED state WHEN: UE receives a MobilityFromNRCommand message and an IMS voice call is ongoing and an UTRA Speech RAB combination is configured for an UTRA cell THEN: UE transmits a HANDOVER TO UTRAN COMPLETE message on the utra cell TP2: [TS 24.501, clause 5.5.1.2.2] WITH: the UE has performed 5G-SRVCC from NG-RAN to UTRAN WHEN: UE in 5GMM-DEREGISTERED state moves from a UTRAN to NG-RAN coverage. THEN: UE starts the Initial registration procedure on the NR cell. | CATT, TDIA | RAN5#90-e (Feb-21) | R5-211493 R5-216316 R5-216480 | Inter-system mobility voice test | 1 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
13 |  | 38.523-2 | 4.1 | Applicability for protocal test case | Adding applicability for the new test cases introduced in 38.523-1 | CATT, TDIA, Huawei, Hisilicon | RAN5#91-e (May-21) | R5-211496 R5-212549 |  | 0.1 | 100% (+20%) | 100% (+20%) |  | 100% | 100%
14 |  | 38.523-2 | 4.2 | Applicability of Protocol conformance test cases Conditions | Adding applicability of protocol conformance test cases conditions for the new test cases introduced in 38.523-1 | CATT, TDIA, Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211496 |  | 0.1 | 100% (+22.5%) | 100% (+22.5%) |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
18 |  | 38.523-3 | 5.2.1.3, 6.5, 9.1, 10.4 | Addition of NR/UTRAN Inter-RAT Test Model | <Describe task> | MCC TF160 | RAN5#92 (Aug-21) | R5-214621 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.