## Cover sheet
3GPP TSG-RAN5 Meeting #93-e | [8 empty] | R5-217315
Electronic Meeting, 8 - 19 November 2021
Agenda Item: | 7.4.2
Source: | China Telecom
Title: | WP for NR_SAR_PC2_interB_SUL_2BUL-UEConTest after RAN5#93e
Work item code: | NR_SAR_PC2_interB_SUL_2BUL-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance test cases corresponding to WID on SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 17% (+12%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 16.9% (+11.9%)
FR1 |  | 16.9% (+11.9%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 0% |  |  | 0%
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx | 30% (+30%) |  |  | 30% (+30%)
FR1 RF Rx test cases | 38.521-1 Rx | 0% |  |  | 0%
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5 References
[1] RP-211139 | New WID on UE Conformance – SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for NR_SAR_PC2_interB_SUL_2BUL-UEConTest | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_SAR_PC2_interB_SUL_2BUL-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance test cases corresponding to WID on SAR schemes for UE power class 2 (PC2) for NR inter-band Carrier Aggregation and supplemental uplink (SUL) configurations with 2 bands UL.
WP Resp: |  | Wu Jingzhou |  |  | wujingzhou@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp:
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
16.9% (+11.9%)
6
2.4
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
PC2 test for example band combinations
UL CA Config:CA_n1A-n78A
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
|  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capability | China Telecom | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
1 |  | 38.521-1 Tx | 6.2A.1 | UE maximum output power for CA | Introduce conformance requirements, test case description, test requirements for PC2 MOP test. | China Telecom | RAN5#94 (Feb-22) | R5-218373 | Test requirement is still missing. | 1 | 30% (+30%) | 30% (+30%) |  | 30%
2 |  | 38.521-1 Rx | 7.3A | Reference sensitivity for CA | Introduce conformance requirements, test case description, test requirements for the test case for reference sensitivity exceptions due to intermodulation interference. | China Telecom | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | China Telecom | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for PC2 test case. | China Telecom | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
|  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of test point analysis. |  | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  | 0%
UL CA Config: CA_n41A-n79A
NOTE: The introduction of PC2 for UL CA Config CA_n41A-n79A will be finished in NR_PC2_CA_R17_2BDL_2BUL-UEConTest WI.
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.