## Cover sheet
3GPP TSG-RAN WG5 Meeting #93-e | [6 empty] | R5-217648
Online, , 8th Nov 2021 - 19th Nov 2021
Agenda Item: | 7.4.2
Source: | NIST
Title: | WP UE Conformance Test Aspects - Enhancements for Mission Critical Services MCPTT, MCData and MCVideo for Rel-15
Work item code: | MCenhUEConTest
Release: | Rel-15
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#89 meeting, RAN5 work item UE Conformance Test Aspects - Enhancements for Mission Critical Services MCPTT, MCData and MCVideo for Rel-15 [1]. The purpose of this present document is to provide a work plan for the RAN5 work item for this. The work plan is updated after each RAN5 meeting to give the status of this work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 49% (+9%) | 31 (+10) | 70 (+1)
Completion Compensation |  | #NAME?
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (Applications) |  | 49.4% (+9.1%) | 31 (+10) | 70 (+1)
Estimation of completion per TS (area):
TS/TR overall completion
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases
LTE
Mission Critical Services
MC Common test environment | 36.579-1 | 98.4% (+1.6%) | 2 | 2
MCPTT UE test cases | 36.579-2 | 100% (+25.7%) | 23 (+8) | 23
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4 | 33.3%
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6 | 8.8% | 3 | 34
MC Data UE test cases | 36.579-7 | 27.5% (+14.6%) | 3 (+2) | 11 (+1)
5 References
[1] RP-201487 | New WID - UE Conformance Test Aspects - Enhancements for Mission Critical Services MCPTT, MCData and MCVideo for Rel-15
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Enhancements for Mission Critical Services MCPTT, MCData and MCVideo for Rel-15 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | MCenhUEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item Enhancements for Mission Critical Services MCPTT, MCData and MCVideo for Rel-15 comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Jason Kahn, NIST |  |  | jason.kahn@nist.gov | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | Applications
49.4% (+9.1%)
111
77.3 (+1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Mission Critical Services
TS 36.579-1: MC Common test environment
|  | 36.579-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 36.579-1 | 5.3 | Generic test procedures for UE MCPTT operation |  |  | RAN5#95 (May-22) |  |  | 0.1 | 50% (+50%) | 50% (+50%) |  | 50%
2 | Y | 36.579-1 | 5.3.24 | Generic Test Procedure for MCPTT functional alias status determination and subscription |  | NIST | RAN5#95 (May-22) | R5-213588 |  | 1 | 100% | 100% |  | 100%
3 | Y | 36.579-1 | 5.3.25 | Generic Test Procedure for MCPTT functional alias status change |  | NIST | RAN5#95 (May-22) | R5-213588 |  | 1 | 100% | 100% |  | 100%
4 |  | 36.579-1 | 5.5 | Default message and other information elements content |  |  | RAN5#95 (May-22) |  |  | 0.1 | 50% (+50%) | 50% (+50%) |  | 50%
5 |  | 36.579-1 | 5.5.6 | Default MCPTT media plane control messages and other information elements | Update for Rel-15 additions | NIST, Samsung, MCC TF160 | RAN5#95 (May-22) | R5-206422, R5-206108, R5-210994, R5-213265 |  | 1 | 100% | 100% |  | 100%
6 |  | 36.579-1 | 5.5.7 | Default MCPTT group management messages and other information elements | Update for Rel-15 additions | MCC TF160, UPV/EHU, Nemergent Solutions, NIST | RAN5#95 (May-22) | R5-206448, R5-206450, R5-213266, R5-217905 |  | 1 | 100% | 100% |  | 100%
7 |  | 36.579-1 | 5.5.8 | Default MCPTT configuration management messages and other information elements | Update for Rel-15 additions | NIST, UPV/EHU, Nemergent Solutions | RAN5#95 (May-22) | R5-206423, R5-206450, R5-206084 |  | 1 | 100% | 100% |  | 100%
8 | Y | 36.579-2 | 5.5.9.1 | Table 5.5.9.1-1A: MIKEY-SAKKE I_MESSAGE (CSK download sent by the SS) | Addition of default message for CSK download scenario | NIST | RAN5#95 (May-22) | R5-216282 |  | 1 | 100% | 100% |  | 100%
9 |  | 36.579-1 | 5.5.11 | Default MCVideo Transmission Control Messages and other Information Elements | Update for Rel-15 additions | NIST | RAN5#95 (May-22) | R5-213267 |  | 1 | 100% | 100% |  | 100%
TS 36.579-2: MCPTT UE test cases
|  | 36.579-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
10 |  | 36.579-2 | 5 | Configuration |  |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
11 | Y | 36.579-2 | 5.6 | Configuration / Downoad CSK | To verify the MCS Client can properly download a new CSK initiated by the SS and then properly use the new CSK See TS 24.379 clause 7.2.5 See TS 33.180 clause 9.2.1.4 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-216283, R5-216644 |  | 1 | 100% | 100% |  | 100%
12 | Y | 36.579-2 | 5.7 | Configuration / Subscription to group dynamic data / De-subscribe | To verify the MCS Client can properly subscribe to group dynamic data and then de-subscribe See TS 24.379 clause 9.2.1.6 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-215601, R5-217976 |  | 1 | 100% | 100% |  | 100%
13 | Y | 36.579-2 | 5.8 | Configuration / Functional Alias / Functional alias status determination / Activate functional alias / Deactivate functional alias | To verify the MCS Client can properly determine the status of a functional alias, activate a functional alias, and deactivate a functional alias See TS 24.379 clause 9A.2.1.2, 9A.2.1.3 | NIST | RAN5#95 (May-22) | R5-213597 |  | 1 | 100% | 100% |  | 100%
14 |  | 36.579-2 | 6 | On-network Test Scenarios |  |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
15 |  | 36.579-2 | 6.1 | Group Calls – same MCPTT system |  |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
16 |  | 36.579-2 | 6.1.1 | Pre-arranged Group Call |  |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
17 | Y | 36.579-2 | 6.1.1.19 | On-network / On-demand Pre-arranged Group Call / Active functional alias / Client Originated (CO) | To very the MCPTT Client can originate an On-demand Pre-arranged Group Call using an active functional alias TS 24.379 clause 10.1.1.2.1.1 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-213255, R5-216646 |  | 1 | 100% | 100% |  | 100%
18 | Y | 36.579-2 | 6.1.1.20 | On-network / On-demand Pre-arranged Group Call / Multi Talker | To verify that the MCPTT Client can properly process the Floor Release Multi Talker message See 24.380 clauses 6.2.4.3.7, 6.2.4.4.10, 6.2.4.5.9, 6.2.4.6.9, 6.2.4.9.14 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-213598, R5-216647 |  | 1 | 100% | 100% |  | 100%
19 |  | 36.579-2 | 6.1.2 | Chat Group Calls |  |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
20 | Y | 36.579-2 | 6.1.2.13 | On-network / Chat Group Call / Join Chat Group Session / Active functional alias / Client Originated (CO) | To verify the MCPTT Client can join a chat group sessions using an active functional alias See TS 24.379 clause 10.1.2.2.1.1 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-213599, R5-216648 |  | 1 | 100% | 100% |  | 100%
21 | Y | 36.579-2 | 6.1.2.14 | On-network / Chat Group Call / Chat Group Call Using Pre-established Session / Active functional alias / Client Originated (CO) | To verify the MCPTT Client can join a chat group sessions using a pre-established session and using an active functional alias See TS 24.379 clause 10.1.2.2.2.1 | NIST, MCC TF160 | RAN5#95 (May-22) | R5-213600, R5-216649 |  | 1 | 100% | 100% |  | 100%
22 |  | 36.579-2 | 6.1.3 | Conference Event Package | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
23 | Y | 36.579-2 | 6.1.3.1 | On-network / Conference Event Package / Subscription to Conference Event Package / Termination of subscription | To verify the MCPTT Client can subscribe to the conference state event package when a group call is ongoing and the ongoing group call is not initiated as a broadcast group call by sending a SIP SUBSCRIBE request to obtain information of the status of a group session To verify the MCPTT Client can terminate the subscription See TS 24.379 clause 10.1.3.2 | NIST | RAN5#95 (May-22) | R5-217907 |  | 1 | 100% (+70%) | 100% (+70%) |  | 100%
24 |  | 36.579-2 | 6.1.4 | Remote Change of Selected Group | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
25 | Y | 36.579-2 | 6.1.4.1 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Originated (CO) | To verify the MCPTT Client can send a group selection change request to change the selected group of a targeted MCPTT user to a specific MCPTT group See TS 24.379 clause 10.1.4.2.1 | NIST | RAN5#95 (May-22) | R5-217908 |  | 1 | 100% (+70%) | 100% (+70%) |  | 100%
26 | Y | 36.579-2 | 6.1.4.2 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Terminated (CT) | To verify the MCPTT Client can, upon receiving a "SIP MESSAGE request for group selection change request for terminating client", change to a specific MCPTT group See TS 24.379 clause 10.1.4.2.2 | NIST | RAN5#95 (May-22) | R5-217909 |  | 1 | 100% (+70%) | 100% (+70%) |  | 100%
27 |  | 36.579-2 | 6.1.5 | Remotely initiated group call | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
28 | Y | 36.579-2 | 6.1.5.1 | On-network / Remotely initiated group call / Client Originated (CO) | To verify the MCPTT Client can, upon receiving a request from the requesting MCPTT user to send a remotely initiated group call request to the remote MCPTT user for a targeted MCPTT group, generate and send a SIP MESSAGE request See TS 24.379 clause 10.1.5.2.1 | NIST | RAN5#95 (May-22) | R5-217910 |  | 1 | 100% (+70%) | 100% (+70%) |  | 100%
29 | Y | 36.579-2 | 6.1.5.2 | On-network / Remotely initiated group call / Client Terminated (CT) | To verify the MCPTT Client can, upon receiving a "SIP MESSAGE request for remotely initiated group call request for terminating client", invoke the procedures of subclause 10.1.1.2.1.1 to originate an MCPTT group call to the targeted MCPTT group and then generate and send a SIP MESSAGE request See TS 24.379 clause 10.1.5.2.2 | NIST | RAN5#95 (May-22) | R5-217911 |  | 1 | 100% (+70%) | 100% (+70%) |  | 100%
30 |  | 36.579-2 | 6.2 | Private Calls |  |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
31 | Y | 36.579-2 | 6.2.18 | On-network / Private Call / Ambient Listening Call / Remote Initiated Ambient Listening Call Using Pre-Established Session / Ambient Listening Call Release / Client Originated (CO) | To verify the MCPTT Client can initiate an ambient listening call using a pre-established session To verify the MCPTT Client can release an ambient listening call using a pre-established session See TS 24.379 clause 11.1.6.2.2.1, 11.1.6.2.2.3, 11.1.6.2.2.4 | NIST | RAN5#95 (May-22) | R5-217912 |  | 1 | 100% (+70%) | 100% (+70%) |  | 100%
32 | Y | 36.579-2 | 6.2.19 | On-network / Private Call / Ambient Listening Call / Remote Initiated Ambient Listening Call Using Pre-Established Session / Ambient Listening Call Release / Client Terminated (CT) | To verify the MCPTT Client can receive an ambient listening call using a pre-established session To verify the MCPTT Client can release an ambient listening call using a pre-established session See TS 24.379 clause 11.1.6.2.2.2, 11.1.6.2.2.5, 11.1.6.2.2.4 | NIST | RAN5#95 (May-22) | R5-217913 |  | 1 | 100% (+70%) | 100% (+70%) |  | 100%
33 | Y | 36.579-2 | 6.2.20 | On-network / First-to-answer call / On-demand session / Client Originated (CO) | To verify the MCPTT Client can initiate a first-to-answer call See TS 24.379 clause 11.1.1.2.1.1 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213590, R5-216650 |  | 1 | 100% | 100% |  | 100%
34 | Y | 36.579-2 | 6.2.21 | On-network / First-to-answer call / On-demand session / Client Terminated (CT) | To verify the MCPTT Client can terminate a first-to-answer call See TS 24.379 clause 11.1.1.2.1.2 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213591, R5-216651 |  | 1 | 100% | 100% |  | 100%
35 | Y | 36.579-2 | 6.2.22 | On-network / First-to-answer call / Pre-established session / Client Originated (CO) | To verify the MCPTT Client can initiate a first-to-answer call using a pre-established session See TS 24.379 clause 11.1.1.2.2.1 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213592, R5-216652 |  | 1 | 100% | 100% |  | 100%
36 | Y | 36.579-2 | 6.2.23 | On-network / First-to-answer call / Pre-established session / Client Terminated (CT) | To verify the MCPTT Client can terminated a first-to-answer call using a pre-established session See TS 24.379 clause 11.1.1.2.2.2 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213593, R5-217906, R5-216657 |  | 1 | 100% | 100% |  | 100%
37 | Y | 36.579-2 | 6.2.24 | On-network / Remotely initiated private call / Client Originated (CO) | To verify the MCPTT Client can originate a remotely initated private call. See TS 24.379 clause 11.1.7.2.1 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213594, R5-217977 |  | 1 | 100% | 100% |  | 100%
38 | Y | 36.579-2 | 6.2.25 | On-network / Remotely initiated private call / On-demand session / Client Terminated (CT) | To verify the MCPTT Client can originate a remotely initated private call. See TS 24.379 clause 11.1.7.2.2 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213595, R5-217978 |  | 1 | 100% | 100% |  | 100%
39 | Y | 36.579-2 | 6.2.26 | On-network / Remotely initiated private call / Pre-established session / Client Terminated (CT) | To verify the MCPTT Client can initiate an ambient listening call using a pre-established session To verify the MCPTT Client can release an ambient listening call using a pre-established session See TS 24.379 clause 11.1.6.2.2.1, 11.1.6.2.2.3, 11.1.6.2.2.4 | Samsung, MCC TF160 | RAN5#95 (May-22) | R5-213596, R5-217979 |  | 1 | 100% | 100% |  | 100%
40 |  | 36.579-2 | 6.4 | MBMS |  |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
41 | Y | 36.579-2 | 6.4.2 | On-network / MBMS / Multi Talker | To verify that the MCPTT Client can properly process the Floor Release Multi Talker message when using MBMS. See 24.380 clauses 6.2.4.3.7, 6.2.4.4.10, 6.2.4.5.9, 6.2.4.6.9, 6.2.4.9.14 | NIST | RAN5#95 (May-22) | R5-217633 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.579-4: Applicability and ICS MC test cases
|  | 36.579-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
42 |  | 36.579-4 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 37.579-x. | Samsung | RAN5#95 (May-22) | R5-211254 |  | 1 | 50% | 50% |  | 50%
43 |  | 36.579-4 | A.4 | ICS proforma tables |  |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
44 |  | 36.579-4 | A.4.1 | Implementation Types | Additions for Rel-15 for the new test cases introduced in 37.579-x. |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
45 |  | 36.579-4 | A.4.2 | Additional information | Additions for Rel-15 for the new test cases introduced in 37.579-x. | Samsung | RAN5#95 (May-22) | R5-211254 |  | 1 | 50% | 50% |  | 50%
TS 36.579-5: MC Test suite (TTCN)
|  | 36.579-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 36.579-6: MC Video UE test cases
|  | 36.579-6 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
46 |  | 36.579-6 | 6 | On-Network Test Scenarios |  |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
47 |  | 36.579-6 | 6.1 | Group Calls |  |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
48 |  | 36.579-6 | 6.1.1 | Pre-Arranged Group Call |  |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
49 | Y | 36.579-6 | 6.1.1.12 | On-network / On-demand Pre-arranged Group Call / Transmission Control State Transitions / Client Originated (CO) | To verufy that the MCVideo Client can properly handle all of the Transmission Control messages | NIST | RAN5#95 (May-22) | R5-213256 |  | 1 | 100% | 100% |  | 100%
50 | Y | 36.579-6 | 6.1.1.13 | On-network / On-demand Pre-arranged Group Call / Reception Control State Transitions / Client Terminated (CT) | To verufy that the MCVideo Client can properly handle all of the Reception Control messages | NIST | RAN5#95 (May-22) | R5-213257 |  | 1 | 100% | 100% |  | 100%
51 | Y | 36.579-6 | 6.1.2.5 | On-network / On-demand Pre-arranged Group Call / Emergency Group Call / Client Originated (CO) | To verify that a device can originate an emergency chat group call. | NIST | RAN5#95 (May-22) | R5-215599 | This test case may need to be added by maintenance rather this work plan. | 1 | 100% | 100% |  | 100%
52 |  | 36.579-6 | 6.1.3 | Subscription to Conference Events Package | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
53 | Y | 36.579-6 | 6.1.3.1 | On-network / Conference Event Package / Subscription to Conference Event Package / Termination of subscription | To verify that a MCVideo Client is able to request subscription to status updates through the Conference State Events Package. This can occur at any time while the Client is connected to a Group Call. See also TS 24.281 clause 9.2.3, 4.4.2, 9.2.1.2.1 See also TS 24.481 clause 7.2.8 See also TS 33.180 clause 7.3 |  | RAN5#95 (May-22) |  | This test case may need to be added by maintenance rather this work plan. | 1 | 0% | 0% |  | 0%
54 |  | 36.579-6 | 6.1.4 | Remote Change of an MCVideo User's selected Group | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
55 | Y | 36.579-6 | 6.1.4.1 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Originated (CO) | To verify that a request from a given user to change the selected Group of a target user executes properly See also TS 24.281 clause 9.2.4.2, 9.2.4.3 See also TS 24.481 clause 6.3 |  | RAN5#95 (May-22) |  | This test case may need to be added by maintenance rather this work plan. | 1 | 0% | 0% |  | 0%
56 | Y | 36.579-6 | 6.1.4.2 | On-network / Remote Change of Selected Group / Selected Group Change of Targeted User / Client Terminated (CT) | To verify that a MCVideo target user receiving a request to change Groups executes properly See also TS24.281 clause 9.2.4.2, 9.2.4.3 See also TS 24.481 clause 6.3 |  | RAN5#95 (May-22) |  | This test case may need to be added by maintenance rather this work plan. | 1 | 0% | 0% |  | 0%
57 |  | 36.579-6 | 6.2 | Private Calls |  |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
58 | Y | 36.579-6 | 6.2.9 | On-network / Private Call / Within a pre-established session / Automatic Commencement Mode / Without Floor Control / Client Originated (CO) | To verify functionality of Private Calls using Pre-established sessions |  | RAN5#95 (May-22) |  | This test case may need to be added by maintenance rather this work plan. | 1 | 0% | 0% |  | 0%
59 | Y | 36.579-6 | 6.2.10 | On-network / Private Call / Within a pre-established session / Automatic Commencement Mode / Without Floor Control / Client Terminated (CT) | To verify functionality of Private Calls using Pre-established sessions |  | RAN5#95 (May-22) |  | This test case may need to be added by maintenance rather this work plan. | 1 | 0% | 0% |  | 0%
60 | Y | 36.579-6 | 6.2.11 | On-network / Private Call / Within a pre-established session / Manual Commencement Mode / Client Terminated (CT) | To verify functionality of Private Calls using Pre-established sessions |  | RAN5#95 (May-22) |  | This test case may need to be added by maintenance rather this work plan. | 1 | 0% | 0% |  | 0%
61 |  | 36.579-6 | 6.3 | Emergnecy Alert | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
62 | Y | 36.579-6 | 6.3.1 | On-network / Emergency Alert / Emergency alert origination / Emergency alert cancellation / Client Originated (CO) | To verify that an Emergency Alert sent from one User reaches the rest of the indicated User Group. To verify that an Emergency Alert notification can be originated (transmitted) properly. To verify that a transmitted Emergency Alert contains the proper information To verify that an Emergency Alert can be properly authenticated See also TS 24.281 clause 4.6.3, 6.2.8.1.6, 11.2.1.1, 11.2.1.2 See also TS 24.481 clause 7.2.8 |  | RAN5#95 (May-22) |  | This test case may need to be added by maintenance rather this work plan. | 1 | 0% | 0% |  | 0%
63 | Y | 36.579-6 | 6.3.2 | On-network / Emergency Alert / Emergency alert origination / Emergency alert cancellation / Client Terminated (CT) | To verify that an Emergency Alert sent from one User reaches the rest of the indicated User Group. To verify that an Emergency Alert notification can be terminated (received) properly. To verify that a received Emergency Alert contains the proper information To verify that an Emergency Alert can be properly authenticated See also TS 24.281 clause 4.6.3, 6.2.8.1.6, 11.2.1, 11.2.1.3 See also TS 24.481 clause 7.2.8 |  | RAN5#95 (May-22) |  | This test case may need to be added by maintenance rather this work plan. | 1 | 0% | 0% |  | 0%
64 |  | 36.579-6 | 6.4 | Video Pull | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
65 | Y | 36.579-6 | 6.4.1 | FFS |  |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
66 |  | 36.579-6 | 6.5 | Video Push | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
67 | Y | 36.579-6 | 6.5.1 | FFS |  |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
68 |  | 36.579-6 | 6.6 | Capability information sharing | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
69 | Y | 36.579-6 | 6.6.1 | FFS |  |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
70 |  | 36.579-6 | 6.7 | Ambient viewing call | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
71 | Y | 36.579-6 | 6.7.1 | FFS |  |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
72 |  | 36.579-6 | 6.8 | Use of MBMS transmission | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
73 | Y | 36.579-6 | 6.8.1 | FFS |  |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
74 |  | 36.579-6 | 7 | Off-Network Test Scenarios | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
75 |  | 36.579-6 | 7.1 | Group Calls | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
76 | Y | 36.579-6 | 7.1.1 | Off-network / Group Call / Transmission Control / Upgrade to Emergency Call / Downgrade from Emergency Call / Upgrade to Imminent Peril Call / Downgrade from Imminent Peril Call / Release call / Client Originated (CO) | To verify if the MCVideo Client can initiate an off-network group call, participate in it respecting transmission control, upgrade to an emergency call, downgrade the emergency call, upgrade to an imminent peril call, downgrade the imminent peril call, and release the call. See TS 24.281 clauses 9.3.2.4.2.1, 9.3.2.4.3.1, 9.3.3.4.2, 9.3.3.4.7.1, 9.3.3.4.8.1, 9.3.3.4.8.4, 9.3.2.4.5.1, 9.3.2.4.5.4, 9.3.3.4.10, TS 24.581 clauses 7.2.3.2.2, 7.2.3.5.5, 7.2.3.3.2, 7.2.3.6.7, 7.2.3.5.4, 7.2.3.5.8, 7.2.3.5.6, 7.2.3.7.3, 7.2.3.7.5, 7.2.3.3.4, 7.2.3.4.3, 7.2.3.3.6, 7.2.3.4.2, 7.2.3.6.4, 7.2.3.6.3, 7.2.3.8.11, 7.2.3.8.3, 7.2.3.8.6, 7.2.3.5.7, 7.2.3.6.9, 7.2.3.6.6. |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
77 | Y | 36.579-6 | 7.1.2 | Off-network / Group Call / Transmission Control / Upgrade to Emergency Call / Downgrade from Emergency Call / Upgrade to Imminent Peril Call / Downgrade from Imminent Peril Call / Release call / Client Originated (CT) | To verify if the MCVIdeo Client can terminate an off-network group call, participate in it respecting transmission control, receive upgrade to an emergency call, receive downgrade the emergency call, receive upgrade to an imminent peril call, receive downgrade the imminent peril call, and release the call. See TS 24.281 clauses 9.3.2.4.3.3, 9.3.3.4.5, 9.3.3.4.7.2, 9.3.3.4.8.3, 9.3.3.4.8.6, 9.3.2.4.5.4, TS 24.581 clauses 7.2.3.2.7, 7.2.3.5.5, 7.2.3.3.2, 7.2.3.6.7, 7.2.3.5.4, 7.2.3.5.8, 7.2.3.5.6, 7.2.3.7.3, 7.2.3.7.5, 7.2.3.3.4, 7.2.3.4.3, 7.2.3.3.6, 7.2.3.4.2, 7.2.3.6.4, 7.2.3.6.3, 7.2.3.8.11, 7.2.3.8.3, 7.2.3.8.6, 7.2.3.5.7, 7.2.3.6.9, 7.2.3.6.6. |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
78 | Y | 36.579-6 | 7.1.3 | Off-network / Group Call / Leave Group Call when GROUP CALL PROBE sent / Initiate Group Call for Released Call / Receive GROUP CALL ACCOUNCEMENT for Released call / No GROUP CALL ACCOUNCEMENTfor Released Call / Receive Response to GROUP CALL PROBE | To verify if the MCPTT Client can initiate an off-network group call as specified in TS 24.281 9.3.2.4.2.1 (go from S1 state to S2 state), leave the group call as specified in TS 24.281 9.3.2.4.5.5 (go from S2 state to S7 state), initiate a group call for a released call as specified in TS 24.281 9.3.2.4.5.6 (go from S7 state to S2 state), leave the group call again and then receive GROUP CALL ACCOUNCEMENT for released call as specified in TS 24.281 9.3.2.4.5.7 (go from S7 state to S6 state), release the call (go to the S1 state) & initate a new call (go to the S2 state) & leave the group call (go to the S7 state) and return to the S1 state upon the expiration of the TFG1 timer as specified in TS 24.281 9.3.2.4.5.8, initiate a call and receive a response to the GROUP CALL PROBE as specified in TS 24.281 9.3.2.4.3.2 (go from S2 state to S3 state). Also see 24.581 7.2.3.2.3 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
79 | Y | 36.579-6 | 7.1.4 | Off-network / Group Call / MCVideo User Acknowledgement Required / With Confirm Indication / MCVideo User Reject / MCVideo User Accept / Client Terminated (CT) | To verify the MCPTT Client can reject a received off-network group call request with confirm indication, and can then accept a received off-network group call request with confirm indication. See TS 24.281 clauses 9.3.2.4.3.3, 9.3.2.4.3.7, 9.3.2.4.3.4. |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
80 | Y | 36.579-6 | 7.1.5 | Off-network / Group Call / MCVideo User Acknowledgement Required / Without Confirm Indication / MCVideo User Reject / MCVideo User Accept / Client Terminated (CT) | To verify the MCPTT Client can reject a received off-network group call request without confirm indication, and can then accept a received off-network group call request with confirm indication. See TS 24.281 clauses 9.3.2.4.3.3, 9.3.2.4.3.7, 9.3.2.4.3.4. |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
81 | Y | 36.579-6 | 7.1.6 | Off-network / Group Call / Merge Two Calls | To verify that the MCPTT Client can merge to calls while in an ongoing call, and participate in it respecting floor control. See TS 24.379 clause 9.3.2.4.6.1, TS 24.581 7.2.3.2.3 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
82 | Y | 36.579-6 | 7.1.7 | Off-network / Group Call / Emergency Call / Imminent Peril Call/ Client Originated (CO) | To verify the MCPTT Client can initiate an off-network emergency group call as specified. To verify the MCPTT Client can initiate an off-network imminent peril group call. See TS 24.379 clauses 9.3.2.4.2.1, 9.3.3.4.2, 9.3.3.4.6, 9.3.2.4.3.1. |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
83 | Y | 36.579-6 | 7.1.8 | Off-network / Group Call / Emergency Call / Imminent Peril Call/ Client Terminated (CT) | To verify the MCPTT Client can terminate an off-network emergency group call. To verify the MCPTT Client can terminate an off-network imminent peril group call. See TS 24.379 clauses 9.3.2.4.3.3, 9.3.3.4.4, 9.3.3.4.5, 9.3.3.4.6. |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
84 |  | 36.579-6 | 7.2 | Broadcast Call | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
85 | Y | 36.579-6 | 7.2.1 | Off-network / Broadcast Group Call / Broadcast Group Call Retransmitting / Broadcast Group Call Release / Client Originated (CO) | To verify that a Client can initiate an off-network Broadcast Group Call To verify that a Client can retransmit a Broadcast Group Call message To verify that a Client can release a Broadcast Group Call See also TS 24.281 clause 9.4, 17.18, 17.19 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
86 | Y | 36.579-6 | 7.2.2 | Off-network / Broadcast Group Call / User ack not required / Broadcast Group Call originator releases call / Client Terminated (CT) | To verify that a Client can terminate an off-network Broadcast Group Call when user acknowlegement is not required To verify that a terminating Client can release an off-network Broadcast Group Call See also TS 24.281 clause 9.4, 17.18, 17.19 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
87 | Y | 36.579-6 | 7.2.3 | Off-network / Broadcast Group Call / User ack required / call rejected / call accepted / terminating user releases call / Client Terminated (CT) | To verify that a Client can terminate an off-network Broadcast Group Call when user acknowlegement is requiered To verify that a terminating Client can reject an incoming Broadcast Group Call To verify that a terminating Client can accept an incoming Broadcast Group Call and then release the call See also TS 24.281 clause 9.4, 17.18, 17.19 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
88 |  | 36.579-6 | 7.3 | Private Call | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
89 | Y | 36.579-6 | 7.3.1 | Off-network / Private Call / Automatic Commencement Mode / No Response to Private Call Setup Request / Private call setup success / With Transmission Control / Upgrade to Emergency Call / Downgrade from Emergency Call / Release Call / Client Originated (CO) | To verify that off-network Private Calls function correctly. To verify that a non-response to a Private Call Setup Request is handled properly. To verify that a Private Call Setup Success response is handled correctly, and respects transmission control. To verify that an Upgrade to Emergency Call notification, and subsequent downgrade notification to normal Private Call, operate correctly. To verify that an Upgrade to Imminent Peril Call notification, and subsequent downgrade notification to normal Private Call, operate correctly. See also TS 24.281 clause 10.3.1.1, 10.3.2.4.2.4, 10.3.2.4.3, 17.1.5, 17.1.6, 17.1.7, 17.1.8, 17.1.9, 17.1.10 See also TS 33.180 clause 7.2 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
90 | Y | 36.579-6 | 7.3.2 | Off-network / Private Call / Automatic Commencement Mode / No Response to Private Call Setup Accept / Private call setup success / With Transmission Control / Upgrade to Emergency Call / Downgrade from Emergency Call / Release Call / Client Terminated (CT) | To verify that off-network Private Calls function correctly. To verify that anon-response to a Private Call Setup Request is handled properly. To verify that a Private Call Setup Success response is handled correctly, and respects transmission control. To verify that an Upgrade to Emergency Call notification, and subsequent downgrade notification to normal Private Call, operate correctly. To verify that an Upgrade to Imminent Peril Call notification, and subsequent downgrade notification to normal Private Call, operate correctly. See also TS 24.281 clause 10.3.1.1, 10.3.2.4.2.4, 10.3.2.4.3, 17.1.5, 17.1.6, 17.1.7, 17.1.8, 17.1.9, 17.1.10 See also TS 33.180 clause 7.2 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
91 | Y | 36.579-6 | 7.3.3 | Off-network / Private Call / Automatic Commencement Mode / Upgrade to Emergency Call Reject/ Downgrade from Emergency Call Failure / Client Originated (CO) | To verify that an Upgrade to Emergency Call notification rejects properly To verify that a Downgrade from Emergency Call notification rejects properly. See also TS 24.281 clause 10.3.2.4.5.8, 10.3.2.4.5.9, 17.1.5, 17.1.6, 17.1.7, 17.1.8, 17.1.9, 17.1.10 See also TS 33.180 clause 7.2 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
92 | Y | 36.579-6 | 7.3.4 | Off-network / Private Call / Manual Commencement Mode / Call Released before establishment completion / Call request Rejected / Call establishment successful / Client Originated (CO) | To verify that a Private Call in Manual Commencement Mode can be cancelled (ended) before it is fully established (i.e., user hangs up while still ringing) To verify that a call can be rejected by a User To verify that a call can be correctly established, if not ended before full establishment. See also TS 24.281 clause 10.3.2.4.4, 10.3.2.4.5, 10.3.2.4.4.2, 17.1.5, 17.1.6, 17.1.7, 17.1.8, 17.1.9, 17.1.10 See also TS 33.180 clause 7.2 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
93 | Y | 36.579-6 | 7.3.5 | Off-network / Private Call / Manual Commencement Mode Call / Released before establishment completion / User does not answer to Ringing / User Rejects call request / Call establishment successful / Client Terminated (CT) | To verify that a Private Call in Manual Commencement Mode can be cancelled (ended) before it is fully established (i.e., UE stops showing incoming call before answering) To verify that a call can be rejected by a User To verify that a call can be correctly established, if not ended before full establishment. See also TS 24.281 clause 10.3.2.4.4.1, 10.3.2.4.4.2, 17.1.5, 17.1.6, 17.1.7, 17.1.8, 17.1.9, 17.1.10 See also TS 33.180 clause 7.2 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
94 |  | 36.579-6 | 7.4 | Emergency Alerts | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
95 | Y | 36.579-6 | 7.4.1 | Off-network / Emergency Alert transmitted by MCVideo Client / TEF2 expires / TEF1 expires / Cancel Emergency Alert / Client Originated (CO) | To verify that when a client transmits an Emergency Alert off-network, its state changes from "E1: Not in Emergency State" to "E2: Emergency State" and begins procedures outlined in TS 24.281 clause 11.3.3.2 To verify that upon expiry of TEF1, the originating client will retransmit the Emergecy Alert and remain in state E2 To verify that upon cancellation of the Emergency Alert by the originating user, the client will change state from E2 to E1 See also TS 24.281 clause 4.1, 4.6.3, 11.3.1, 11.3.2, 11.3.3, 11.3.3.6, 9.3.3.4.2, 11.3.3.2, 17, annex B.3.4 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
96 | Y | 36.579-6 | 7.4.2 | Off-network / Emergency Alert transmitted by MCVideo Client / Emergency Alert retransmitted / Cancel Emergency Alert / Client Terminated (CT) | To verify that when a client receives an Emergency Alert off-network, its begins procedures outlined in TS 24.281 clause 11.3.3.3 To verify that when an originating Client cancelles an Emergency Alert, a terminating client will also terminate the state. See also TS 24.281 clause 11.3.1, 11.3.2, 11.3.3.4, 9.3.3.4.2, 11.3.3.2, 11.3.3.4, 17 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
TS 36.579-7: MC Data UE test cases
|  | 36.579-7 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
97 |  | 36.579-7 | 6 | On-Network Test Scenarios |  |  | RAN5#95 (May-22) |  |  | 0.1 | 50% (+50%) | 50% (+50%) |  | 50%
98 | Y | 36.579-7 | 6.2.13 | On-network / File Distribution (FD) / Accessing list of deferred data group communications / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-213420 |  | 1 | 100% | 100% |  | 100%
99 |  | 36.579-7 | 6.3 | Enhanced Status (ES) | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 50% (+50%) | 50% (+50%) |  | 50%
100 | Y | 36.579-7 | 6.3.1 | On-network / Enhanced Status (ES) / Client Originated (CO) |  | NIST | RAN5#95 (May-22) | R5-217914 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
101 | Y | 36.579-7 | 6.3.2 | On-network / Enhanced Status (ES) / Client Terminated (CT) |  | NIST | RAN5#95 (May-22) | R5-217915 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
102 |  | 36.579-7 | 7.1 | Short Data Service | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
103 | Y | 36.579-7 | 7.1.1 | Off-network / Short Data Service (SDS) / Group Standalone SDS / Client Originated (CO) | To verify the MCData Client can send an off-network SDS message to a group See TS 24.282 clause 9.3.2.2, 9.3.1.2, 15.1.7, and 15.2 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
104 | Y | 36.579-7 | 7.1.2 | Off-network / Short Data Service (SDS) / Group Standalone SDS / Client Terminated (CT) | To verify the MCData Client can receive an off-network SDS message to a group See TS 24.282 clause 9.3.2.4 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
105 | Y | 36.579-7 | 7.1.3 | Off-network / Short Data Service (SDS) / One-to-one Standalone SDS / Client Originated (CO) | To verify the MCData Client can send an off-network SDS message to a client See TS 24.282 clause 9.3.2.2, 9.3.1.1, 15.1.7, and 15.2 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
106 | Y | 36.579-7 | 7.1.4 | Off-network / Short Data Service (SDS) / One-to-one Standalone SDS / Client Terminated (CT) | To verify the MCData Client can receive an off-network SDS message to a client See TS 24.282 clause 9.3.2.4 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
107 | Y | 36.579-7 | 7.1.5 | Off-network / Short Data Service (SDS) / Group Standalone SDS / Client Originated (CO) | To verify the MCData Client can send an off-network SDS message to a group and retransmit when the TSF1 timer expires See TS 24.282 clause 9.3.2.2, 9.3.1.2, 15.1.7, 9.3.2.3, and 15.2 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
108 | Y | 36.579-7 | 7.1.6 | Off-network / Short Data Service (SDS) / One-to-one Standalone SDS / Client Originated (CO) | To verify the MCData Client can send an off-network SDS message to a client and retransmit when the TSF1 timer expires See TS 24.282 clause 9.3.2.2, 9.3.1.1, 15.1.7, 9.3.2.3, and 15.2 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
109 | Y | 36.579-7 | 7.1.7 | Off-network / Short Data Service (SDS) / Expiry of Timer TFS3 (delivery and read) / Client Terminated (CT) | To verify the MCData client can send the proper notofications upon expiry of Timer TFS3 (delivery and read) See TS 24.482 clause 9.3.2.6 |  | RAN5#95 (May-22) |  |  | 1 | 0% | 0% |  | 0%
110 |  | 36.579-7 | 7.2 | Enhanced Status (ES) | New sub-clause header |  | RAN5#95 (May-22) |  |  | 0 | 0% | 0% |  | 0%
111 | Y | 36.579-7 | 7.2.1 | FFS |  |  | RAN5#95 (May-22) |  |  | 1 | 0% (-30%) | 0% (-30%) |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.