## Summary
Work plan summary:
Common Implementation Conformance Statement (ICS, TS 38.508-2)
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| Common Implementation Conformance Statement (ICS, TS 38.508-2) | SA Option 2 (SA NR) | 100% | 100% | 100%
|  | NSA Option 3 (EN-DC) | 57.31% | 57.31% | 57.31%
|  | SA Option 5 | 100% | 100% | 100%
|  | NSA Option 4 (NE-DC) | 57.31% | 57.31% | 57.31%
|  | NSA Option 7 (NGEN-DC) | 57.31% | 57.31% | 57.31%

## Common ICS
WP Title: | Common Implementation Conformance Statement (ICS, TS 38.508-2) | [9 empty] | WP item applicability | [9 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | This work plan section covers tasks for all SA and NSA options for any Implementation Conformance Statement (ICS) needed for all types of 5GS conformance test cases. | [9 empty] | 5GC/NR |  | 5GC/LTE |  | EPC/LTE |  | 5GC/NR master |  | 5GC / LTE master
WP Resp: | Mohammad, Abdul Rasheed |  |  | rasheed@MOTOROLA.COM
TS Resp: | Mohammad, Abdul Rasheed |  |  | rasheed@MOTOROLA.COM | [6 empty] | SA |  |  |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 |  | Opt. 3 |  | Opt. 4 |  | Opt. 7
[10 empty] | Overall | 100% |  | 57.31% |  | 100% |  | 57.31% |  | 57.31%
[10 empty] | Phase 1 | 100% |  | 57.31% |  | 100% |  | 57.31% |  | 57.31%
Phase 2
Phase 3
Phase 4
Phase 5
Phase 6
Phase 7
Phase 8
Phase 9
Phase 10
Phase 11
[6 empty] | Overall #WP items: Phase 1 #WP items: Phase 2 #WP items: Phase 3 #WP items: Phase 4 #WP items: Phase 5 #WP items: Phase 6 #WP items: Phase 7 #WP items: Phase 8 # WP items: Phase 9 # WP items: Phase 10 # WP items: Phase 11 # WP items: |  |  |  |  | 7 7 0 0 0 0 0 0 0 0 0 0 |  | 7 7 0 0 0 0 0 0 0 0 0 0 |  | 7 7 0 0 0 0 0 0 0 0 0 0 |  | 7 7 0 0 0 0 0 0 0 0 0 0 |  | 7 7 0 0 0 0 0 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [10 empty] | Phase number (1,2 etc) and completion (%) per option
TS 38.508-2 work tasks
1 | 38.508-2 | 1 | Scope | Define scope of TS |  | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: FFS Opt 7: FFS |  |  | 0.1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100%
2 | 38.508-2 | 2 | References | Define References made in TS |  | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: FFS Opt 7: FFS |  |  | 0.1 | 76% | 1 | 100% | 1 | 60% | 1 | 100% | 1 | 60% | 1 | 60%
3 | 38.508-2 | 3 | Definitions, symbols and abbreviations | Define 'Definitions, symbols and abbreviations' |  | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: FFS Opt 7: FFS |  |  | 0.1 | 76% | 1 | 100% | 1 | 60% | 1 | 100% | 1 | 60% | 1 | 60%
4 | 38.508-2 | Annex A | ICS proforma for E-UTRA/EPC Generation User Equipment | ICS proforma |  |  |  |  | 0.1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
5 | 38.508-2 | Annex A.1 | Guidance for completing the ICS proforma | Guidance for completing the ICS proforma |  | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: FFS Opt 7: FFS |  |  | 0.1 | 94% | 1 | 100% | 1 | 90% | 1 | 100% | 1 | 90% | 1 | 90%
6 | 38.508-2 | Annex A.2 | Identification of the User Equipment | Identification of the User Equipment |  | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: FFS Opt 7: FFS |  |  | 0.1 | 94% | 1 | 100% | 1 | 90% | 1 | 100% | 1 | 90% | 1 | 90%
7 | 38.508-2 | Annex A.3 | Identification of the protocol | Identification of protocol |  | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: FFS Opt 7: FFS |  |  | 0.1 | 94% | 1 | 100% | 1 | 90% | 1 | 100% | 1 | 90% | 1 | 90%
8 | 38.508-2 | Annex A.4 | ICS proforma tables Option 2 | Define PICs |  | Opt 2: RAN5#81 (Nov-18) | R5-182069, R5-183223, R5-185161, R5-187040, R5-187777, R5-192747, R5-192746, R5-192748, R5-195331, R5-197225, R5-198963, R5-198169, R5-198964, R5-199305, R5-198349, R5-198873, R5-199039, R5-200592, R5-201123, R5-200903, R5-200923, R5-200558, R5-200969, R5-200970, R5-201162, R5-202108, R5-202709, R5-202226, R5-202228, R5-202871, R5-202591, R5-204853, R5-204902, R5-204710, R5-204904, R5-203911, R5-203912, R5-204802, R5-203914, R5-203279, R5-204332, R5-203457, R5-203463, R5-204544, R5-205053, R5-205695, R5-206635, R5-206636, R5-206637, R5-206310, R5-205941 |  | 2 | 100% | 1 | 100% | 1 |  | 1 |  | 1 |  | 1
9 | 38.508-2 | Annex A.4 | ICS proforma tables Option 3 | Define PICs |  | Opt 3: RAN5#79 (May-18) | R5-182069, R5-183223, R5-185161, R5-187040, R5-187777, R5-197225, R5-198963, R5-198169, R5-199305, R5-199306, R5-198873, R5-199039, R5-201158, R5-201062, R5-200592, R5-200598, R5-202709, R5-202228, R5-202446, R5-201923, R5-202591, R5-203632, R5-204903, R5-204759, R5-204801, R5-203635, R5-204803, R5-204804, R5-203917, R5-204805, R5-204806, R5-205053, R5-206634, R5-205695, R5-205774, R5-206635, R5-206636, R5-206637, R5-206310 |  | 2 | 100% | 1 |  | 1 |  | 1 | 100% | 1 |  | 1
10 | 38.508-2 | Annex A.4 | ICS proforma tables Option 4 | Define PICs |  | Opt 4: FFS | R5-182069, R5-185161 |  | 2 | 50% | 1 |  | 1 |  | 1 |  | 1 | 50% | 1
11 | 38.508-2 | Annex A.4 | ICS proforma tables Option 5 | Define PICs |  | Opt 5: FFS | R5-182069, R5-185161 |  | 2 | 50% | 1 |  | 1 | 50% | 1 |  | 1 |  | 1
12 | 38.508-2 | Annex A.4 | ICS proforma tables Option 7 | Define PICs |  | Opt 7: FFS | R5-182069, R5-185161 |  | 2 | 50% | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 50%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.