## Summary
Work plan summary:
5GS Positioning test cases (TS 37.571-x)
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| 5GS Positioning test cases (TS 37.571-x) | SA Option 2 (SA NR) | 100% | 100% | 100%
|  | NSA Option 3 (EN-DC) | 100% | 100% | 100%
|  | SA Option 5 | 70% | 70% | 70%
|  | NSA Option 4 (NE-DC) | 100% | 100% | 100%
|  | NSA Option 7 (NGEN-DC) | 70% | 70% | 70%
Test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of FR1+FR2 specific test cases
|  |  | Overall | Completed | Overall | Completed | Overall | Completed | Overall | Completed
| 5GS Positioning test cases (TS 37.571-x) | SA Option 2 (SA NR) | 22 | 22 | 22 | 22 | 22 | 22
|  | NSA Option 3 (EN-DC) | 22 | 22 | 22 | 22 | 22 | 22
|  | SA Option 5 | 10 | 0
|  | NSA Option 4 (NE-DC) | 10 | 10
|  | NSA Option 7 (NGEN-DC) | 10 | 0

## Positioning
WP Title: | 5GS Positioning test cases (TS 37.571-x) | [10 empty] | WP item applicability | [11 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | This work plan section covers new 5GS positioning test cases to be specified in the 37.571 series of test specifications. | [10 empty] | 5GC/NR |  |  | 5GC/LTE |  | EPC/LTE |  |  | 5GC/NR master |  | 5GC / LTE master
WP Resp: | Adrian Cardalda-Garcia, Rohde & Schwarz |  |  |  | Adrian.Cardalda-Garcia@rohde-schwarz.com
TS Resp: | - |  |  |  | - | [6 empty] | SA |  |  |  |  | NSA
WP Item ID | Is test case | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  |  | Opt. 5 |  | Opt. 3 |  |  | Opt. 4 |  | Opt. 7
[12 empty] | Target | FR1 | FR2 |  |  | Target | FR1 | FR2
[11 empty] | Overall |  | 100% |  | 70% |  |  | 100% |  | 100% |  | 70%
[13 empty] | 100% | 100% |  |  |  | 100% | 100%
[11 empty] | Phase 1 |  |  |  | 70% |  |  |  |  | 100% |  | 70%
[11 empty] | Phase 2 | [6 empty] | 100% | 100%
[11 empty] | Phase 3 |  | 100% | 100%
[11 empty] | Phase 4 |  | 100% | 100%
[11 empty] | Phase 5 |  | 100% | 100% |  |  |  | 100% | 100%
[11 empty] | Phase 6 | [6 empty] | 100% | 100%
[11 empty] | Phase7 |  | 100% | 100%
[11 empty] | Phase8 | [6 empty] | 100% | 100%
Phase9
Phase10
Phase11
[7 empty] | Overall# WP items: Phase 1# WP items: Phase 2# WP items: Phase 3# WP items: Phase 4# WP items: Phase 5# WP items: Phase 6# WP items: Phase 7# WP items: Phase 8# WP items: Phase 9# WP items: Phase 10# WP items: Phase 11# WP items: | [5 empty] | 25 0 0 2 9 13 0 1 0 0 0 0 | 25 0 0 2 9 13 0 1 0 0 0 0 | 10 10 0 0 0 0 0 0 0 0 0 0 |  |  | 25 0 2 0 0 9 13 0 1 0 0 0 | 25 0 2 0 0 9 13 0 1 0 0 0 | 10 10 0 0 0 0 0 0 0 0 0 0 |  | 10 10 0 0 0 0 0 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [11 empty] | Phase number (1,2 etc) and completion (%) per option
Test Conditions and General Settings
16 |  | 37.571-1 | 4.12 | NR test conditions | Specify the default test settings and conditions to be used for 5G - NR minimum performance test cases | Spirent Communications | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-194099 R5-198470 |  | 1 | 100% | 5 | 100% | 100% | 1 |  | 6 | 100% | 100% | 1 |  | 1
1 |  | 37.571-2 | 8 | Default Test Conditions for NR | Specify the default test settings and conditions to be used for 5G - NR protocol test cases | Spirent Communications | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#81 (Nov-18) | R5-186618 |  | 1 | 100% | 3 | 100% | 100% | 1 |  | 2 | 100% | 100% | 1 |  | 1
31 |  | 37.571-5 | All | Assistance data and test scenarios | Update references in TS 37.571-5 to add the new tests | Spirent Communications | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#81 (Nov-18) | R5-186630 |  | 1 | 100% | 3 | 100% | 100% | 1 |  | 2 | 100% | 100% | 1 |  | 1
Protocol Conformance Test Cases for NR
|  | 37.571-2 | 9 | Protocol Conformance Test Cases for NR | New clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
|  | 37.571-2 | 9.1 | NAS Protocol Procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
|  | 37.571-2 | 9.2 | LCS Procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
|  | 37.571-2 | 9.2.1 | Location Notification and Privacy Verification | New sub-clause |  |  |  |  | 0 |  | 1
|  | 37.571-2 | 9.3 | LPP Procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
|  | 37.571-2 | 9.3.1 | LPP Common Procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
6 | Y | 37.571-2 | 9.3.1.1 | LPP Position Capability Transfer | New test case to verify the conformance requirements in TS 36.355 clause 5.1.3 | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 3: RAN5#84 (Aug-19) Opt 4: FFS Opt 7: FFS | R5-187726 R5-192382 R5-195203 R5-197168 |  | 1 | 88% | 4 | 100% | 100% | 1 | 70% | 5 | 100% | 100% | 1 | 100% | 1 | 70%
7 | Y | 37.571-2 | 9.3.1.2 | Network initiated Abort | New test case to verify the conformance requirements in TS 36.355 clause 5.5.3 | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 3: RAN5#84 (Aug-19) Opt 4: FFS Opt 7: FFS | R5-187726 R5-192382 R5-195203 R5-197168 R5-204489 R5-205667 R5-206443 |  | 1 | 88% | 4 | 100% | 100% | 1 | 70% | 5 | 100% | 100% | 1 | 100% | 1 | 70%
|  | 37.571-2 | 9.3.2 | LPP Transport | New sub-clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 1 |  | 1
8 | Y | 37.571-2 | 9.3.2.1 | LPP Duplicated Message | New test case to verify the conformance requirements in TS 36.355 clause 4.3 for LPP message duplication detection | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 3: RAN5#84 (Aug-19) Opt 4: FFS Opt 7: FFS | R5-187726 R5-192382 R5-195203 R5-197168 |  | 1 | 88% | 4 | 100% | 100% | 1 | 70% | 5 | 100% | 100% | 1 | 100% | 1 | 70%
9 | Y | 37.571-2 | 9.3.2.2 | LPP Acknowledgement | New test case to verify the conformance requirements in TS 36.355 clause 4.3 for LPP Acknowledgements | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 3: RAN5#84 (Aug-19) Opt 4: FFS Opt 7: FFS | R5-187726 R5-192382 R5-195203 R5-197168 |  | 1 | 88% | 4 | 100% | 100% | 1 | 70% | 5 | 100% | 100% | 1 | 100% | 1 | 70%
10 | Y | 37.571-2 | 9.3.2.3 | LPP Retransmission | New test case to verify the conformance requirements in TS 36.355 clause 4.3 for LPP Retransmissions | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 3: RAN5#84 (Aug-19) Opt 4: FFS Opt 7: FFS | R5-187726 R5-192382 R5-195203 R5-197168 |  | 1 | 88% | 4 | 100% | 100% | 1 | 70% | 5 | 100% | 100% | 1 | 100% | 1 | 70%
|  | 37.571-2 | 9.3.3 | LPP Error Handling | New sub-clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 1 |  | 1
11 | Y | 37.571-2 | 9.3.3.1 | Void | [5 empty] | 1 |  | 7
33 | Y | 37.571-2 | 9.3.3.1A | Void | [5 empty] | 1
34 | Y | 37.571-2 | 9.3.3.1B | LPP Requested Method not Supported – UE-Assisted (Rel 14 onwards) | New test case to verify the conformance requirements in TS 36.355 clause 5.3.3 and 5.4.3 | Rohde & Schwarz | Opt 2: RAN5#87 (May-20) Opt 5: FFS Opt 3: RAN5#87 (May-20) Opt 4: FFS Opt 7: FFS | R5-187726 R5-192382 R5-195203 R5-197168 R5-204532 R5-205667 |  | 1 | 88% | 7 | 100% | 100% | 1 | 70% | 8 | 100% | 100% | 1 | 100% | 1 | 70%
|  | 37.571-2 | 9.3.4 | LPP Positioning Procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 1 |  | 1
12 | Y | 37.571-2 | 9.3.4.1 | Network Initiated Assistance Data Delivery followed by Location Information Transfer: UE-Based | New test case to verify the conformance requirements in TS 36.355 clause 5.2.4, 5.3.3 and 5.3.4 | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 3: RAN5#84 (Aug-19) Opt 4: FFS Opt 7: FFS | R5-187726 R5-192382 R5-195203 R5-197168 R5-206443 |  | 1 | 88% | 4 | 100% | 100% | 1 | 70% | 5 | 100% | 100% | 1 | 100% | 1 | 70%
13 | Y | 37.571-2 | 9.3.4.2 | Network Initiated Assistance Data Delivery followed by Location Information Transfer: UE-Assisted | New test case to verify the conformance requirements in TS 36.355 clause 5.2.4, 5.3.3 and 5.3.4 | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 3: RAN5#84 (Aug-19) Opt 4: FFS Opt 7: FFS | R5-187726 R5-192382 R5-195203 R5-197168 R5-204489 R5-205667 R5-206443 |  | 1 | 88% | 4 | 100% | 100% | 1 | 70% | 5 | 100% | 100% | 1 | 100% | 1 | 70%
14 | Y | 37.571-2 | 9.3.4.3 | Network Initiated Position Measurement without Assistance Data: UE-Based | New test case to verify the conformance requirements in TS 36.355 clause 5.2.3, 5.2.4, 5.3.3 and 5.3.4 | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 3: RAN5#84 (Aug-19) Opt 4: FFS Opt 7: FFS | R5-187726 R5-192382 R5-195203 R5-197168 R5-206443 |  | 1 | 88% | 4 | 100% | 100% | 1 | 70% | 5 | 100% | 100% | 1 | 100% | 1 | 70%
15 | Y | 37.571-2 | 9.3.4.4 | Network Initiated Position Measurement without Assistance Data: UE-Assisted | New test case to verify the conformance requirements in TS 36.355 clause 5.2.3, 5.2.4, 5.3.3 and 5.3.4 | Rohde & Schwarz | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 3: RAN5#84 (Aug-19) Opt 4: FFS Opt 7: FFS | R5-187726 R5-192382 R5-195203 R5-197168 R5-204489 R5-205667 R5-206443 |  | 1 | 88% | 4 | 100% | 100% | 1 | 70% | 5 | 100% | 100% | 1 | 100% | 1 | 70%
|  | 37.571-2 | 9.4 | RRC Protocol Procedures | New sub-clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
|  | 37.571-2 | 9.4.x | FFS | FFS |  |  |  |  | 0 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
Minimum Performance Test Cases for NR
23 | Y | 37.571-1 | 11.1B | MBS Measurement Reporting Delay |  | NextNav | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-195009 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
24 | Y | 37.571-1 | 11.2B | MBS Sensitivity Measurement Accuracy |  | NextNav | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-195009 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
25 | Y | 37.571-1 | 11.3B | MBS Nominal Measurement Accuracy |  | NextNav | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-195009 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
26 | Y | 37.571-1 | 11.4B | MBS Dynamic Range Measurement Accuracy |  | NextNav | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-195009 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
27 | Y | 37.571-1 | 11.5B | MBS Measurement Accuracy in Multipath |  | NextNav | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-195009 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
|  | 37.571-1 | 13 | NR A-GNSS minimum performance requirements | New sub-clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
|  | 37.571-1 | 13.1 | General | New sub-clause |  |  |  |  | 0 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
17 | Y | 37.571-1 | 13.2.1 | Sensitivity Coarse time assistance |  | Spirent Communications | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-194099 R5-198470 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
18 | Y | 37.571-1 | 13.2.2 | Sensitivity Fine time assistance |  | Spirent Communications | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-194099 R5-198470 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
19 | Y | 37.571-1 | 13.3 | Nominal Accuracy |  | Spirent Communications | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-194099 R5-198470 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
20 | Y | 37.571-1 | 13.4 | Dynamic Range |  | Spirent Communications | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-194099 R5-198470 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
21 | Y | 37.571-1 | 13.5 | Multi-Path scenario |  | Spirent Communications | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-194099 R5-198470 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
22 | Y | 37.571-1 | 13.6 | Moving scenario and periodic update (Rel-9 to Rel-13) |  | Spirent Communications | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-194099 R5-198470 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
32 | Y | 37.571-1 | 13.6 | Moving scenario and periodic update (Rel-4 onwards) |  | Spirent Communications | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) | R5-194099 R5-198470 |  | 1 | 100% | 5 | 100% | 100% |  |  | 6 | 100% | 100%
<area#4>
|  | <37.571-x> | <Clause> | <Title> | [5 empty] | 1 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
<area#5>
|  | <37.571-x> | <Clause> | <Title> | [5 empty] | 1 |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.