## Protocol EPC Option 3
WP Title: | EPC Protocol Test Cases for Option 3 (TS 38.523-1) | [9 empty] | WP item applicability | [5 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | This work plan section covers the EPC protocol test cases for NSA option 3. | [9 empty] | 5GC/NR | 5GC/LTE | EPC/LTE |  | 5GC/NR master | 5GC / LTE master
WP Resp: | Calle Hagenfeldt, Ericsson |  |  | calle.hagenfeldt@ericsson.com
TS Resp: | Stoyan Baev, Samsung |  |  | stoyan.baev@partner.samsung.com | [6 empty] | SA |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 | Opt. 5 | Opt. 3 |  | Opt. 4 | Opt. 7
[10 empty] | Overall |  |  | 100%
[10 empty] | Phase 1 |  |  | 100%
Phase 2
Phase 3
[6 empty] | Overall #WP items: Phase 1 #WP items: Phase 2 #WP items: Phase 3 #WP items: |  |  |  |  | 0 0 0 0 | 0 0 0 0 | 8 8 0 0 |  | 0 0 0 0 | 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [10 empty] | Phase number (1,2 etc) and completion (%) per option
NAS - Mobility Management
16 | 36.508 |  | Integrity protection | **** TP1: [TS 33.401:7.2.4.4, E.3.4.3; TS 24.301:FFS] WITH: successful completion of EPS authentication and key agreement (AKA) procedure WHEN: UE receives an integrity protected SECURITY MODE COMMAND message, to start integrity protection using algorithm NR SNOW3G THEN: UE sends SECURITY MODE COMPLETE, integrity protected with SNOW3G and starts applying the NAS Integrity protection in both UL and DL **** TP2: [TS 24.301:4.4.4.2] WITH: Integrity protection successful started by executing Security Mode Procedure WHEN: UE receives an IDENTITY REQUEST message without integrity protected THEN: UE does not transmit an IDENTITY RESPONSE message **** TP3: [TS 33.401:7.2.4.4, E.3.4.3; TS 24.301:FFS] WITH: successful completion of EPS authentication and key agreement (AKA) procedure WHEN: UE receives an integrity protected SECURITY MODE COMMAND message, to start integrity protection using algorithm NR AES THEN: UE sends SECURITY MODE COMPLETE, integrity protected with AES and starts applying the NAS Integrity protection in both UL and DL **** TP4: [TS 24.301:4.4.4.2] WITH: Integrity protection successful started by executing Security Mode Procedure WHEN: UE receives an IDENTITY REQUEST message without integrity protected THEN: UE does not transmit an IDENTITY RESPONSE message **** TP5: [TS 33.401:7.2.4.4, E.3.4.3] WITH: successful completion of EPS authentication and key agreement (AKA) procedure WHEN: UE receives an integrity protected SECURITY MODE COMMAND message, to start integrity protection using algorithm NR ZUC THEN: UE sends SECURITY MODE COMPLETE, integrity protected with ZUC and starts applying the NAS Integrity protection in both UL and DL **** TP6: [TS 24.301:4.4.4.2] WITH: Integrity protection successful started by executing Security Mode Procedure WHEN: UE receives an IDENTITY REQUEST message without integrity protected THEN: UE does not transmit an IDENTITY RESPONSE message | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-182074 | These Test Purposes are implicitly tested by the default message definitions. | 1 | 100% | 1 | 1 | 1 | 100% | 1 | 1
17 | 36.508 |  | Ciphering and deciphering | **** TP1: [TS 33.401:7.2.4.4, E.3.4.3] WITH: successful completion of EPS authentication and key agreement (AKA) procedure WHEN: UE receives a SECURITY MODE COMMAND instructing to start ciphering using algorithm NR SNOW3G THEN: UE sends a SECURITY MODE COMPLETE message ciphered with NR SNOW3G and starts applying the NAS ciphering in both UL and DL **** TP2: [TS 33.401:7.2.4.4, E.3.4.3] WITH: successful completion of EPS authentication and key agreement (AKA) procedure WHEN: UE receives a SECURITY MODE COMMAND instructing to start ciphering using algorithm NR AES THEN: UE sends a SECURITY MODE COMPLETE message ciphered with NR AES and starts applying the NAS ciphering in both UL and DL **** TP3: [TS 33.401:7.2.4.4, E.3.4.3] WITH: successful completion of EPS authentication and key agreement (AKA) procedure WHEN: UE receives a SECURITY MODE COMMAND instructing to start ciphering using algorithm NR ZUC THEN: UE sends a SECURITY MODE COMPLETE message ciphered with NR ZUC and starts applying the NAS ciphering in both UL and DL | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-182074 | These Test Purposes are implicitly tested by the default message definitions. | 1 | 100% | 1 | 1 | 1 | 100% | 1 | 1
3 | 36.508 |  | DCNR bit in ATTACH and TAU | **** TP1: [TS 24.301:5.5.3.2.2, 9.9.3.34] WITH: the UE supporting dual connectivity with New Radio (NR) AND the UE in state EMM-REGISTERED and EMM-IDLE mode WHEN: UE detects entering a new tracking area not included in the TAI list THEN: UE sends TRACKING AREA UPDATE REQUEST message with the DCNR bit in the UE network capability IE set to "dual connectivity with NR supported" **** TP2: [TS 24.301:5.5.3.2.2, 9.9.3.34] WITH: the UE supporting dual connectivity with New Radio (NR) AND the UE in state EMM-REGISTERED and EMM-IDLE mode WHEN: the periodic tracking area updating timer T3412 expires THEN: UE sends TRACKING AREA UPDATE REQUEST message with the DCNR bit in the UE network capability IE set to "dual connectivity with NR supported" **** TP3: [TS 24.301:5.5.1.2.2, 9.9.3.34] Editor's note: <Add TP note here if needed> WITH: the UE supporting dual connectivity with New Radio (NR) AND the UE is switched-off with a valid USIM inserted WHEN: UE is powered on THEN: the UE transmits an ATTACH REQUEST message with the DCNR bit in the UE network capability IE set to "dual connectivity with NR supported" | Samsung | Opt 3: RAN5#79 (May-18) | R5-182074 R5-181991 | Verifying that the UE sends the DCNR bit in ATTACH and TAU procedures. This is implicitly tested by the default message definitions. | 1 | 100% | 1 | 1 | 1 | 100% | 1 | 1
NAS - Session Management
| 38.523-1 | 10.2 | EN-DC session management | New Clause |  |  |  |  | 0 |  | 1 | 1 | 1 |  | 1 | 1
| 38.523-1 | 10.2.1 | Network initiated procedures | New Clause |  |  |  |  | 0 |  | 1 | 1 | 1 |  | 1 | 1
11 | 38.523-1 | 10.2.1.1 | Default EPS bearer context activation | **** TP1: [TS 24.301:6.4.1.3, 8.3.6.1, 9.9.4.2a, 9.9.4.3a] WITH: UE has sent a PDN CONNECTIVITY REQUEST message WHEN: UE receives an RRCConnectionReconfiguration message including an ACTIVATE DEFAULT EPS BEARER CONTEXT REQUEST message with IE Procedure transaction identity matching the PDN CONNECTIVITY REQUEST message and including the Extended QoS and Extended APN-AMBR IEs THEN: UE transmits an ACTIVATE DEFAULT EPS BEARER CONTEXT ACCEPT message and enters BEARER CONTEXT ACTIVE state | Qualcomm Y | Opt 3: RAN5#79 (May-18) | R5-183263 R5-182897 |  | 1 | 100% | 1 | 1 | 1 | 100% | 1 | 1
12 | 38.523-1 | 10.2.1.2 | Dedicated EPS bearer context activation | **** TP1: [TS 24.301:8.3.3.1, 9.9.4.3a] WITH: UE is in EMM-REGISTERED state and a PDN address for an active default EPS bearer was received in an ACTIVATE DEFAULT EPS BEARER CONTEXT REQUEST WHEN: UE receives an ACTIVATE DEDICATED EPS BEARER CONTEXT REQUEST message, including the Extended QoS IE, linked to the existing default EPS bearer THEN: UE transmits an ACTIVATE DEDICATED EPS BEARER CONTEXT ACCEPT | Tech Mahindra | Opt 3: RAN5#79 (May-18) | R5-181988 R5-181838 R5-182897 R5-185155 |  | 1 | 100% | 1 | 1 | 1 | 100% | 1 | 1
13 | 38.523-1 |  | EPS bearer context modification / Success | **** TP1: [TS 24.301:8.3.18.1, 9.9.4.2a, 9.9.4.3a] WITH: the UE is in BEARER CONTEXT ACTIVE STATE and in EMM-CONNECTED mode WHEN: the UE receives a MODIFY EPS BEARER CONTEXT REQUEST message including the Extended QoS and Extended APN-AMBR IEs THEN: UE transmits a MODIFY EPS BEARER CONTEXT ACCEPT | Tech Mahindra | Opt 3: RAN5#79 (May-18) |  | Merged into TC 10.2.1.2 | 1 | 100% | 1 | 1 | 1 | 100% | 1 | 1
| 38.523-1 | 10.2.2 | UE initiated procedures | New Heading |  |  |  |  | 0 |  | 1 | 1 | 1 |  | 1 | 1
14 | 38.523-1 | 10.2.2.1 | EPS bearer resource allocation / modification | **** TP1: [TS 24.301:6.5.3.2, 8.3.8, 9.9.4.3a] WITH: UE in PROCEDURE TRANSACTION INACTIVE state and in EMM-IDLE mode WHEN: UE is requested to allocate bearer resource using Extended EPS QoS THEN: UE sends a BEARER RESOURCE ALLOCATION REQUEST including the Extended EPS QoS IE **** TP2: [TS 24.301:6.5.3.3] WITH: UE has sent the BEARER RESOURCE ALLOCATION REQUEST message WHEN: UE receives an ACTIVATE DEDICATED EPS BEARER CONTEXT REQUEST message with the procedure transaction identity (PTI) indicated in the BEARER RESOURCE ALLOCATION REQUEST message THEN: UE sends an ACTIVATE DEDICATED EPS BEARER CONTEXT ACCEPT message | Ericsson 1 | Opt 3: RAN5#79 (May-18) | R5-181992 R5-181838 R5-183265 R5-183236 R5-185167 |  | 1 | 100% | 1 | 1 | 1 | 100% | 1 | 1
15 | 38.523-1 |  | EPS bearer resource modification / New EPS bearer context | **** TP1: [TS 24.301:6.5.4.2, 8.3.10, 9.9.4.3a] WITH: UE in PROCEDURE TRANSACTION INACTIVE state and in EMM-CONNECTED mode WHEN: UE is requested to modify of bearer resource corresponding to the dedicated bearer using Extended EPS QoS THEN: UE sends a BEARER RESOURCE MODIFICATION REQUEST message including the Extended EPS QoS IE **** TP2: [TS 24.301:6.4.2.3, 6.5.4.3] WITH: UE having sent the BEARER RESOURCE MODIFICATION REQUEST message WHEN: UE receives an ACTIVATE DEDICATED EPS BEARER CONTEXT REQUEST message with the procedure transaction identity (PTI) indicated in the BEARER RESOURCE MODIFICATION REQUEST message THEN: UE sends an ACTIVATE DEDICATED EPS BEARER CONTEXT ACCEPT message | Ericsson 1 | Opt 3: RAN5#79 (May-18) |  | Merged into TC 10.2.2.1 | 1 | 100% | 1 | 1 | 1 | 100% | 1 | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.