## TR 38.905
WP Title: | TR 38.905 - NR; Derivation of test points for radio transmission and reception conformance test cases | [9 empty] | WP item applicability
RAN-CN interface options dependency
WP Scope: | This work plan section covers the content of TR 36.906 with the exception of: - Content related to specific test cases (this is handled as part of the work plan item for the test case in the TS 38.521-x and -y section of the work plan) | [9 empty] | 5GC/NR |  | 5GC/LTE | EPC/LTE |  | 5GC/NR master |  | 5GC / LTE master
WP Resp: | Mats Johansson |  |  | mats.e.johansson@ericsson.com
TS Resp: | Mats Johansson |  |  | mats.e.johansson@ericsson.com | [6 empty] | SA |  |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 | Opt. 3 |  | Opt. 4 |  | Opt. 7
[10 empty] | Overall | 100% |  |  | 100% |  | 100% |  | 100%
[10 empty] | Phase 1 | 100% |  |  |  |  | 100% |  | 100%
[10 empty] | Phase 1.5 |  |  |  | 100%
[10 empty] | Phase 2 |  |  |  | 100%
[10 empty] | Phase 3 | 100%
[10 empty] | Phase 4 |  |  |  | 100%
Phase 5
Phase 6
[6 empty] | Overall #WP items: Phase 1 #WP items: Phase 2 #WP items: Phase 3 #WP items: Phase 4 #WP items: Phase 5 #WP items: Phase 6 #WP items: |  |  |  |  | 5 4 0 1 0 0 0 |  | 0 0 0 0 0 0 0 | 5 0 1 0 1 0 0 |  | 5 5 0 0 0 0 0 |  | 5 5 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [10 empty] | Phase number (1,2 etc) and completion (%) per option
Test coverage analysis (Clause 4)
1 | TR 38.905 | 1 to 4 | Test point analysis for FR1 | Add headings and general text to clauses 1 to 4 | Ericsson | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#84 (Aug-19) Opt 7: RAN5#84 (Aug-19) | R5-181954 |  | 1 | 100% | 1 | 100% | 1 | 2 | 100% | 1 | 100% | 1 | 100%
2 | TR 38.905 | 4.1 | Test point analysis for FR1 | Add header, general text and table struktur to list test point analysis for FR1 TX and RX test cases. | Ericsson | <Autofilled> | R5-181954 R5-184303 R5-185307 R5-185309 R5-185311 R5-185314 R5-185316 R5-185412 R5-187806 R5-187907 R5-187808 R5-187809 R5-187396 R5-187489 R5-186454 R5-187035 R5-187584 R5-187593 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 | 100% | 1 | 100%
3 | TR 38.905 | 4.2 | Test point analysis for FR2 | Add header, general text and table struktur to list test point analysis for FR2 TX and RX test cases. | Ericsson | <Autofilled> | R5-181954 R5-184923 R5-184961 R5-185491 R5-184958 R5-187836 R5-187483 R5-187582 R5-187583 R5-187587 R5-187589 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 | 100% | 1 | 100%
4 | TR 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Add header, general text and table struktur to list test point analysis for NR CA and EN-DC, TX and RX test cases. | Ericsson | <Autofilled> | R5-181954 [R5-185430] R5-187817 R5-187818 [R5-187400] R5-186455 R5-186609 R5-186610 R5-186611 R5-186674 R5-186791 R5-186792 |  | 1 | 100% | 1 | 100% | 1 | 1.5 | 100% | 1 | 100% | 1 | 100%
5 | TR 38.905 | Annex A | Derivation documents | Specify rules for naming of zipped background documents | Ericsson | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#84 (Aug-19) Opt 7: RAN5#84 (Aug-19) | R5-181954 R5-194168 |  | 1 | 100% | 3 | 100% | 1 | 4 | 100% | 1 | 100% | 1 | 100%
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.