## UE Test Functions
WP Title: | 5GS UE test functions (TS 38.509 and TS 36.509) | [9 empty] | WP item applicability | [9 empty] | End of work plan columns. Note! Do not remove this column. | Columns U to X is only used for WP rapporteur guide and notes and will be removed when the work plan is published
[11 empty] | RAN-CN interface options dependency | [10 empty] | WP rapporteur's guide: All WP rows that represent WP work tasks must have a WP item ID number assigned. Other WP rows such as header rows used to group WP Items should NOT have any WP item ID numbers assigned (leave empty). How to assign unique WP item ID numbers (column A): In the WP item ID column double-click in the cell for the WP item row to assign the next free WP item ID number. Note! If You add numbers manually make sure each WP item row have an unique WP item ID number.
WP Scope: | This work plan section covers UE test functions for all SA and NSA options. | [9 empty] | 5GC/NR |  | 5GC/LTE |  | EPC/LTE |  | 5GC/NR master |  | 5GC / LTE master
WP Resp: | Ramakrishnan Thiruvathirai, Rohde & Schwarz |  |  | Ramakrishnan.Thiruvathirai@rohde-schwarz.com
TS Resp: | Ramakrishnan Thiruvathirai, Rohde & Schwarz |  |  | Ramakrishnan.Thiruvathirai@rohde-schwarz.com | [6 empty] | SA |  |  |  | NSA
WP Item ID | TS | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | WP item compl. | Opt. 2 |  | Opt. 5 |  | Opt. 3 |  | Opt. 4 |  | Opt. 7 |  |  | WP rapporteur internal notes |  | Company <-> Contact email address(es)
[22 empty] | <Internal note column#1> | <Internal note column#2> | Company | E-mail address(es)
[10 empty] | Overall | 100% |  | 100% |  | 100% |  | 85.71% |  | 100%
[10 empty] | Phase 1 | 100% |  | 100% |  | 100% |  | 100%
[10 empty] | Phase 2 |  |  | 100% |  | 100% |  | 0% |  | 100%
[10 empty] | Phase 3 | 100%
[10 empty] | Phase 4 | 100% |  |  |  | 100%
Phase 5
Phase 6
Phase 7
Phase 8
Phase 9
Phase 10
Phase 11
Phase 12
Phase 13
Phase 14
Phase 15
[6 empty] | Overall# WP items: Phase 1 # WP items: Phase 2# WP items: Phase 3# WP items: Phase 4# WP items: Phase 5# WP items: Phase 6# WP items: Phase 7# WP items: Phase 8# WP items: Phase 9# WP items: Phase 10# WP items: Phase 11# WP items: Phase 12# WP items: Phase 13# WP items: Phase 14# WP items: Phase 15# WP items: |  |  |  |  | 7 5 0 1 1 0 0 0 0 0 0 0 0 0 0 0 |  | 5 3 2 0 0 0 0 0 0 0 0 0 0 0 0 0 |  | 6 3 2 0 1 0 0 0 0 0 0 0 0 0 0 0 |  | 7 6 1 0 0 0 0 0 0 0 0 0 0 0 0 0 |  | 7 0 7 0 0 0 0 0 0 0 0 0 0 0 0 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
TS 38.509 work tasks
1 | 38.509 | General | General sections | Specify content for General sections providing auxiliary information in regard to the diferent test functions specified. |  | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#94 (Feb-22) Opt 7: FFS | R5-174100, R5-182070, R5-182423, R5-187113, R5-190664, R5-191196 | Remains for NE-DC: Block diagram for NE-DC and UE test loop mode A and B need to be added in clause 5.3.4.1 and 5.3.4.2. | 1 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 2 | 0% | 2 | 100%
2 | 38.509 | 5.3.4.1, 6.3 | Specific Test Mode functionality: Test Loop Mode A | Specific Test Mode functionality: Test Loop Mode A (loopback of PDCP SDUs for bi-directional NR data radio bearers) | Samsung | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183081, R5-187113 |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 2 | 100%
3 | 38.509 | 5.3.4.2, 6.3 | Specific Test Mode functionality: Test Loop Mode B | Specific Test Mode functionality: Test Loop Mode B (loopback of PDCP SDUs for bi-directional EPS/5GC bearers) | Samsung | Opt 2: RAN5#81 (Nov-18) Opt 5: FFS Opt 3: RAN5#79 (May-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-183081, R5-187684 | HAndling of SDAP was originally considered as a separate Test Mode but at RAN5#81 was added as part of Loop Mode B | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 2 | 100%
4 | 38.509 | 5.4, 6.4 | Specific Test Mode functionality: UE beamlock function for NR FR2 testing | Specific Test Mode functionality: UE beamlock function | Keysight | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-176997, R5-182354, R5-183701, R5-185523, R5-186863, R5-199307 | RF part for Option 3 completed. Usage for SIG under investigation. For Other Options RF and SIG relevant input is expected | 1 | 100% | 1 | 100% | 1 |  | 2 | 100% | 1 | 100% | 2 | 100%
5 | 38.509 | 5.5, 6.5 | Specific Test Mode functionality: UE SS-RSRPB per receiver branch reporting function forNR FR2 testing | Specific Test Mode functionality: UE SS-RSRPB per receiver branch reporting | Qualcomm | Opt 2: RAN5#81 (Nov-18) Opt 3: RAN5#81 (Nov-18) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-182037, R5-182354, R5-187891, R5-197306 |  | 1 | 100% | 1 | 100% | 1 |  | 2 | 100% | 1 | 100% | 2 | 100%
11 | 38.509 | 5.3.4 | SDP test loop for 5GS and NG-RAN | Specific Test Mode functionality for SDP test loop for 5GS and NG-RAN | Motorola Mobility, Ericsson |  |  | Not pursued. CR with first ideas was submitted to RAN5#80 (R5-185058) but withdrawn because more considerations were needed. At RAN5#81 it was agreed to be added as part of Test Loop Mode B (R5-187684) | 0 |  | 1 |  | 1 |  | 2 |  | 1 |  | 1
12 | 38.509 | 5 | Specific Test Mode functionality: ETC Reset command | Specific Test Mode functionality: Rest UE Possitioning Stored Information | Rohde & Schwarz | Opt 2: RAN5#83 (May-19) Opt 5: FFS Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-191128 | For Option 3 (EN-DC) reference to 36.509 needs to be added as the command will be used over the LTE interface. | 1 | 100% | 3 | 100% | 2 | 100% | 4 | 100% | 1 | 100% | 2 | 100%
13 | 38.509 | 5 | Specific Test Mode functionality: Update UE Location Information | Specific Test Mode functionality: Update UE Location Information and UTC time reset | Rohde & Schwarz |  |  | Not used for minimum performance testing; used for signalling. Not pursued. Present assumption: No need for 5GC - legacy functions in 36.508 | 0 |  | 2 |  | 1 |  | 3 |  | 1 |  | 1
15 | 38.509 | 5.7, 6.7 | NSSAI delete test function | Specific Test Mode functionality: The SS use the NSSAI delete test procedure to delete NSSAI information in the UE such as Default configured NSSAI, Configured NSSAI or Allowed NSSAI information | Qualcomm | Opt 2: RAN5#84 (Aug-19) Opt 5: FFS Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-195334, R5-197184 |  | 1 | 100% | 4 | 100% | 2 | 100% | 1 |  | 1 | 100% | 2 | 100%
TS 36.509 work tasks
10 | 36.509 | General | General sections | Specify content for General sections providing auxiliary information in regard to the diferent test functions specified | Samsung |  | R5-176914 | R5-176914 Withdrawn as RAN5 agreed to specify all 5GS UE test functions in 38.509. | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row. | End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.
Note on AA6: The company and email addresses are used by the WP support tool when creating WP status update request emails. The companies in the company column should be the assigned companies in column F of the WP.
Note on AB7: Use email address format as used in the address fields of emails. If needed multipe email addresses may be included separated by semicolon (;).

## Deliverables
Deliverables:
Deliverables |  | Standalone (SA) Targets |  | Non-Standalone (NSA) Targets
Target ID | Phase | SA Option 2 | SA Option 5 | NSA Option 3 | NSA Option 4 | NSA Option 7
1 | Phase 1 | RAN5#81 (Nov-18) | FFS | RAN5#79 (May-18) | RAN5#93 (Nov-21) | FFS
1.5 | Phase 1 | - | - | RAN5#80 (Aug-18) | - | -
2 | Phase 2 | RAN5#82 (Feb-19) | FFS | RAN5#81 (Nov-18) | RAN5#94 (Feb-22) | FFS
3 | Phase 3 | RAN5#83 (May-19) | FFS | RAN5#82 (Feb-19) | FFS | FFS
4 | Phase 4 | RAN5#84 (Aug-19) | FFS | RAN5#83 (May-19) | FFS | FFS
5 | Phase 5 | RAN5#85 (Nov-19) | FFS | RAN5#84 (Aug-19) | FFS | FFS
6 | Phase 6 | RAN5#86 (Feb-20) | FFS | RAN5#85 (Nov-19) | FFS | FFS
7 | Phase 7 | RAN5#87 (May-20) | FFS | RAN5#86 (Feb-20) | FFS | FFS
8 | Phase 8 | RAN5#88 (Aug-20) | FFS | RAN5#87 (May-20) | FFS | FFS
9 | Phase 9 | RAN5#89 (Nov-20) | FFS | RAN5#88 (Aug-20) | FFS | FFS
10 | Phase 10 | RAN5#90 (Feb-21) | FFS | RAN5#89 (Nov-20) | FFS | FFS
11 | Phase 11 | RAN5#91 (May-21) | FFS | RAN5#90 (Feb-21) | FFS | FFS
12 | Phase 12 | RAN5#92 (Aug-21) | FFS | RAN5#91 (May-21) | FFS | FFS
13 | Phase 13 | RAN5#93 (Nov-21) | FFS | RAN5#92 (Aug-21) | FFS | FFS
14 | Phase 14 | RAN5#94 (Feb-22) | FFS | RAN5#93 (Nov-21) | FFS | FFS
15 | Phase 15 | FFS | FFS | RAN5#94 (Feb-22) | FFS | FFS

## Status to overall report
|  | SA | [16 empty] | NSA | [19 empty] | SA | [16 empty] | NSA
| Option: | Option 2 | [14 empty] | Option 5 |  | Option 3 | [15 empty] | Option 4 |  | Option 7 |  | Option 2 | [14 empty] | Option 5 |  | Option 3 | [15 empty] | Option 4 |  | Option 7
| Phase: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 1 | 2 | 1 | 1.5 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 1 | 2 | 1 | 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 1 | 2 | 1 | 1.5 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 1 | 2 | 1 | 2
| Target date: | Option 2 1: RAN5#81 (Nov-18); Option 2 2: RAN5#82 (Feb-19); Option 2 3: RAN5#83 (May-19); Option 2 4: RAN5#84 (Aug-19); Option 2 5: RAN5#85 (Nov-19); Option 2 6: RAN5#86 (Feb-20); Option 2 7: RAN5#87 (May-20); Option 2 8: RAN5#88 (Aug-20); Option 2 9: RAN5#89 (Nov-20); Option 2 10: RAN5#90 (Feb-21); Option 2 11: RAN5#91 (May-21); Option 2 12: RAN5#92 (Aug-21); Option 2 13: RAN5#93 (Nov-21); Option 2 14: RAN5#94 (Feb-22); Option 2 15: FFS; Option 5 1: FFS; Option 5 2: FFS; Option 3 1: RAN5#79 (May-18); Option 3 1.5: RAN5#80 (Aug-18); Option 3 2: RAN5#81 (Nov-18); Option 3 3: RAN5#82 (Feb-19); Option 3 4: RAN5#83 (May-19); Option 3 5: RAN5#84 (Aug-19); Option 3 6: RAN5#85 (Nov-19); Option 3 7: RAN5#86 (Feb-20); Option 3 8: RAN5#87 (May-20); Option 3 9: RAN5#88 (Aug-20); Option 3 10: RAN5#89 (Nov-20); Option 3 11: RAN5#90 (Feb-21); Option 3 12: RAN5#91 (May-21); Option 3 13: RAN5#92 (Aug-21); Option 3 14: RAN5#93 (Nov-21); Option 3 15: RAN5#94 (Feb-22); Option 4 1: RAN5#93 (Nov-21); Option 4 2: RAN5#94 (Feb-22); Option 7 1: FFS; Option 7 2: FFS; Option 2 1: Contribution Weight per option and phase (used to calculate its contribution for the overall completion)
Area | TS
UE test functions | 38.509 | 100% |  | 100% | 100% | [11 empty] | 100% | 100% | 100% |  | 100% |  | 100% | [11 empty] | 100% | 0% |  | 100% | 5 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 7