## Cover sheet
3GPP TSG-RAN WG5 Meeting #94-e | [10 empty] | R5-220026
Electronic Meeting, Feb 21 – Mar 4, 2022
Agenda Item: | 7.4.2
Source: | Rapporteurs (China Mobile, China Telecom, China Unicom)
Title: | WP - UE Conformance Test Aspects for LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39
Work item code: | DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At RAN#94e meeting in December 2021, a Release 17 work item for LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 was approved [1]. The objective of this work item is to define the UE conformance requirements corresponding to WID on LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 UE with Unique identifier 940089. This work item will cover RF conformance test specifications with LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+95%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+95%)
FR1 |  | 100% (+95%)
FR2 |  | 100% (+95%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
NR RF/RRM
RF test cases | 38.521-1 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5 References
[1] RP-213036 | New WID on UE Conformance Test Aspects for LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance Test Aspects for LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-UEConTest
WP Scope: |  | UE Conformance Test Aspects for LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 (UID-940089) | [12 empty] | vs Area
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 100% (+95%) | 100% (+95%)
[14 empty] | 9 (+6) | 9 (+6)
[14 empty] | 1 | 1
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.521-1 | 5.4.2 | Channel raster | Updated Channel raster for TDD DSS in Band 34/n34 and Band 39/n39 | CMCC | RAN5#97-e (Nov-22) |  | CMCC Dan Song <songdan@chinamobile.com> No need for additional changes since the channel raster for TDD DSS in Band 34/n34 and Band 39/n39 have been updated already in TS 38.521-1 Section 5.4.2 before the kick off of this WI. | 0.5 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
|  | 38.521-1 | 6.4.1 | Frequency error | Updated Frequency error for TDD DSS in Band 34/n34 and Band 39/n39 | CMCC |  | R5-221905 | CMCC Dan Song <songdan@chinamobile.com> | 0 |  |  |  | 100% | 100%
|  | 38.521-1 | 6.4D.1 | Frequency error for UL MIMO | Updated Frequency error for UL MIMO for DSS testing | CMCC |  | R5-221906 | CMCC Dan Song <songdan@chinamobile.com> | 0 |  |  |  | 100% | 100%
|  | 38.521-1 | 6.4A.1 | Frequency error for CA | Updated Frequency error for CA for DSS testing | CMCC |  | R5-221907 | CMCC Dan Song <songdan@chinamobile.com> | 0 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.522 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.522 | 4 | Test case conditions and selection criteria | Update Test case conditions and selection criteria for TDD DSS in Band 34/n34 and Band 39/n39 | CMCC | RAN5#94 (Feb-22) | R5-220041 R5-221849 | CMCC Dan Song <songdan@chinamobile.com> R5-221849 has been submitted under “NR_perf_enh-UEConTest” WI to updated the Test case conditions and selection criteria for TDD DSS NR bands n38, n48, n90 | 0.5 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
3 |  | 38.522 | 4.1 | RF conformance test cases | Update test cases for TDD DSS in Band 34/n34 and Band 39/n39 | CMCC | RAN5#94 (Feb-22) | R5-221849 | CMCC Dan Song <songdan@chinamobile.com> R5-221849 has been submitted under “NR_perf_enh-UEConTest” WI to updated the Test case conditions and selection criteria for TDD DSS NR bands n38, n48, n90 | 0 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.508-1: Common test environment
3 |  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
3 |  | 38.508-1 | 4.6.3 |  | Updated the related RRC information for DSS | CMCC |  | R5-221670 | CMCC Dan Song <songdan@chinamobile.com> R5-221670 has been submitted under “5GS_NR_LTE-UEConTest” WI to Updated the related RRC information for DSS | 0 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.508-2: Common ICS
3 |  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | 0 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
3 |  | 38.508-2 | A.4.3.2 |  | Added PICS for "frequencyShift7p5khz" | CMCC |  | R5-221673 | CMCC Dan Song <songdan@chinamobile.com> R5-221673 has been submitted under “5GS_NR_LTE-UEConTest” WI to add PICS for frequencyShift 7.5khz | 0 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.