## Cover sheet
3GPP TSG-RAN WG5 Meeting #94-e | [10 empty] | R5-220032
Electronic Meeting, Feb 21 - Mar 4, 2022
Agenda Item: | 7.4.2
Source: | CMCC
Title: | Study on 5G NR UE full stack testing for Network Slicing
Work item code: | FS_NR_Slice_Test
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 51% (+16%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 50.7% (+15.7%)
FR1 |  | 50.7% (+15.7%)
FR2 |  | 50.7% (+15.7%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
Study on 5G NR User Equipment (UE) Full Stack Testing for Network Slicing | 38.918
5 References
[1] RP-210371 | New SID: Study on 5G NR UE full stack testing for Network Slicing
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Study on 5G NR UE full stack testing for Network Slicing | [9 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | FS_NR_Slice_Test
WP Scope: |  | TR 38.918 Study on 5G NR User Equipment (UE) Full Stack Testing for Network Slicing | [11 empty] | vs Area
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com |  |  |  |  | WP item completion |  |  | SA Option 2 (SA NR)
TR Resp: |  | Luting Kong, CMCC |  |  | kongluting@chinamobile.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[13 empty] | 50.7% (+15.7%) | 50.7% (+15.7%)
[13 empty] | 29 | 29
[13 empty] | 18.7 | 18.7
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
|  |  | 1 | Scope
|  |  | 2 | Referencs
|  |  | 3 | Definitions of terms, symbols and abbreviations
|  |  | 4 | General
1 |  | 38.918 | 4.1 | Background | CMCC | RAN5#93-e (Nov-21) | R5-213433 |  | 0.1 | 100% | 100% |  | 100% | 100%
2 |  | 38.918 | 4.2 | Study Item Objective | CMCC | RAN5#93-e (Nov-21) | R5-213433 |  | 0.1 | 100% | 100% |  | 100% | 100%
|  |  | 5 | Study on 5G NR UE Full Stack Testing for Network Slicing
|  | 38.918 | 5.1 | Definition of 5G NR UE Full Stack Testing for Network Slicing |  |  |  | sub-clause title | 0
3 |  | 38.918 | 5.1.1 | Definition of Full Stack | CMCC | RAN5#91-e (May-21) | R5-213434 |  | 0.1 | 100% | 100% |  | 100% | 100%
|  | 38.918 | 5.2 | Test Configurations |  |  |  | sub-clause title | 0
4 |  | 38.918 | 5.2.1 | UE Full Stack Network Slicing Test Equipment | CMCC | RAN5#95-e (May-22) | R5-213435 |  | 0.5 | 80% | 80% |  | 80% | 80%
5 |  | 38.918 | 5.2.2 | UE Full Stack Network Slicing Test Equipment Connection Diagrams | CMCC | RAN5#95-e (May-22) | R5-213436 |  | 0.5 | 80% | 80% |  | 80% | 80%
6 |  | 38.918 | 5.2.3 | Network Slicing Configurations | CMCC | RAN5#95-e (May-22) | R5-217266 R5-220179 |  | 0.5 | 70% (+10%) | 70% (+10%) |  | 70% | 70%
7 |  | 38.918 | 5.2.4 | Message and Information Elements Contents | CMCC | RAN5#93-e (Nov-21) | R5-216352 R5-217265 |  | 0.5 | 100% | 100% |  | 100% | 100%
8 |  | 38.918 | 5.2.5 | UE Specific Items | CMCC | RAN5#95-e (May-22) | R5-216352 R5-220179 |  | 0.5 | 70% (+10%) | 70% (+10%) |  | 70% | 70%
|  | 38.918 | 5.3 | Application Simulation |  |  |  | sub-clause title | 0
9 |  | 38.918 | 5.3.1 | APP simulator | CMCC | RAN5#95-e (May-22) | R5-215247 |  | 0.5 | 80% | 80% |  | 80% | 80%
10 |  | 38.918 | 5.3.2 | Test Models |  | RAN5#95-e (May-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
|  | 38.918 | 5.4 | Statistical Analysis |  |  |  | sub-clause title | 0
11 |  | 38.918 | 5.4.1 | Overview of Mapping Application to Network Slicing | CMCC | RAN5#93-e (Nov-21) | R5-215248 |  | 0.5 | 100% | 100% |  | 100% | 100%
12 |  | 38.918 | 5.4.2 | Overview of Application Layer Throughput With Network Slicing | R&S | RAN5#92-e (Aug-21) | R5-221035 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
13 |  | 38.918 | 5.4.3 | Overview of Application Layer Latency With Network Slicing | R&S | RAN5#92-e (Aug-21) | R5-221035 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
|  | 38.918 | 5.5 | Test System Uncertainty and Test Tolerance |  |  |  | sub-clause title | 0
14 |  | 38.918 | 5.5.1 | Test System Uncertainty and Test Tolerance for FR1 testing |  | RAN5#95-e (May-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
|  |  | 6 | Conclusions
15 |  | 38.918 | <clause> | <Title> |  | RAN5#95-e (May-22) |  |  | 0.5 | 0% | 0% |  | 0% | 0%
|  |  | Annex A | Test Procedures
16 |  | 38.918 | A.1 | Purpose of annex |  | RAN5#95-e (May-22) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
|  | 38.918 | A.2 | 5G NR /URSP Configuration and Application Mapping |  |  |  | sub-clause title | 0
|  | 38.918 | A.2.1 | 5G NR /URSP Configuration |  |  |  | sub-clause title | 0
17 |  | 38.918 | A.2.1.1 | 5G NR / URSP Configuration / Signalling | CMCC | RAN5#92-e (Aug-21) | R5-215249 R5-220180 |  | 1 | 100% (+20%) | 100% (+20%) |  | 100% | 100%
|  | 38.918 | A.2.2 | 5G NR / Mapping Application to Network Slicing |  |  |  |  | 0
18 |  | 38.918 | A.2.2.1 | 5G NR / Mapping Application to Network Slicing / DNN | CMCC | RAN5#95-e (May-22) | R5-215250 R5-220181 |  | 1 | 80% (+10%) | 80% (+10%) |  | 80% | 80%
19 |  | 38.918 | A.2.2.2 | 5G NR / Mapping Application to Network Slicing / APP ID | CMCC | RAN5#95-e (May-22) | R5-217264 R5-220182 |  | 1 | 80% (+10%) | 80% (+10%) |  | 80% | 80%
20 |  | 38.918 | A.2.2.3 | 5G NR / Mapping Application to Network Slicing / FQDN | CMCC | RAN5#95-e (May-22) | R5-220177 |  | 1 | 80% (+80%) | 80% (+80%) |  | 80% | 80%
21 |  | 38.918 | A.2.2.4 | 5G NR / Mapping Application to Network Slicing / IP 3 Tuples | CMCC | RAN5#95-e (May-22) | R5-220178 |  | 1 | 80% (+80%) | 80% (+80%) |  | 80% | 80%
22 |  | 38.918 | A.2.2.5 | 5G NR / Mapping Application to Network Slicing / Connection Capabilities |  | RAN5#95-e (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
23 |  | 38.918 | A.2.2.6 | 5G NR / Mapping Application to Network Slicing / URSP Update |  | RAN5#95-e (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
|  | 38.918 | A.3 | 5G NR / Service Performance Testing with Network Slicing |  |  |  | sub-clause title | 0
|  | 38.918 | A.3.1 | 5G NR / Service Performance / Single Network Slicing |  |  |  | sub-clause title | 0
24 |  | 38.918 | A.3.1.1 | 5G NR / Service Performance / Single Application with Single Network Slicing | CMCC | RAN5#95-e (May-22) | R5-215283 |  | 1 | 60% | 60% |  | 60% | 60%
25 |  | 38.918 | A.3.1.2 | 5G NR / Service Performance / Multiple Applications with Single Network Slicing | CMCC | RAN5#95-e (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
|  | 38.918 | A.3.2 | 5G NR / Service Performance / Multiple Network Slicing |  |  |  | sub-clause title | 0
26 |  | 38.918 | A.3.2.1 | 5G NR / Service Performance / Multiple Applications with Multiple Network Slicing | CMCC | RAN5#95-e (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
|  | 38.918 | A.3.3 | 5G NR / Service Performance / URSP Update |  |  |  | sub-clause title
27 |  | 38.918 | A.3.3.1 | 5G NR / Service Performance / Single Network Slicing / URSP update | CMCC | RAN5#95-e (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
28 |  | 38.918 | A.3.3.2 | 5G NR / Service Performance / Multiple Network Slicing / URSP update | CMCC | RAN5#95-e (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
|  |  | Annex B | Applicability
29 |  | 38.918 | <clause> | <Title> | CMCC | RAN5#95-e (May-22) |  |  | 0.3 | 0% | 0% |  | 0% | 0%
|  |  | Annex C | Change history
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on J6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.